## Client Team
Project Roles Table- Client Team | RIBA (2020) Stage
Refer to Glossary of Roles and Expertise
| 0 | 1 | 2 | 3 | 4a | 4b | 5 | 6 | 7
Function | 4a: Design Team; 4b: Contractor
PRE- PROJECT
Client- Senior Responsible Officer SRO | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer
Asset Strategy | 0: Assett Strategy Consultant/ Client Team
Capital Investment | 0: Capital Investment Consultant/ Client team
Place/ Design Definition and Development | 0: Architect/ Design team; 1: Architect/ Design team
PROJECT
Client- Senior Responsible Officer SRO | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer
Vision Development, Definition and Validation | Vision Champion | Vision Champion | Vision Champion/ Validator | Vision Champion/ Validator | Vision Champion/ Validator | Vision Champion/ Validator | Vision Champion/ Validator | Vision Champion/ Validator
Briefing Development/ Client Requirements | 0: Briefing Specialist/ Architect; 1: Briefing Specialist/ Architect
Project Management |  | Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | Project Manager
Cost Management | Cost Consulltant | Cost Consultant | Cost Consultant | Cost Consultant | Cost Consultant | Cost Consultant | Cost Consultant | Cost Consultant
BIM/Digital Information Management | BIM Information Manager | BIM Information Manager | BIM Information Manager | BIM Information Manager | BIM Information Manager | BIM Information Manager | BIM Information Manager | BIM Information Manager
Post Occupancy Evaluation | 0: POE Consultants (MEP/Architect); 6: POE Consultants (MEP/Architect); 7: POE Consultants (MEP/Architect)
Contract Administration | 4b: Project Manager/ Architect; 5: Project Manager/ Architect; 6: Project Manager/ Architect
Compliance Management | Compliance Manager | Compliance Manager | Compliance Manager | Compliance Manager | Compliance Manager | Compliance Manager | Compliance Manager | Compliance Manager
Utilisation/ Operations/Facilities Management | Utilisation/ Operations/FM | Utlilisation/ Operations/FM | Utilisation/ Operations/FM | Utilisation/ Operations/FM | Utilisation/ Operations/FM | Utilisation/ Operations/FM | Utilisation/ Operations/FM | Utilisation/ Operations/FM | Utilisation/ Operations/FM
Quality Monitoring | Quality Champion | Quality Champion | Quality Champion | Quality Champion | Quality Champion | Quality Champion | Quality Champion/ Clerk of Works | Quality Champion/ Clerk of Works | Quality Champion
Other specialist consultant advisors
Planning | Planning Consultant/ Architect (or internal advice) | Planning Consultant/ Architect (or internal advice) | Planning Consultant/ Architect (or internal advice | Planning Consultant/ Architect (or internal advice) | Planning Consultant/ Architect (or internal advice) | Planning Consultant/ Architect (or internal advice) | Planning Consultant/ Architect | Planning Consultant/ Architect
Whole Life/ Carbon Assessment | Whole Life Consultant/ Architect/ MEP | Whole Life Consultant/ Architect/ MEP | Whole Life Consultant/ Architect/ MEP | Whole Life Consultant/ Architect/ MEP | Whole Life Consultant/ Architect/ MEP | Whole Life Consultant/ Architect/ MEP | Whole Life Consultant/ Architect/ MEP | Whole Life Consultant/ Architect/ MEP | Whole Life Consultant/Architect/ MEP
NZC (Carbon) | NZC Champion | NZC Champion | NZC Champion | NZC Champion | NZC Champion | NZC Champion | NZC Champion | NZC Champion | NZC Champion
Soft Landings/Plan for Use | Soft Landings Champion | Soft Landings Champion | Soft Landings Champion | Soft Landings Champion | Soft Landings Champion | Soft Landings Champion | Soft Landings Champion | Soft Landings Champion
Sustainability (including standards based sustainable targets- Passivhaus, BREEAM etc) | MEP Consultant |  | MEP Consultant/ Architect | MEP Consultant/ Architect | MEP Consultant/ Architects | MEP Consultant/ Architect | MEP Consultant/ Architect | MEP Consultan/Architect
Legal Advisor | Lawyer | Lawyer | Lawyer | Lawyer | Lawyer | Lawyer | Lawyer | Lawyer | Lawyer
Financial Advisor
Representatives from funders
Security advisor
Construction advisers
Operational advisers

## Design Team
Project Roles Table- Design Team | RIBA (2020) Stage
Refer to Glossary of Roles and Expertise
| 0 | 1 | 2 | 3 | 4a | 4b | 5 | 6 | 7
Function | 4a: Design Team; 4b: Contractor
Design Services (lead) |  |  | Architect | Architect | Architect | Architect | Architect | Architect | Architect
Architectural Design |  |  | Project Architect | Project Architect | Project Architect | Project Architect | Project Architect | Project Architect
Principal Designer/H&S Advice |  |  | Principal Designer | Principal Designer | Principal Designer | Principal Designer | Principal Designer | Principal Designer
Building services design (MEP) | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant
Building Energy Modelling | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant
Environmental | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant
Structural Design |  |  | CES Engineer | CES Engineer | CES Engineer | CES Engineer | CES Engineer | CES Engineer
Civil & Geotechnical Design |  |  | CES Engineer | CES Engineer | CES Engineer | CES Engineer | CES Engineer | CES Engineer
Fire engineering & strategy |  | Fire Engineer/ architect | Fire Engineer/ Architect | Fire Engineer/Architect | Fire Engineer/ Architect | Fire Engineer/Architect | Fire Engineer/ Architect | Fire Engineer/ Architect

## Other Specialist Services
Project Roles Table - Other Specialist Services | RIBA (2020) Stage
Refer to Glossary of Roles and Expertise
| 0 | 1 | 2 | 3 | 4a | 4b | 5 | 6 | 7
Function | 4a: Design Team; 4b: Contractor
Interior design |  |  |  | Interior Specialist | Interior Specialist | Interior Specialist | Interior Specialist | Interior Specialist | Interior Specialist
Landscape Design |  |  |  | Landscape Architect | Landscape Architect | Landscape Architect | Landscape Architect | Landscape Architect | Landscape Architect
Acoustic design/advice |  |  | Architect | Architect | Architect | Architect | Architect | Architect
Inclusive Design- Access design/advice |  |  | Architect | Architect | Architect | Architect | Architect | Architect
Digital Information management |  |  | Architect | Architect | Architect | Architect | Architect | Architect
Ecology/ Biodiversity | Environmental Manager |  | Environmental Manager | Environmental Manager | Environmental Manager | Environmental Manager | Environmental Manager | Environmental Manager
Highways/transportation design |  |  | CES Engineer | CES Engineer | CES Engineer | CES Engineer | CES Engineer | CES Engineer
Independent Checking | 4b: Independent Checker; 5: Independent Checker; 6: Independent Checker
Specialist Facilities (e.g. Sports Pitch design) |  |  | Architect | Architect | Architect | Architect | Architect | Architect
Sustainability | MEP Consultant |  | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant
SERVICE | 4b: Technical Advisor; 5: Technical Advisor; 6: Technical Advisor
Other Specialist Services