## Introduction
Scottish Futures Trust Transforming The Value of Consultancy Project Team Scope Toolbox Template Medium Size & Complexity Project
Status: For review Version 2.7: January 2023
Project Team
Project Role definition
Pick Lists » |  | Project Roles Table (PRT) » |  | Contractual Tree (CT) »
Functions, Roles and Scopes of Service
New Dimensions & Adding Value (NDAV) »
Design Responsibility Matrix (incorporating Information Exchanges) (DRMIE) »
Task Responsibility Matrix (TRM) »
Meeting Schedule »
Project Stage Notes
Stage 0: Strategic Definition (0 -SD) »
Stage 1: Preparation and Briefing (1 - PB) »
Stage 2: Concept Design (2 - CD) »
Stage 3: Spatial Coordination (3 - SC) »
Stage 4: Technical Design (4 - TD) »
Stage 5: Manufacturing and Construction (5 - MC) »
Stage 6: Handover and Close Out (6 - H) »
Stage 7: Use (7- U) »
Reference
| RIBA Plan of Work 2020 » |  | Uniclass table adoption » | Level of information need »
| Useful Links » |  | Revision Notes »
NB This TVC toolbox example is based upon the RIBA toolbox and stages. It has been shared for industry consultation and review purposes only. A final version is subject to further review and agreement with the RIBA toolbox owner and authors.
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hub North comments: - cross reference to current best practice and guidance, for example briefing and evaluation toolkit to support the vision process. - new roles identified may benefit from definition, for example compliance champion - consider adding critical gateways linked to the end of RIBA stages: critical issues around budget validation - add a glossary of the lesser known roles so that it can be easily understood if the role is required.

## Pick Lists
Setup: Pick Lists
5
|  | List of Roles | Organisation (once known) | Uniclass Role (Ro) | Level of information need - geometrical | Level of information need - alphanumerical | Yes / No
| General | Not decided |  |  | [Not decided] | [Not decided] | TBC
|  | Not required |  |  | TBC | TBC | Yes
|  | All Parties |  |  | Not Applicable | Not Applicable | No
|  | All Designers |  | Ro_50 | Yes- Generic | Yes- Project
[5 empty] | Yes- Developed | Yes- Asset
| Client/Employer | Client/Employer |  |  | Yes- Detailed | Yes- Both
|  | Vision Champion |  |  | Yes- Constructed
Briefing Specialist
Compliance Manager
|  | BIM Information Manager |  | Ro_30_10_42
Whole Life Consultant
NZC Champion
Operations/FM
Soft Landings Champion
|  | Client Ops/FM |  | Ro_30_50_61
Technical Advisor
Independent Checker
|  | Clerk of Works |  | Ro_30_10_13
Move Manager
| Consultants | Project Manager |  | Ro_30_10_67
Project Controls
Programmer
|  | Contract Administrator/Employer's Agent |  | Ro_30_10_27 Ro_30_10_19
Supervisor (NEC)
Cost Consultant
WLC Assessor
Capital Allowances
Principal Designer
|  | Health & Safety Advisor |  | Ro_50_20_68
BIM Coordinator
Soft Landings Champion
|  | Lead Designer/Consultant |  | Ro_30_50_25
|  | Architect |  | Ro_50_10_03
|  | Conservation Architect/Consultant |  | Ro_70_40
|  | Interior Designer |  | Ro_50_10_43
Other Architectural Services
|  | Lighting Designer |  | Ro_50_10_50
|  | Signage Designer |  | Ro_50_10_80
Façade Specialist
Master planner
|  | Landscape Architect |  | Ro_50_30_47
|  | Interior Designer |  | Ro_50_10_43
Sports Designer
|  | Access Consultant |  | Ro_50_10_01
|  | Catering Consultant |  | Ro_50_10_11
|  | Landscape Architect |  | Ro_50_30_47
Passivhaus Designer
|  | Acoustician |  | Ro_50_20_02
|  | Planning Consultant |  | Ro_70_10_64
|  | CES Engineer |  | Ro_50_20
|  | Structural Engineer |  | Ro_50_20_83
|  | Civil Engineer |  | Ro_50_20_11
|  | Drainage Consultant |  | Ro_50_20_28
Flood Consultant
|  | Geotechnical Engineer |  | Ro_50_20_37
Contamination Consultant
Mining Consultant
|  | Transportation Consultant |  | Ro_70_70
|  | MEP Consultant |  | Ro_50_20_08
|  | Mechanical Engineer |  | Ro_50_20_54
|  | Electrical Engineer |  | Ro_50_20_30
Plumbing Engineer
|  | Water Engineer |  | Ro_50_20_96
BMS/Controls Consultant
|  | IT/AV Engineer |  | Ro_50_20_04
Utilities Consultant
Building Physics
NZC Consultant
Commissioning Consultant
|  | Fire Engineer/Consultant |  | Ro_50_20_33
Construction Adviser
|  | Sustainability/Environmental Consultant |  | Ro_70_30_85
NZC Consultant
BREEAM Assessor
WELL Assessor
Ecologist(s)
NZC Verifier
Passivhaus Certifier
Others
Other Consultants
| Contractors | Principal Contractor
Buildability Adviser
Design Manager/Coordinator
Social Benefits specialist
| Specialist Contractors | Specialist design contractors
Others
| Uniclass Classification Tables | Project Management (PM) | Elements / Functions (EF) | Roles (Ro) | Activities (Ac) | Systems (Ac) | Products (Pr)
| The following Uniclass table versions have been adopted for use within this project toolbox. Current versions should be used and referenced here when initially developing this toolbox on a new project. | v 1.18 - October 2022 | v1.12 - July 2022 | v1.5 - April 2021 | v1.18 - July 2022 | vx.xx - TBC (if adopted within DMRIE at later design development stage) | vx.xx - TBC (if adopted within DMRIE at later design development stage)
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hub- North comments- new roles champions for vision, net zero, soft landings. Are these all client side functions?
Note on C4: List of Roles: Add the list of Roles which will be required on the Project. NB these can be selected or linked to the Uniclass Roles (Ro).
Note on D4: Enter name of appointed organisation, once known
Note on E4: Uniclass Role Enter Uniclass Role code if required
Note on H4: Yes or No: The values in this pick list are used in the Design Responsibilities and Information Exchange Matrix to determine answers to questions such as "Is a warranty required?".

## PRT
Project Roles Table- Client Team | RIBA (2020) Stage
Refer to Glossary of Roles and Expertise
| 0 | 1 | 2 | 3 | 4a | 4b | 5 | 6 | 7
Function | 4a: Design Team; 4b: Contractor
PRE- PROJECT
Client- Senior Responsible Officer SRO | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer
Asset Strategy | 0: Assett Strategy Consultant/ Client Team
Capital Investment | 0: Capital Investment Consultant/ Client team
Place/ Design Definition and Development | 0: Architect/ Design team; 1: Architect/ Design team
PROJECT
Client- Senior Responsible Officer SRO | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer | Client/Employer
Vision Development, Definition and Validation | Vision Champion | Vision Champion | Vision Champion/ Validator | Vision Champion/ Validator | Vision Champion/ Validator | Vision Champion/ Validator | Vision Champion/ Validator | Vision Champion/ Validator
Briefing Development/ Client Requirements | 0: Briefing Specialist/ Architect; 1: Briefing Specialist/ Architect
Project Management |  | Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | Project Manager
Cost Management | Cost Consulltant | Cost Consultant | Cost Consultant | Cost Consultant | Cost Consultant | Cost Consultant | Cost Consultant | Cost Consultant
BIM/Digital Information Management | BIM Information Manager | BIM Information Manager | BIM Information Manager | BIM Information Manager | BIM Information Manager | BIM Information Manager | BIM Information Manager | BIM Information Manager
Post Occupancy Evaluation | 0: POE Consultants (MEP/Architect); 6: POE Consultants (MEP/Architect); 7: POE Consultants (MEP/Architect)
Contract Administration | 4b: Project Manager/ Architect; 5: Project Manager/ Architect; 6: Project Manager/ Architect
Compliance Management | Compliance Manager | Compliance Manager | Compliance Manager | Compliance Manager | Compliance Manager | Compliance Manager | Compliance Manager | Compliance Manager
Utilisation/ Operations/Facilities Management | Utilisation/ Operations/FM | Utlilisation/ Operations/FM | Utilisation/ Operations/FM | Utilisation/ Operations/FM | Utilisation/ Operations/FM | Utilisation/ Operations/FM | Utilisation/ Operations/FM | Utilisation/ Operations/FM | Utilisation/ Operations/FM
Quality Monitoring | Quality Champion | Quality Champion | Quality Champion | Quality Champion | Quality Champion | Quality Champion | Quality Champion/ Clerk of Works | Quality Champion/ Clerk of Works | Quality Champion
Other specialist consultant advisors
Planning | Planning Consultant/ Architect (or internal advice) | Planning Consultant/ Architect (or internal advice) | Planning Consultant/ Architect (or internal advice | Planning Consultant/ Architect (or internal advice) | Planning Consultant/ Architect (or internal advice) | Planning Consultant/ Architect (or internal advice) | Planning Consultant/ Architect | Planning Consultant/ Architect
Whole Life Assessment | Whole Life Consultant | Whole Life Consultant | Whole Life Consultant | Whole Life Consultant | Whole Life Consultant | Whole Life Consultant | Whole Life Consultant | Whole Life Consultant | Whole Life Consultant
NZC (Carbon) | NZC Champion | NZC Champion | NZC Champion | NZC Champion | NZC Champion | NZC Champion | NZC Champion | NZC Champion | NZC Champion
Soft Landings/Plan for Use | Soft Landings Champion | Soft Landings Champion | Soft Landings Champion | Soft Landings Champion | Soft Landings Champion | Soft Landings Champion | Soft Landings Champion | Soft Landings Champion
Passivhaus Assessment |  |  | Architect | Architect | Architect | Architect | Architect | Architect
Sustainability | MEP Consultant |  | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant
Legal Advisor | Lawyer | Lawyer | Lawyer | Lawyer | Lawyer | Lawyer | Lawyer | Lawyer | Lawyer
Financial Advisor
Representatives from funders
Security advisor
Construction advisers
Operational advisers
BREEAM advisor
Project Roles Table- Design Team | 0: RIBA (2020) Stage
DESIGN TEAM
Design Services (lead) |  |  | Architect | Architect | Architect | Architect | Architect | Architect | Architect
Architectural Design |  |  | Project Architect | Project Architect | Project Architect | Project Architect | Project Architect | Project Architect
Principal Designer/H&S Advice |  |  | Principal Designer | Principal Designer | Principal Designer | Principal Designer | Principal Designer | Principal Designer
Building services design (MEP) | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant
Building Energy Modelling | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant
Environmental | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant
Structural Design |  |  | CES Engineer | CES Engineer | CES Engineer | CES Engineer | CES Engineer | CES Engineer
Civil & Geotechnical Design |  |  | CES Engineer | CES Engineer | CES Engineer | CES Engineer | CES Engineer | CES Engineer
Fire engineering & strategy |  | Fire Engineer/ architect | Fire Engineer/ Architect | Fire Engineer/Architect | Fire Engineer/ Architect | Fire Engineer/Architect | Fire Engineer/ Architect | Fire Engineer/ Architect
OTHER SPECIALIST SERVICES
Interior design |  |  |  | Interior Specialist | Interior Specialist | Interior Specialist | Interior Specialist | Interior Specialist | Interior Specialist
Landscape Design | O |  |  | Landscape Architect | Landscape Architect | Landscape Architect | Landscape Architect | Landscape Architect | Landscape Architect
Acoustic design/advice |  |  | Architect | Architect | Architect | Architect | Architect | Architect
Inclusive Design- Access design/advice |  |  | Architect | Architect | Architect | Architect | Architect | Architect
Digital Information management |  |  | Architect | Architect | Architect | Architect | Architect | Architect
Ecology/ Biodiversity | Environmental Manager |  | Environmental Manager | Environmental Manager | Environmental Manager | Environmental Manager | Environmental Manager | Environmental Manager
Highways/transportation design |  |  | CES Engineer | CES Engineer | CES Engineer | CES Engineer | CES Engineer | CES Engineer
Independent Checking | 4b: Independent Checker; 5: Independent Checker; 6: Independent Checker
Specialist Facilities (e.g. Sports Pitch design) |  |  | Architect | Architect | Architect | Architect | Architect | Architect
Sustainability | MEP Consultant |  | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant | MEP Consultant
SERVICE | 4b: Technical Advisor; 5: Technical Advisor; 6: Technical Advisor
Other Specialist Services

## CT
Contractual Tree
Responsibility Organisation Chart (Design & Build example)
Design Stage RIBA 2-4a (Pre-Novation)
Construction Stage RIBA 4b to 6
Notes

## DMRIE
Design Responsibility Matrix incorporating Information Exchanges | [10 empty] | NB This Schedules details Uniclass Elements/Functions to Sub-Group level. Consultants will be responsible for the design of associated Uniclass Systems and Products.
The Uniclass Elements and Functions (EF) have been listed to Sub-Group level. The design to higher levels of detail (Section and Object), as well as Uniclass System (Ss) and Product (Pr) are deemed to be included as appropriate, once these have been determined as the design development progresses.
* refer to separate guidance tab on level of information need framework. |  | 1- Preparation and Briefing | 2 - Concept Design |  |  |  | 3 - Spatial Coordination |  |  |  | 4a - Technical Design |  |  |  | 4b - Technical Design | [6 empty] | 5 - Manufacturing and Construction |  |  |  | 6 - Handover
Aspect of Design |  | Design Team | Design team |  |  |  | Design team |  |  |  | Design team |  |  |  | Contractor |  |  |  | Contractor/Supply Chain
Uniclass Element | Element |  | Design responsibility (Predecessor) | Support & Contribution (Dependencies) | * Level of information need |  | Design responsibility (Predecessor) | Support & Contribution (Dependencies) | * Level of information need |  | Design responsibility (Predecessor) | Support & Contribution (Dependencies) | * Level of information need |  | Design responsibility (Predecessor) | Support & Contribution (Dependencies) | * Level of information need |  | Contractor's designed portion | * Level of information need |  | Design responsibility (Predecessor) | Support & Contribution (Dependencies) | * Level of information need |  | Design responsibility (Predecessor) | Support & Contribution (Dependencies) | * Level of information need |  | Collateral Warranty required?
[5 empty] | Geometrical | Alphanumerical |  |  | Geometrical | Alphanumerical |  |  | Geometrical | Alphanumerical |  |  | Geometrical | Alphanumerical |  | Geometrical | Alphanumerical |  |  | Geometrical | Alphanumerical |  |  | Geometrical | Alphanumerical
| Capturing early tasks and outputs that will shape stage 2 design (Vision and Objectives, sustainability strategy Net Zero Carbon etc) | Lead Designer and design team
EF_15 | Earthworks and remediation |  | CES Engineer | Architect | Yes- Generic | Yes- Project | CES Engineer | Architect | Yes- Developed | TBC | CES Engineer | Architect | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC | Principal Contractor | Specialist design contractors | Yes- Constructed | TBC
EF_15_10 | Groundworks and earthworks |  | CES Engineer | Architect | Yes- Generic | Yes- Project | CES Engineer | Architect | Yes- Developed | TBC | CES Engineer | Architect | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_20 | Structural elements |  | CES Engineer | Architect | Yes- Generic | Yes- Project | CES Engineer | Architect | Yes- Developed | TBC | CES Engineer | Architect | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_20_05 | Substructure |  | CES Engineer | Architect | Yes- Generic | Yes- Project | CES Engineer | Architect | Yes- Developed | TBC | CES Engineer | Architect | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_20_10 | Superstructure |  | CES Engineer | Architect | Yes- Generic | Yes- Project | CES Engineer | Architect | Yes- Developed | TBC | CES Engineer | Architect | Yes- Detailed | TBC | Specialist design contractors | CES Engineer | Yes- Detailed | TBC | Steel connections | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_25 | Walls & Barrier Systems |  | Architect | CES Engineer | Yes- Generic | Yes- Project | Architect | CES Engineer | Yes- Developed | TBC | Architect | CES Engineer | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_25_10 | Walls |  | Architect | CES Engineer | Yes- Generic | Yes- Project | Architect | CES Engineer | Yes- Developed | TBC | Architect | CES Engineer | Yes- Detailed | TBC | Specialist design contractors | Architect | Yes- Detailed | TBC | Curtain walling | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_25_30 | Openings |  | Architect | MEP Consultant | Yes- Generic | Yes- Project | Architect | MEP Consultant | Yes- Developed | TBC | Architect | MEP Consultant | Yes- Detailed | TBC | Specialist design contractors | Architect | Yes- Detailed | TBC | Specialist installations | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_25_30_25 | Doors |  | Architect | Not decided | Yes- Generic | Yes- Project | Architect | Not decided | Yes- Developed | TBC | Architect | Not decided | Yes- Detailed | TBC | Not decided | Not decided | Yes- Detailed | TBC | Not decided | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_25_30_97 | Windows |  | Architect | Not decided | Yes- Generic | Yes- Project | Architect | Not decided | Yes- Developed | TBC | Architect | Not decided | Yes- Detailed | TBC | Not decided | Not decided | Yes- Detailed | TBC | Not decided | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_30 | Roofs, floor and paving elements |  | Architect | CES Engineer | Yes- Generic | Yes- Project | Architect | CES Engineer | Yes- Developed | TBC | Architect | CES Engineer | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_30_10 | Roofs |  | Architect | CES Engineer | Yes- Generic | Yes- Project | Architect | CES Engineer | Yes- Developed | TBC | Architect | CES Engineer | Yes- Detailed | TBC | Specialist design contractors | Architect | Yes- Detailed | TBC | Roof system | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_30_20 | Floors |  | Architect | CES Engineer | Yes- Generic | Yes- Project | Architect | CES Engineer | Yes- Developed | TBC | Architect | CES Engineer | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_30_25 | Ceilings and soffits |  | Architect | MEP Consultant | Yes- Generic | Yes- Project | Architect | MEP Consultant | Yes- Developed | TBC | Architect | MEP Consultant | Yes- Detailed | TBC | Architect, Specialist design contractors | Architect | Yes- Detailed | TBC | Specialist systems | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_30_30 | Decks |  | Architect | CES Engineer | Yes- Generic | Yes- Project | Architect | CES Engineer | Yes- Developed | TBC | Architect | CES Engineer | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_30_60 | Pavements |  | Architect | CES Engineer | Yes- Generic | Yes- Project | Architect | CES Engineer | Yes- Developed | TBC | Architect | CES Engineer | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_35 | Stairs and ramps |  | Architect | CES Engineer | Yes- Generic | Yes- Project | Architect | CES Engineer | Yes- Developed | TBC | Architect | CES Engineer | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_35_10 | Stairs |  | Architect | CES Engineer | Yes- Generic | Yes- Project | Architect | CES Engineer | Yes- Developed | TBC | Architect | CES Engineer | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_35_20 | Ramps |  | Architect | CES Engineer | Yes- Generic | Yes- Project | Architect | CES Engineer | Yes- Developed | TBC | Architect | CES Engineer | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_40 | Signage, fittings, furnishings and equipment |  | Architect | MEP Consultant | Yes- Generic | Yes- Project | Architect | MEP Consultant | Yes- Developed | TBC | Architect | MEP Consultant | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_40_10 | Signage |  | Architect | MEP Consultant | Yes- Generic | Yes- Project | Architect | MEP Consultant | Yes- Developed | TBC | Architect | MEP Consultant | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_40_20 | Fittings |  | Architect | MEP Consultant | Yes- Generic | Yes- Project | Architect | MEP Consultant | Yes- Developed | TBC | Architect | MEP Consultant | Yes- Detailed | TBC | Specialist design contractors | Architect | Yes- Detailed | TBC | Specialist installations | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_40_30 | Furnishings |  | Architect |  | Yes- Generic | Yes- Project | Architect |  | Yes- Developed | TBC | Architect |  | Yes- Detailed | TBC | Specialist design contractors | Architect | Yes- Detailed | TBC | Specialist installations | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_40_40 | Equipment |  | Architect | MEP Consultant | Yes- Generic | Yes- Project | Architect | MEP Consultant | Yes- Developed | TBC | Architect | MEP Consultant | Yes- Detailed | TBC | Specialist design contractors | Architect | Yes- Detailed | TBC | Specialist installations | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_45 | Flora and fauna elements |  | Architect |  | Yes- Generic | Yes- Project | Architect |  | Yes- Developed | TBC | Architect |  | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_45_20 | Grass and meadow elements |  | Architect |  | Yes- Generic | Yes- Project | Architect |  | Yes- Developed | TBC | Architect |  | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_45_90 | Tree, shrub and herbaceous plant elements |  | Architect |  | Yes- Generic | Yes- Project | Architect |  | Yes- Developed | TBC | Architect |  | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_50 | Waste disposal functions |  | MEP Consultant |  | Yes- Generic | Yes- Project | MEP Consultant |  | Yes- Developed | TBC | MEP Consultant |  | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_50_30 | Above-ground drainage collection |  | MEP Consultant | CES Engineer | Yes- Generic | Yes- Project | MEP Consultant | CES Engineer | Yes- Developed | TBC | MEP Consultant | CES Engineer | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_50_35 | Below-ground drainage collection |  | CES Engineer | MEP Consultant | Yes- Generic | Yes- Project | CES Engineer | MEP Consultant | Yes- Developed | TBC | CES Engineer | MEP Consultant | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_55 | Piped supply functions |  | MEP Consultant |  | Yes- Generic | Yes- Project | MEP Consultant |  | Yes- Developed | TBC | MEP Consultant |  | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_55_20 | Gas supply |  | MEP Consultant |  | Yes- Generic | Yes- Project | MEP Consultant |  | Yes- Developed | TBC | MEP Consultant |  | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_55_30 | Fire-extinguishing supply |  | MEP Consultant |  | Yes- Generic | Yes- Project | MEP Consultant |  | Yes- Developed | TBC | MEP Consultant |  | Yes- Detailed | TBC | Specialist design contractors | MEP Consultant | Yes- Detailed | TBC | Sprinkler installation | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_55_70 | Water supply |  | MEP Consultant |  | Yes- Generic | Yes- Project | MEP Consultant |  | Yes- Developed | TBC | MEP Consultant |  | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_60 | Heating, cooling and refrigeration functions |  | MEP Consultant |  | Yes- Generic | Yes- Project | MEP Consultant |  | Yes- Developed | TBC | MEP Consultant |  | Yes- Detailed | TBC | Specialist design contractors | MEP Consultant | Yes- Detailed | TBC | Installation drawings, plant selection | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_60_40 | Space heating and cooling |  | MEP Consultant |  | Yes- Generic | Yes- Project | MEP Consultant |  | Yes- Developed | TBC | MEP Consultant |  | Yes- Detailed | TBC | Specialist design contractors | MEP Consultant | Yes- Detailed | TBC | Installation drawings, plant selection | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_60_60 | Refrigeration |  | MEP Consultant |  | Yes- Generic | Yes- Project | MEP Consultant |  | Yes- Developed | TBC | MEP Consultant |  | Yes- Detailed | TBC | Specialist design contractors | MEP Consultant | Yes- Detailed | TBC | Installation drawings, plant selection | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_60_80 | Drying |  | MEP Consultant |  | Yes- Generic | Yes- Project | MEP Consultant |  | Yes- Developed | TBC | MEP Consultant |  | Yes- Detailed | TBC | Specialist design contractors | MEP Consultant | Yes- Detailed | TBC | Installation drawings, plant selection | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_65 | Ventilation and air conditioning functions |  | MEP Consultant |  | Yes- Generic | Yes- Project | MEP Consultant |  | Yes- Developed | TBC | MEP Consultant |  | Yes- Detailed | TBC | Specialist design contractors | MEP Consultant | Yes- Detailed | TBC | Installation drawings, plant selection | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_65_40 | Ventilation |  | MEP Consultant |  | Yes- Generic | Yes- Project | MEP Consultant |  | Yes- Developed | TBC | MEP Consultant |  | Yes- Detailed | TBC | Specialist design contractors | MEP Consultant | Yes- Detailed | TBC | Installation drawings, plant selection | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_65_80 | Air conditioning |  | MEP Consultant |  | Yes- Generic | Yes- Project | MEP Consultant |  | Yes- Developed | TBC | MEP Consultant |  | Yes- Detailed | TBC | Specialist design contractors | MEP Consultant | Yes- Detailed | TBC | Installation drawings, plant selection | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_70 | Electrical power and lighting functions |  | MEP Consultant |  | Yes- Generic | Yes- Project | MEP Consultant |  | Yes- Developed | TBC | MEP Consultant |  | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_70_10 | Electrical power generation |  | MEP Consultant |  | Yes- Generic | Yes- Project | MEP Consultant |  | Yes- Developed | TBC | MEP Consultant |  | Yes- Detailed | TBC | Specialist design contractors | MEP Consultant | Yes- Detailed | TBC | Installation drawings, plant selection | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_70_30 | Electricity distribution and transmission |  | MEP Consultant |  | Yes- Generic | Yes- Project | MEP Consultant |  | Yes- Developed | TBC | MEP Consultant |  | Yes- Detailed | TBC | Specialist design contractors | MEP Consultant | Yes- Detailed | TBC | Installation drawings, plant selection | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_70_80 | Lighting |  | MEP Consultant | Architect | Yes- Generic | Yes- Project | MEP Consultant | Architect | Yes- Developed | TBC | MEP Consultant | Architect | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_75 | Communications, security, safety and protection functions |  | MEP Consultant |  | Yes- Generic | Yes- Project | MEP Consultant |  | Yes- Developed | TBC | MEP Consultant |  | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_75_10 | Communication |  | MEP Consultant | Architect | Yes- Generic | Yes- Project | MEP Consultant | Architect | Yes- Developed | TBC | MEP Consultant | Architect | Yes- Detailed | TBC | Specialist design contractors | MEP Consultant | Yes- Detailed | TBC | Specialist systems | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_75_40 | Security |  | MEP Consultant | Architect | Yes- Generic | Yes- Project | MEP Consultant | Architect | Yes- Developed | TBC | MEP Consultant | Architect | Yes- Detailed | TBC | Specialist design contractors | MEP Consultant | Yes- Detailed | TBC | Specialist systems | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_80 | Transport functions |  | MEP Consultant |  | Yes- Generic | Yes- Project | MEP Consultant |  | Yes- Developed | TBC | MEP Consultant |  | Yes- Detailed | TBC |  |  | Yes- Detailed | TBC |  | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
EF_80_49 | Lifts |  | MEP Consultant | Architect | Yes- Generic | Yes- Project | MEP Consultant | Architect | Yes- Developed | TBC | MEP Consultant | Architect | Yes- Detailed | TBC | Specialist design contractors | MEP Consultant | Yes- Detailed | TBC | Contractor design | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
| Other Project Specific Elements Sports pitches |  | Architect | CES Engineer | Yes- Generic | Yes- Project | Architect | CES Engineer | Yes- Developed | TBC | Architect | CES Engineer | Yes- Detailed | TBC | Specialist design contractors | Architect | Yes- Detailed | TBC | Sports pitch system | Yes- Detailed | TBC |  |  | Yes- Constructed | TBC |  |  | Yes- Constructed | TBC
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hub North comments: limited reference to the specific roles and functions of the Lead Designer Reply: Hub-North comments: Stage 1 missing, capturing brief translation feels essential/ co-ordination between briefing team and design team Reply: Hub-North comments: Limited reference to strategic planning around architecture in early design, adjacency planning, site constraints/ dependencies etc Reply: Hub-North comments: limited reference to place in early design and briefing, alignment with other partners and agencies Reply: Hub-north comments: consider town planning and incorporation of NPF4 policy drivers
Note on AF7: The Design Responsibility Matrix cannot deal with the complexity of the many design interfaces encountered on a project. To bring further clarity notes can be added to bring clarity on certain subjects.
Note on B9: Selected Uniclass Codes. Amend to suit particular project requirements
Note on E10: Design responsibility: This is the party that is responsible for this aspect of design at this stage.
Note on F10: Support & Contribution Parties whose contribution and input is required to develop and coordinate the aspect of the design
Note on I10: Design responsibility: This is the party that is responsible for this aspect of design at this stage.
Note on J10: Support & Contribution Parties whose contribution and input is required to develop and coordinate the aspect of the design
Note on M10: Design responsibility: This is the party that is responsible for this aspect of design at this stage.
Note on N10: Support & Contribution: Parties whose contribution and input is required to develop and coordinate the aspect of the design
Note on Q10: Design responsibility: This is the party that is responsible for this aspect of design at this stage.
Note on R10: Support & Contribution: Parties whose contribution and input is required to develop and coordinate the aspect of the design
Note on U10: Contractor's designed portion: This column is for use on a SBCC (or JCT) traditional form of contract using the Contractor’s Designed Portion to allocate discrete aspects of the design to the contractor within the Building Contract. It can be deleted for design and build or contractor-led forms of procurement.
Note on X10: Design responsibility: This is the party that is responsible for this aspect of design at this stage.
Note on Y10: Support & Contribution: Parties whose contribution and input is required to develop and coordinate the aspect of the design
Note on AB10: Design responsibility: This is the party that is responsible for this aspect of design at this stage.
Note on AC10: Support & Contribution: Parties whose contribution and input is required to develop and coordinate the aspect of the design
Note on AF10: Collateral Warranty required? This column is for use to identify aspects of the design where the client may require a Collateral Warranty to be provided by a specialist subcontractor to be identified and incorporated into the Building Contract.

## TRM
NB This schedule is not exhaustive and consultants will provide all services reasonably expected from experienced consultants undertaking the roles detailed on the PRT
| * Refer to Picklist tab for Uniclass tables adopted on this project. |  |  |  |  | 0 - Strategic (Place, Capital Investment and Governance) |  |  | 0 - Strategic Definition |  |  | 1 - Preparation and Briefing |  |  | 2 - Concept Design |  |  | 3 - Spatial Coordination |  |  | 4a - Technical Design |  |  | 4b - Technical Design |  |  | 5 - Manufacturing and Construction |  |  | 6 - Handover |  |  | 7 - Use
[9 empty] | Client/Employer |  |  | Client/Employer |  |  | Project Team |  |  | Project Team |  |  | Project Team |  |  | Contractor (Design & Build) |  |  | Contractor |  |  | Contractor |  |  | Client/Employer
Task | Activity-based outcome? | * Uniclass Activities (Ac) Code & Description | Required information deliverable? | * Uniclass Project Management (PM) Code & Description | Document/ Tools Links | Primary Responsibility | Support & Constribution | Notes/ Questions | Primary Responsibility | Support & Contribution | Notes and questions | Primary Responsibility | Support & Contribution | Notes | Primary Responsibility | Support & Contribution | Notes | Primary Responsibility | Support & Contribution | Notes | Primary Responsibility | Support & Contribution | Notes | Primary Responsibility | Support & Contribution | Notes | Primary Responsibility | Support & Contribution | Notes | Primary Responsibility | Support & Contribution | Notes | Primary Responsibility | Support & Contribution | Notes | Notes
Pre- Project , Strategic Capital Investment & Governance Approach
[5 empty] | NHS Scottish Capital Investment Manual (SCIM) | Client/Employer
Complete Baseline Skillset Tool for construction procurement | No |  | The toolkit generates a report comparing the baseline skillset determined by a project’s complexity with a candidate’s skillset across seven competencies. The full guidance note contains recommendations for dealing with any skills shortages |  | Baseline Skillset Tool for construction procurement | Client/Employer
Estate Strategy/ Capital Investment Plan/ Assett Strategy- Whole life and strategic asset management overview- systems approach- in order to define capital investment programme | Yes |  | TBC |  |  | Client/Employer | Project Lead
Investment hierarchy exercise | Yes |  | preferred option appaisal |  | Property Investment Strategy | Client/Employer
Delivering resilient and sustainable places- Phase 1 assessment |  |  |  |  | The Place Guide | Client/Employer | Project Lead
| yes |  |  |  | SFT Place Guide | Client/Employer | Project Lead
| TBC |  | TBC |  | Place Standard Tool- (Design Version) | Client/Employer | Project Lead
| TBC |  | TBC |  | SFT Place Tool/ Place Standard Tool (Plus design version) | Client/Employer | Project Lead
Whole Life Performance | TBC |  | TBC |  | Whole Life Appraisal Tool | Client/Employer | whole life consultant
Briefing and evaluation- stage 1 | Yes |  | outline objectives for stage 0 |  |  | Client/Employer | Breifing specialist
Defining Project Requirements
Prepare Project Initiation Document (PID) | TBC |  | TBC | [5 empty] | Client/Employer
Complete Baseline Skillset Tool/ Construction Capability Assessment Tool (Scottish Government Construction Procurement). | TBC |  | TBC |  | Baseline Skillset Tool |  |  |  | Client/Employer
Develop Project Requirements: | TBC | Ac_05_00_80 : Strategic brief preparation | TBC | PM_10_20 : Client requirements PM_35 Project performance requirements | Briefing & Evaluation Framework |  |  |  | Client/Employer
Prepare Statement of Needs/Vision | TBC |  | TBC | PM_10_20_82 : Statement of requirements | Briefing & Evaluation Framework |  |  |  | Client/Employer | Briefing Specialist | Dependant upon client capability | Client/Employer | Briefing Specialist
Define Project Outcomes | TBC |  | TBC |  | Briefing & Evaluation Framework |  |  |  | Client/Employer | Briefing Specialist | Dependant upon client capability | Client/Employer | Briefing Specialist
Develop SMART Objectives. | TBC |  | TBC |  | Briefing & Evaluation Framework |  |  |  | Client/Employer | Briefing Specialist | Dependant upon client capability | Client/Employer | Briefing Specialist
Undertake Site Appraisals & conduct Feasibility Studies & Fabric Audits | TBC | Ac_05_10_29 Feasibility study preparation | TBC | PM_10_20_73 : Site appraisals |  |  |  |  | Client/Employer | Design specialist |  | Client/Employer
Develop and confirm Project Budget | TBC |  | TBC | PM_60_50_10 : Budget |  |  |  |  | Client/Employer | Cost Consultant |  | Cost Consultant
Develop and confirm programme parameters | TBC |  | TBC | [5 empty] | Client/Employer
Develop project information requirements - Complete BIM Grading Tool | TBC |  | TBC |  | Scottish Futures Trust BIM Grading Tool |  |  |  | Client/Employer | BIM Information Manager |  | Client/Employer | BIM Information Manager
Develop and confirm Project Governance requirements and procedures | TBC |  | TBC | PM_70_95_34 : Governance strategy information |  |  |  |  | Client/Employer
Define Project constraints and key issues (funding requirements etc) | TBC |  | TBC | [5 empty] | Client/Employer
Define Procurement Strategy (stage 1) | [8 empty] | Cliet/ Employer |  | workshop?
Develop Strategic Business Case | TBC | Ac_05_00_10 : Business case development | TBC | PM_50_30_10 : Business case |  |  |  |  | Client/Employer
Undertake a Whole Life Performance Review/ Approach | [8 empty] | Client/ Employer | Whole Life Aoorausak. Finance | report
Prepare service/ elected members report for sign off | TBC | [7 empty] | Client/Employer
Post Occupancy Evaluation- review/ benchmark
Plan for Use-This includes setting realistic and measurable targets, managing risks to performance and measuring your clients' desired outcomes. | Yes |  | a series of soft landing and validation points |  |  | Client/ employer | Plan for Use specialist/ FM advisor |  | Client/ Employer | Plan for Use Specialist
Brief
Confirm project Vision, Outcomes & SMART Objectives | TBC |  | TBC | [8 empty] | Client/Employer
Develop and confirm project quality aspirations, operational and spatial requirements | TBC |  | TBC | PM_10_80 Space management requirements | [7 empty] | Briefing Specialist
Prepare Project Brief including project budget | TBC | Ac_05_10_65 : Project brief and objectives preparation | TBC | PM_10_20_07 : Brief | [7 empty] | Briefing Specialist | All Parties/ cost consultant | client review and validation required
Ongoing validation and development of Project Brief | TBC |  | TBC | PM_10_20_07 : Brief | [7 empty] | Briefing Specialist
Agree Project Brief derogations | TBC |  | TBC | PM_55_15_65 : Project brief derogations | [10 empty] | All Designers |  | record/ validation
Governance and Approvals
Confirm & approve Project Brief | TBC | Ac_05_10_67 : Project brief and objectives submission | TBC | PM_10_20_07 : Brief | [7 empty] | Client/Employer
Confirm and authorise changes to Project Brief | TBC |  | TBC | PM_10_20_07 : Brief | [10 empty] | Client/Employer |  | report | Client/Employer |  | No changes beyond end of Stage 3
Confirm commitment to adopt LEIP / NZPSBS / PH / UKNZCBS on the project? | [11 empty] | Client/Employer |  |  | client/ Employer |  | technical standards | Client/ Employer |  | No changes beyond end of Stage 3
Ongoing validation to ensure achievement of project outcomes and objectives : regularly check and gain assurance that emerging design is addressing all Project Outcomes & Objectives | TBC |  | TBC | PM_40_60_07 : Benefits realization plan | Briefing & Evaluation Framework | [6 empty] | Client/Employer |  | Vaildation/ Checklist | Client/Employer and Design Team | Vision Champion | report | Client/Employer and Design .team | vision Champion/ | Report | Client/Employer |  |  | Client/Employer |  |  | Client/Employer |  |  | Client/Employer |  |  | Client/Employer
Project Business Case - prepare, maintain and obtain required approvals- OBC and FBC | TBC | Ac_05_00_10 : Business case development | TBC | PM_50_30_10 : Business case |  |  |  |  | Client/Employer |  |  | Client/Employer |  | Validation/ Checklist | Client/Employer |  | report | Client/Employer |  |  | Client/Employer |  |  | Client/Employer |  | TBC Complete/ submitted
Approve Stage Reports & Stage completion | TBC |  | TBC | PM_60_30_80 : Stage end report |  |  |  |  | Client/Employer |  |  | Client/Employer |  | report/ Validation | Client/Employer |  | approval | Client/Employer |  |  | Client/Employer |  |  | Client/Employer
Authorise Project to commence next Stage | TBC |  | TBC | PM_40_50_41 : Internal approval |  |  |  |  | Client/Employer |  |  | Client/Employer |  | Authorise | [5 empty] | Client Validation Point????
Authorise risk/contingency expenditure, within authorised delegation limits | TBC |  | TBC | [11 empty] | Client/Employer |  | authorise | Client/Employer |  |  | Client/Employer |  |  | Client/Employer |  |  | Client/Employer |  |  | Client/Employer
Approve Tender Recommendations for appointment of consultants and contractors | TBC |  | TBC | [5 empty] | Client/Employer |  | Specialist advisers, PM, cost consultant | Client/Employer |  | Consultants' appointments | Client/Employer | Project Manager, All Designers | Surveys, first stage contractor |  |  |  | Client/Employer | Project Manager, All Designers | Contractor
Authorise Project changes via formal Change Control process | TBC |  | TBC | [14 empty] | Client/Employer | Project Manager |  | Client/Employer | Project Manager |  | Client/Employer | Project Manager |  | Client/Employer | Project Manager |  | Client/Employer | Project Manager
Building design Compliance reviews | TBC |  | TBC | PM_70_95_20 : Design compliance review report | [10 empty] | Compliance Manager |  | Review | Compliance Specialist |  |  | Compliance Manager |  |  | Compliance Manager
Arrange & participate in Gateway Reviews | TBC |  | TBC | PM_70_95_33 : Gateway review information |  |  |  |  | Client/Employer | All Parties | Gateway 0 Workshop | Client/Employer | All Parties | Gateway 1 | Client/Employer | All Parties | Gateway 2 | Client | All Parties | participate in Gateway Review 3 | Client/Employer | All Parties | Gateway 3 | [6 empty] | Client/Employer | All Parties | Gateway 4 | Client/Employer | All Parties | Gateway 5
Comply with Project Governance requirements | TBC |  | TBC | PM_70_95_34 : Governance strategy information |  |  |  |  | Client/ Employer | All Parties | Governance Workshop
Project Management
Project Execution Plan (PEP) - prepare & maintain | TBC |  | TBC | PM_40_60_65 : Project execution plan | [7 empty] | Project Manager |  | Plan | Project Manager |  |  | Project Manager |  |  | Project Manager |  |  | Project Manager |  |  | Project Manager |  |  | Project Manager
Project Programme - prepare, monitor and update | TBC |  | TBC | PM_60_30_20 : Contract programme | [7 empty] | Project Manager |  | Programme | Project Manager |  |  | Project Manager | All Parties | validate across the team | Project Manager |  |  | Project Manager |  |  | Project Manager |  |  | Project Manager
Design Programme - prepare, monitor and update | TBC |  | TBC | PM_40_60_26 : Design programme | [10 empty] | Architect | All Designers |  | Architect/ Design Specialist | All Designers and possible specialist product design | link to above and validate across the team | Architect | All Designers |  | Principal Contractor | All Designers
Project Report - prepare (monthly) project reports, providing status update, identifying risks and issues to inform Client decision making | TBC |  | TBC | PM_60_30_66 : Progress report | [7 empty] | Project Manager | All Consultants | Programme | Project Manager | All Consultants |  | Project Manager | All Consultants |  | Project Manager | All Consultants |  | Project Manager | All Consultants, Principal Contractor |  | Project Manager | All Consultants, Principal Contractor |  | Project Manager | All Consultants, Principal Contractor
Project Cost Reports/End of Stage Cost Plans | TBC |  | TBC | PM_60_50_27 : Cost information report | [7 empty] | Cost Consultant | All Consultants | Gateway 2- Interrogate Cost Plan | Cost Consultant | All Consultants |  | Cost Consultant | All Consultants |  | Cost Consultant | All Consultants |  | Cost Consultant | All Consultants, Principal Contractor |  | Cost Consultant | All Consultants, Principal Contractor |  | Cost Consultant | All Consultants, Principal Contractor
Design Reports - prepare (monthly) design progress report for incorporation into Project Report. | TBC | Ac_05_40_91 Technical design submission | TBC | PM_60_30_66 : Progress report | [10 empty] | All Designers |  |  | All Designers |  |  | All Designers |  |  | Principal Contractor | All Designers
Approval Design Reports and authorise project to move to next Stage. | TBC | Ac_05_40_91 Technical design submission | TBC | [8 empty] | Client/Employer |  | Gateway 2- Approval | Client/Employer |  |  | Client/Employer |  | Client Validation | Client/Employer | [5 empty] | Client/Employer |  |  | Client/Employer
Manage formal Change Control procedure | TBC |  | TBC | PM_60_50_19 : Contract change to forecast | [13 empty] | Project Manager | Cost Consultant, All Designers |  | Project Manager | Cost Consultant, All Designers |  | Project Manager | Cost Consultant, Principal Contractor, All Designers |  | Project Manager | Cost Consultant, Principal Contractor, All Designers |  | Project Manager | Cost Consultant, Principal Contractor, All Designers
Administer the Construction Contract | TBC | Ac_05_60_10 Building contract administrating | TBC | PM_60_30_19 : Contract administration information | [19 empty] | Project Manager |  |  | Project Manager |  |  | Project Manager
Attend meetings as detailed on Meeting Schedule | TBC |  |  | PM_60_40 Meetings and records |  |  |  |  | All Parties |  |  | All Parties |  | actions and decisions agreed | All Parties |  |  | All Parties |  | Validation driven-Risks, Quality and values etc | All Parties |  |  | All Parties |  |  | All Parties |  |  | All Parties |  |  | All Parties
Building In Use/ Plan for Use
Build in early considerations of use- refer to Defining Project Requirements | [8 empty] | Client/ Employer
Develop Building In Use requirements | TBC |  | TBC | PM_35_10 : Quality and operational properties performance requirements
Contribute to design process & approve designs with respect to operational requirements | TBC |  | TBC | [11 empty] | Whole Life Consultant | Operations/FM | design/ validation | Whole Life Consultant | Operations/FM | cross validation with design and project reports- above | Whole Life Consultant | Operations/FM |  | Whole Life Consultant | Operations/FM |  | Whole Life Consultant | Operations/FM |  | Whole Life Consultant | Operations/FM
Participate in commissioning, witnessing and defects inspections | TBC |  | TBC | PM_60_90_40 : Site inspection report | [25 empty] | MEP Consultant | All Designers
Arrange and participate in Lessons Learned/ Post Project Review | TBC |  | TBC | PM_60_90_47 : Lessons learned report | Briefing & Evaluation Framework | [24 empty] | Client/Employer | All Parties
Operate and maintain facility | TBC |  | TBC | [29 empty] | Client/Employer | Operations/FM
Maintain Building Manual | TBC |  | TBC | PM_70_85_10 : Building manual | [28 empty] | Client/Employer | Operations/FM
Maintain Health & Safety File | TBC |  | TBC | PM_70_85_40 : Health and safety file | [28 empty] | Client/Employer | Operations/FM
Monitor Building performance and actual energy use | TBC |  | TBC | PM_80_10_12 : Building performance evaluation plan | [25 empty] | Whole Life Consultant | MEP Consultant, Operations/FM |  | Whole Life Consultant | Operations/FM
PM_80_25_26 : Energy performance assessments
Arrange and participate in Post Occupancy Evaluation, verify achievement of project outcomes and share lessons learned | TBC |  | TBC | PM_40_60_62 : Post-occupancy evaluation | Minimum parameters and guidance for POE | [24 empty] | Client/Employer | All Parties
| TBC |  | TBC |  | Briefing & Evaluation Framework
Risk Management
Set up Risk Management Strategy | [11 empty] | Client/ Emmployer
Prepare & Maintain Project Risk Register, review and update at monthly intervals | TBC |  | TBC | PM_60_40_72 : Risk register | [7 empty] | Project Manager |  |  | Project Manager |  | register |  | Project Manager |  | Project Manager |  |  | Project Manager |  |  | Project Manager |  |  | Project Manager
Attend Risk Workshops & reviews, contribute to Project Risk Register | TBC |  | TBC | [8 empty] | All Parties |  | Risk commitments and evaluation defined | All Parties |  | Reviews- Risk commitments and evaluation defined |  | All Parties | validation point | All Parties |  |  | All Parties |  |  | All Parties |  |  | All Parties
Provide quantitative Risk Register information | TBC |  | TBC | [11 empty] | Cost Consultant |  | data |  | Cost Consultant |  | Cost Consultant |  |  | Cost Consultant |  |  | Cost Consultant |  |  | Cost Consultant
Design
Prepare Design Responsibility Matrix | TBC |  | TBC | PM_40_30_24 : Design responsibility matrix | [7 empty] | Project Manager | Design consultant, client | Basis of design appointments- be clear of skills and expertise requirements | Project Manager | All Designers | Develop | Project Manager | All Designers | Develop in collaboration with client | Project Manager | All Designers | Basis of construction contract
Prepare design Team quality management plan | TBC |  | TBC | PM_10_20_69 : Quality plan | Link to CQIC website | [9 empty] | Architect | All Designers | Plan | All Designers | Develop | Review & update | All Designers | Develop | Review & update | Principal Contractor | All Designers | Review & update
Receive and validate Client's Brief | TBC |  | TBC | PM_10_20_07 : Brief |  |  |  |  | All Parties
Ongoing validation to ensure achievement of project outcomes and objectives : regularly check and demonstrate alignment of emerging design with Project Outcomes & Objectives | TBC |  | TBC | PM_40_60_07 : Benefits realization plan | Briefing & Evaluation Framework | [9 empty] | All Designers |  | Validfation | All Designers |  |  | All Designers |  |  | All Designers |  |  | Principal Contractor | All Designers |  | Principal Contractor | All Designers
Participate in design reviews and technical workshops as required | TBC |  | TBC | PM_70_95_20 : Design compliance review report | [10 empty] | All Designers | Client/Employer, Project Manager, Cost Consultant | Workshop | All Designers | Client/Employer, Project Manager, Cost Consultant | design review against objectives | All Designers | Client/Employer, Project Manager, Cost Consultant |  | Principal Contractor | All Designers, Project Manager, Cost Consultant
Develop Stage design proposals (appropriate to role/discipline) | TBC | Ac_05_30_25 : Definition design development Ac_05_40_89 Technical design report preparation | TBC | PM_40_50_21 : Design submittals | [10 empty] | All Designers |  |  | All Designers |  |  | All Designers | Specialist design contractors |  | Principal Contractor | All Designers, Specialist design contractors
Stakeholder, client engagement | TBC |  | TBC | PM_10_20_75 : Stakeholder engagement plan |  |  |  |  | Client/Employer | All Parties |  | All Parties |  |  | All Parties |  |  | All Parties | [5 empty] | All Parties |  |  | All Parties |  |  | All Parties
Coordination of design | TBC |  | TBC | PM_40_40_15 : Coordination drawings | [10 empty] | Architect | All Designers | Design | Architect | All Designers | Architect Lead Designer role | Architect | All Designers | Architect Lead Designer role | Principal Contractor | All Designers
Prepare Accommodation Schedule (utilisation) from Client Brief and client requirements | TBC |  | TBC | PM_10_80_10 : Accommodation and layout plan | [7 empty] | Briefing Specialist |  | Strategic requirements | Architect
Co-ordinate building services designs | TBC |  | TBC | PM_40_40_15 : Coordination drawings | [10 empty] | MEP Consultant |  | Design | MEP Consultant |  |  | MEP Consultant |  |  | MEP Consultant | Specialist design contractors
Consider and advise on opportunities for Modern Methods of Construction (MMC) | TBC |  | TBC | [8 empty] | Briefing Specialist | Design specialists, Whole Life Consultant |  | All Designers |  | advice
Space Planning (including adjacencies, flow, etc) | TBC |  | TBC | PM_10_80_80 : Space plan | [7 empty] | Briefing Specialist | Design specialists, Whole Life Consultant |  | Architect |  | Table | Architect | MEP Consultant, Principal Designer |  | Architect
Develop Access & Maintenance strategies | TBC |  | TBC | PM_40_20_01 : Access and maintenance strategy | [10 empty] | Architect | MEP Consultant, Principal Designer, Operations/FM | strategy | Architect | MEP Consultant, Principal Designer, Operations/FM |  | Architect | MEP Consultant, Principal Designer, Operations/FM |  | Architect | MEP Consultant, Principal Designer, Operations/FM, Contractor
Prepare Room Data Sheets | TBC |  | TBC | PM_40_30_70 : Room data | [13 empty] | Architect | MEP Consultant |  | Architect | MEP consultant
Prepare Internal room elevations | TBC |  | TBC | PM_40_40_27 : Elevation drawings | [16 empty] | Architect | MEP consultant
Respond to site queries | TBC |  | TBC | PM_60_50_88 : Technical query | [19 empty] | All Designers |  |  | All Designers |  |  | All Designers
Prepare SER | TBC |  | TBC | [17 empty] | CES Engineer
Calculate gross and net internal floor areas | TBC |  | TBC | PM_40_30_70 : Room data | [10 empty] | Architect |  | data | Architect |  |  | Architect
Develop Fire Strategy & contribute design to design solutions | TBC |  | TBC | PM_40_20_30 : Fire safety strategy | [10 empty] | Architect | All Designers | design strategy | Architect | All designers | link to design review- above | Architect | All designers |  | Architect | All designers, Contractor
Develop Acoustic Strategy & contribute to design solutions | TBC |  | TBC | PM_40_20_02 : Acoustic strategy | [10 empty] | Architect | All Designers | design strategy | Architect | All designers | link to design review- above | Architect | All designers |  | Architect | All designers, Contractor
Develop design solutions/concepts to achieve sustainability/net zero carbon requirements. | TBC |  | TBC | PM_40_20_85 : Sustainability strategy | [10 empty] | MEP Consultant | All Designers | design | MEP Consultant | All Designers | link to design review- above | MEP Consultant | All Designers |  | MEP Consultant | All Designers, Contractor
Provide deliverability and buildability advice and support to the design team, advising on construction methodologies and techniques | TBC |  | TBC
Prepare construction phasing and delivery strategies | TBC |  | TBC
Review contractor design portions and confirm compliance with Specifications/Works Information | TBC |  | TBC | [20 empty] | All Designers
Review Contractor's alternative proposals and make recommendations for acceptance/rejection | TBC |  | TBC | [20 empty] | All Designers
Review Contractor's as-constructed information for compliance, accuracy and completeness | TBC |  | TBC | PM_70_90 : Record information | [25 empty] | All Designers
Develop the building services proposals that meet the client brief, in accordance with the contents of BSRIA BG6/2018 'A Design Framework for Building Services | TBC |  | TBC | [11 empty] | MEP Consultant |  | Design and Build proposals | MEP Consultant |  |  | MEP Consultant |  |  | MEP Consultant
Produce Energy Performance Certificate | TBC |  | TBC | PM_80_10_25 : Energy performance certificate | [19 empty] | MEP Consultant
Undertake Interstitial condensation calculations baseline | TBC |  | TBC | [17 empty] | Architect
Develop and confirm ICT strategy | TBC |  | TBC | PM_40_20_43 : Information and communications technology (ICT) strategy |  |  |  |  | Client/Employer |  |  | Client/Employer |  |  | Client/Employer | MEP Consultant | report | Client/Employer | MEP Consultant |  | Client/Employer | MEP Consultant |  | Specialist design contractors | MEP Consultant
Liaise with utility providers and develop site utilities requirements and strategies. Obtain quotations on Client's behalf | TBC |  | TBC | [11 empty] | MEP Consultant |  | Data and strategy | MEP Consultant |  |  | MEP Consultant |  |  | MEP Consultant |  |  | Principal Contractor | MEP Consultant
Information Management
Prepare Exchange Information Requirements (EIR) | TBC |  | TBC | PM_10_20_28 : Exchange information requirements | Scottish Futures Trust BIM Portal Guidance |  |  |  | BIM Information Manager |  |  | BIM Information Manager
Prepare Standard Information Management Plan (SIMP) | TBC |  | TBC |  | Standard Information Management Plan V2 | [6 empty] | BIM Information Manager
Prepare BIM Execution Plan | TBC |  | TBC | PM_40_60_08 : BIM execution plan | Scottish Futures Trust BIM Portal Guidance | [9 empty] | Architect | Information Coordinator | Plan
Coordinate & Federate BIM model | TBC |  | TBC | PM_40_60_31 : Federated coordination models | [13 empty] | Architect |  | Information Coordinator role | Architect |  | Information Coordinator role | Architect |  | Information Coordinator role | Architect |  | Information Coordinator role | Architect |  | Information Coordinator role
Incorporate Contractor design portions, as-constructed information and any applicable Client items into BIM model | TBC |  | TBC | [26 empty] | Architect
Provide, maintain and manage Common Data Environment | TBC |  | TBC | [11 empty] | Client/Employer | BIM Information Manager | report | Client/Employer | BIM Information Manager |  | Client/Employer | BIM Information Manager |  | Client/Employer | BIM Information Manager |  | Client/Employer | BIM Information Manager |  | Client/Employer | BIM Information Manager |  | Client/Employer | BIM Information Manager
Validate BIM Model at each design stage | TBC |  | TBC | PM_40_60_39 : Information validation | [10 empty] | BIM Information Manager |  | validate | BIM Information Manager |  |  | BIM Information Manager |  |  | BIM Information Manager | [5 empty] | BIM Information Manager
Prepare BIM requirements in contractor tender documents and participate in contractor procurement process and evaluation | TBC |  | TBC | PM_40_60_64 : Pre-appointment BIM execution plan | [16 empty] | BIM Information Manager
Prepare as constructed information | TBC |  | TBC | PM_70_90 : Record information | [25 empty] | All Designers, Principal Contractor, Specialist design contractors
Update and finalise BIM model with as constructed information | TBC |  | TBC | PM_40_60_33 : Federated information models | [25 empty] | BIM Coordinator | All Designers
Maintain & manage BIM model | TBC |  | TBC | PM_40_60_33 : Federated information models | [28 empty] | Client/Employer | BIM Information Manager, Operations/FM
Statutory Consents
Undertake strategic appraisal/place standard review to inform statutory requirements | [11 empty] | ¦Planning | All Parties | Workshop | Architect
Develop manage and coordinate Consenting Strategy | TBC |  | TBC | PM_40_50_03 : Approvals and assurance plan | [10 empty] | Architect | Planning Consultant | strategy
Pre-Consultation Agreement with Planners | TBC |  | TBC | PM_40_20_63 : Planning strategy | [10 empty] | Architect | Planning Consultant | notes/ advice
Pre-Consultation with Planners | TBC |  | TBC | [11 empty] | Architect | Planning Consultant | consultation
Prepare Proposal of Application Notice (PAN) & manage PAC process | TBC |  | TBC | [11 empty] | Architect | Planning Consultant | application
Pre-Application Consultation | TBC |  | TBC | PM_40_20_63 : Planning strategy | [13 empty] | Architect | All Designers/ client | Client/ PM overvuew
Prepare Planning Submission | TBC | Ac_05_30_64 Planning preparation | TBC | PM_40_50_63 : Planning application | [13 empty] | Architect | All Designers
Submit Planning Submission & liaise with Planners | TBC |  | TBC | PM_40_50_63 : Planning application | [13 empty] | Architect |  | feed into programme/ design risk???
Manage the purification of all Planning conditions | TBC |  | TBC | PM_40_50_64 : Planning conditions information | [16 empty] | Architect | All Parties |  | Architect | All Parties |  | Architect | All Parties |  | Architect | All Parties |  | Architect | All Parties
Agree Section 75 Agreement | TBC |  | TBC | [17 empty] | Client/Employer | Architect
Prepare Building Warrant submissions | TBC |  | TBC | PM_40_50_10 : Building codes application | [16 empty] | All Designers |  |  | All Designers
Prepare application and obtain CAR Licence from SEPA | TBC |  | TBC
Coordinate Statutory approvals process | TBC |  | TBC | PM_40_50_10 : Building codes application | [16 empty] | Compliance Manager
Obtain Building Warrants | TBC |  | TBC | PM_40_50_12 : Building codes approval
Substructure & drainage | TBC |  | TBC | [20 empty] | CES Engineer
Superstructure | TBC |  | TBC | [20 empty] | CES Engineer
Envelope | TBC |  | TBC | [20 empty] | Architect
Fire | TBC |  | TBC | [20 empty] | Architect
Internal | TBC |  | TBC | [20 empty] | Architect
Services | TBC |  | TBC | [20 empty] | MEP Consultant
Landscape | TBC |  | TBC | [20 empty] | Architect
Others | TBC |  | TBC
Prepare structural calculations & SER | TBC |  | TBC | [20 empty] | CES Engineer
Road Construction Consent (RCC), Temporary Road Orders (TRO) etc | TBC |  | TBC | [20 empty] | CES Engineer
Prepare Road Safety Audit | TBC |  | TBC | PM_30_30_72 : Road safety audit report | [19 empty] | CES Engineer |  | Stage 1 |  |  |  | Principal Contractor | CES Engineer | Stage 2
Flood Risk Assessment/ Adaptation approach | TBC |  | TBC | PM_30_30_29 : Flood risk assessment report | [10 empty] | CES Engineer |  | Assessment | CES Engineer
Prepare Site Drainage & SUDS design | TBC |  | TBC | PM_40_20_24 : Drainage strategy | [10 empty] | CES Engineer |  | Design | CES Engineer
Obtain Completion Certificate from Local Authority | TBC |  | TBC | [26 empty] | Principal Contractor | All Designers | Incl Temporary Occupation Certificate if appropriate
Others | TBC |  | TBC
Health & Safety
Contribute to Health & Safety Strategy as required and to delivering the project in a safe manner. Provide all necessary information to the Principal Designer and comply with the CDM Regulations 2015. | TBC |  | TBC | PM_40_20_36 : Health and safety strategy |  |  |  |  | All Parties |  |  | All Parties |  |  | All Parties |  | strategy | All Parties |  |  | All Parties |  |  | All Parties |  |  | All Parties |  |  | All Parties
Advise Client of their obligations under the Construction Design and Management Regulations (2015). | TBC |  | TBC | [11 empty] | Principal Designer |  | Advice/ report
Appoint Principal Designer | TBC |  | TBC | [8 empty] | Client/Employer
Prepare Design Risk Assessments | TBC |  | TBC | PM_40_30_22 : Designer health and safety risk assessment | [10 empty] | All Designers |  | First Stage tender |  |  |  | All Designers |  | 2nd Stage/Traditional tender
Pre-Construction Information Pack | TBC |  | TBC | PM_60_20_60 : Pre-construction information | [10 empty] | Principal Designer |  | First Stage tender |  |  |  | Principal Designer |  | 2nd Stage/Traditional tender
Prepare & submit F10 | TBC |  | TBC | [17 empty] | Principal Designer
Assess the competency of Consultants & Contractors | TBC |  | TBC | [8 empty] | Client/Employer | Compliance Manager, Project Manager | Design Team & Principal Designer | Client/Employer | Principal Designer, Compliance Manager | report- competencies |  |  |  | Client/Employer | Principal Designer, Compliance Manager | 2nd Stage/Traditional tender
Review and accept Contractor's Construction Stage Health & Safety Plan | TBC |  | TBC | PM_60_70_17 : Construction phase health and safety plan | [19 empty] | Principal Designer
Review Contractor's Risk Assessments & Method Statements (RAMS) | TBC |  | TBC | PM_60_70_18 : Construction phase risk assessment report | [19 empty] | Principal Designer
| TBC |  | TBC | PM_60_20_22 : Construction method statement
Compile Health & Safety File and issue to Client | TBC |  | TBC | PM_70_85_40 : Health and safety file | [25 empty] | Principal Designer | Principal Contractor
Visit site and review Contractor's Health & Safety performance | TBC |  | TBC | PM_60_70_17 : Construction phase health and safety plan | [22 empty] | Principal Designer |  |  | Principal Designer
Building Performance
MEP Systems Performance | TBC |  | TBC | PM_80_10_60 : Performance analysis
Regulation Compliance Analysis | TBC |  | TBC | PM_80_10_60 : Performance analysis | [10 empty] | Compliance Manager |  | assessemnts | Compliance Manager |  |  | Compliance Manager
Thermal Simulation | TBC |  | TBC | [11 empty] | MEP Consultant |  | model | MEP Consultant |  |  | MEP Consultant
Building energy analysis | TBC |  | TBC | PM_40_20_26 : Energy strategy | [10 empty] | MEP Consultant |  | modelling and testing | MEP Consultant |  |  | MEP Consultant
Undertake whole life carbon assessment | TBC |  | TBC | PM_30_30_10 : Carbon calculation report | [10 empty] | MEP Consultant | Architect | measurement and verification plan | MEP Consultant | Architect |  | MEP Consultant | Architect
Complete Whole Life Appraisal Tool | TBC |  | TBC |  | Whole Life Appraisal Tool | [9 empty] | MEP Consultant | Architect | model/ comparison dashboard | MEP Consultant | Architect |  | MEP Consultant | Architect
Sustainability Analysis | TBC | Ac_05_30_85 : Sustainability assessing | TBC | PM_40_20_85 : Sustainability strategy | [10 empty] | MEP Consultant | Architect | report | MEP Consultant | Architect |  | MEP Consultant | Architect
Daylight strategy & analysis | TBC |  | TBC | PM_40_20_21 : Daylight design strategy | [10 empty] | MEP Consultant | Architect | strategy | MEP Consultant | Architect |  | MEP Consultant | Architect
Solar gain and shading strategy & analysis | TBC |  | TBC | PM_35_70_20 : Daylight and shading performance requirements | [10 empty] | MEP Consultant | Architect | stratregy | MEP Consultant | Architect |  | MEP Consultant | Architect
Permeability and air tightness strategy & analysis | TBC |  | TBC | PM_35_70_03 : Airtightness performance requirements | [10 empty] | Architect | MEP Consultant | strategy | Architect | MEP Consultant |  | Architect | MEP Consultant
Acoustic strategy and analysis | TBC |  | TBC | PM_40_20_02 : Acoustic strategy | [10 empty] | Architect | MEP Consultant | strategy | Architect | MEP Consultant |  | Architect | MEP Consultant
Review and monitor building operation and in-use energy performance over initial 24 months operation. Provide advise with respect to building operation to achieve design performance | TBC |  | TBC | PM_80_10_60 : Performance analysis | Minimum parameters and guidance for POE | [24 empty] | MEP Consultant
Passivhaus reviews at each design stage | TBC |  | TBC | [11 empty] | Architect |  | design | Architect |  |  | Architect
Surveys and Investigations
Undertake desktop surveys of available Site Information, identify need, scope & support procurement of surveys and investigations. | TBC |  | TBC | PM_30_10 : Site survey information
Topographical | TBC |  | TBC | PM_30_10_88 : Topographical survey information | [10 empty] | CES Engineer | Architect | data/digital plan
Site Investigation | TBC |  | TBC | PM_30_20_35 : Ground investigation report | [10 empty] | CES Engineer |  | investigation
Site Contamination | TBC |  | TBC | PM_30_20_17 : Contaminated land survey report | [10 empty] | CES Engineer |  | investigation/ analysis
Mining | TBC |  | TBC | [11 empty] | CES Engineer |  | analysis
Drainage | TBC |  | TBC | [11 empty] | CES Engineer |  | investigation/ analysis
Utilities | TBC |  | TBC | PM_30_10_93 : Utilities and services survey information | [10 empty] | MEP Consultant |  | investigation/ analysis
Underground services | TBC |  | TBC | PM_30_20_24 : Underground services survey report | [10 empty] | MEP Consultant |  | investigation/ analysis
Ecological | TBC |  | TBC | PM_30_30_25 : Ecology survey report | [10 empty] | MEP Consultant |  | survey/ analysis
Traffic & Transport | TBC |  | TBC | PM_30_10_90 : Transport feasibility survey information | [10 empty] | CES Engineer |  | survey/ analysis
Site boundary (red/blue line confirmation) | TBC |  | TBC | PM_30_10_80 : Site boundary information | [10 empty] | Architect |  | survey/ analysis
Others | TBC |  | TBC
Cost
Project affordability check | TBC |  | TBC | [5 empty] | Client/Employer |  |  | Cost Consultant
Prepare and analyse Cost Options- elemental cost plan | TBC | Ac_05_10_15 : Cost estimate preparation | TBC | PM_40_20_19 : Cost plan strategy | [7 empty] | Cost Consultant
Prepare and update detailed Elemental Cost Plan | TBC |  | TBC | PM_50_30_18 : Cost model and indicative costing | [7 empty] | Cost Consultant | design team | collaborative review | Cost Consultant | Project Manager/ Design Team |  | Cost Consultant | Project Manager | stage 3 elemental cost plan | Cost Consultant | Project Manager |  | Cost Consultant | Principal Contractor |  | Cost Consultant | Principal Contractor |  | Cost Consultant | Principal Contractor
Prepare and update Cash Flow | TBC |  | TBC | PM_60_50_12 : Cash flow forecast | [7 empty] | Cost Consultant |  |  | Cost Consultant | Project Manager/ Design Team |  | Cost Consultant | Project Manager |  | Cost Consultant | Project Manager |  | Cost Consultant | Principal Contractor |  | Cost Consultant | Principal Contractor |  | Cost Consultant | Principal Contractor
Carry out benchmarking report to confirm project brief and quality can be delivered within budget | TBC |  | TBC | [8 empty] | Cost Consultant | design team | client approval-Gateway 1 | Cost Consultant
Advise on costs of different design options | TBC |  | TBC | [11 empty] | Cost Consultant |  |  | Cost Consultant
Develop a contingency development strategy for the project | TBC |  | TBC | [5 empty] | Client/Employer |  |  | Cost Consultant | design team | client approval- Gateway 1
Value Management/ Engineering studies (if relevant) | TBC |  | TBC | [11 empty] | Cost Consultant | All Designers |  | Cost Consultant | All Designers
Manage consultant fee expenditure | TBC |  | TBC | PM_60_50_50 : Milestone payment schedule | [10 empty] | Project Manager |  |  | Project Manager | Client |  | Project Manager
Prepare pre-tender cost estimate | TBC |  | TBC | PM_60_50_25 : Cost forecast | [16 empty] | Cost Consultant
Complete Community Infrastructure Benchmark Database Project Data Template | TBC |  | TBC |  | Community Infrastructure Benchmark Database | [21 empty] | Cost Consultant | Client/Employer, All Designers |  | Cost Consultant | Client/Employer, All Designers
Valuations/Assessments | TBC |  | TBC | PM_60_50_60 Payment application PM_60_50_62 Payment certificate | [13 empty] | Cost Consultant |  | First Stage services | Cost Consultant |  | First Stage services | Cost Consultant |  |  | Cost Consultant |  |  | Cost Consultant
Agree Variations/Compensation Events | TBC |  | TBC | PM_60_50_16 : Compensation event | [19 empty] | Cost Consultant | Project Manager |  | Cost Consultant | Project Manager |  | Cost Consultant | Project Manager
Monthly Cost Report including statement of final cost | TBC |  | TBC | PM_60_50_27 : Cost information report | [10 empty] | Cost Consultant |  |  | Cost Consultant |  |  | Cost Consultant |  |  | Cost Consultant |  |  | Cost Consultant |  |  | Cost Consultant
Agree Final Account | TBC |  | TBC | [26 empty] | Cost Consultant
Review contractors' claims for extension of time and/or loss and expense [potential additional service] | TBC |  | TBC
Recommend Retention Release at end of Defects Period | TBC |  | TBC | [26 empty] | Cost Consultant
Procurement & Award
Define Procurement Strategy (stage 1)
Review procurement options | TBC |  | TBC | PM_50_50_01 : Procurement strategy | [7 empty] | Client/ Employer | All Parties |  | Project Manager
Contractor Procurement Options Workshop | TBC |  | TBC | [8 empty] | Project Manager | All Parties | review and agree outputs | Project Manager | All Parties
Administer Procurement process, | TBC |  | TBC | [8 empty] | Client/Employer | Project Manager |  | Client/Employer | Project Manager, Cost Consultant | First Stage Service |  |  |  | Client/Employer | Project Manager, Cost Consultant | Second Stage/Traditional
Respond to tender queries | TBC |  | TBC | PM_50_50_10 : Tender enquiry | [7 empty] | Project Manager | Design Team |  | Project Manager | All Designers |  |  |  |  | Project Manager | All Designers
Tender quality/technical response appraisal | TBC |  | TBC | [11 empty] | Project Manager | Client/Employer, All Designers
Tender commercial response appraisal | TBC |  | TBC | [11 empty] | Cost Consultant | All Designers |  |  |  |  | Cost Consultant | All Designers
Procurement Recommendation Report | TBC |  | TBC | PM_50_50_05 : Advance procurement information | [7 empty] | Project Manager | Design Team | Client Approval | Project Manager | Cost Consultant, All Designers |  |  |  |  | Project Manager | Cost Consultant, All Designers
Procure Site Surveys & Investigations | TBC |  | TBC | PM_30_10 : Site survey information | [7 empty] | Client/Employer | All Designers
Prepare tender documentation/Works Information/Employer's Requirements | TBC |  | TBC | PM_50_50_35 : Tender documents | [7 empty] | Project Manager |  |  | Project Manager | Cost Consultant, All Designers |  |  |  |  | Project Manager | Cost Consultant, All Designers
Prepare Bills of Quantities/Activity Schedule/Pricing Document | TBC |  | TBC | PM_60_50_63 Pricing document | [10 empty] | Cost Consultant | All Designers |  |  |  |  | Cost Consultant | All Designers
Attend Post Tender Interviews (as required) | TBC |  | TBC | [8 empty] | All Parties |  |  | All Parties | [5 empty] | All Parties
Procure Client direct items | TBC |  | TBC | PM_50_50_01 : Procurement strategy
Quality
Develop, maintain and implement Client Construction Quality Plan | TBC |  | TBC | PM_10_20_69 : Quality plan | A Guide for Developing a Client Construction Quality Plan |  |  |  | Client/Employer |  |  | Client/Employer |  |  | Client/Employer |  |  | Client/Employer |  |  | Client/Employer |  |  | Client/Employer |  |  | Client/Employer |  |  | Client/Employer |  |  | Client/Employer
Retain 'ownership' of design quality throughout the project stages, maintain the 'Golden Thread'. | TBC |  | TBC | PM_35_10_22 : Design quality performance requirements |  |  |  |  | Client/Employer |  |  | Client/Employer |  | Client Values and Culture- feed into client requirements | All Designers |  |  | All Designers |  |  | All Designers |  |  | All Designers |  |  | All Designers |  |  | All Designers
Develop, maintain and implement Contractor Construction Quality Plan | TBC |  | TBC | PM_60_90 : Contract quality standards information | Link to CQIC website | [18 empty] | Principal Contractor |  |  | Principal Contractor |  |  | Principal Contractor
Regularly attend site and inspect works as they proceed to check quality and compliance with the design drawings and specifications. Frequency of visits to reflect the works being undertaken. Prepare Witten report following every site visit to record any areas of concern, quality issues or areas of non-conformance. | TBC |  | TBC | PM_60_30_77 : Site inspection programme | [22 empty] | All Designers, Clerk of Works, Contract Administrator/Employer's Agent | Project Manager, Compliance Manager |  | All Designers, Clerk of Works | Project Manager, Compliance Manager
Inspect Works as they proceed, providing Inspection Report identifying any comments, non-conformances or areas of concern. | TBC |  | TBC | PM_60_90_40 : Site inspection report
Agree any remedial or corrective action proposals with the Contractor | TBC |  | TBC | PM_70_85_18 : Defects notification information | [22 empty] | Contract Administrator/Employer's Agent | Clerk of Works, All Designers |  | Contract Administrator/Employer's Agent | Clerk of Works, All Designers
Identify any inspection hold points or items to be signed-off prior to being covered | TBC |  | TBC | PM_60_30_77 : Site inspection programme | [22 empty] | Clerk of Works | All Designers, Contract Administrator/Employer's Agent |  | Clerk of Works | All Designers, Contract Administrator/Employer's Agent
Inspect the works on completion and confirm compliance with the Employer's Requirements/Specifications. | TBC |  | TBC | [26 empty] | Contract Administrator/Employer's Agent | Clerk of Works, All Designers, Compliance Manager
Agree snagging/defects schedule with the Contractor. | TBC |  | TBC | PM_70_85_22 : Defects register | [25 empty] | Contract Administrator/Employer's Agent | Clerk of Works, All Designers
Inspect the defects/snagging once notified by the Contractor and confirm if they have been satisfactorily rectified. | TBC |  | TBC | PM_55_15_15 : Compliance statement | [25 empty] | Contract Administrator/Employer's Agent | Clerk of Works, All Designers
Inspect the works at the end of the defects period, prepare defects schedule | TBC |  | TBC | PM_70_85_20 : Defects rectification report | [25 empty] | Contract Administrator/Employer's Agent | Clerk of Works, All Designers
Environmental Impact Assessment
Support the achievement of the client's sustainability objectives and the Scottish Government's commitment for Scotland to become a net-zero society | TBC |  | TBC | [5 empty] | Client/Employer | NZC Champion, Whole Life Consultant, All Parties |  | Client/Employer | NZC Champion, Whole Life Consultant, All Parties | Client Values and culture- feed into client requirements | Client/Employer | NZC Champion, Whole Life Consultant, All Parties |  | Client/Employer | NZC Champion, Whole Life Consultant, All Parties |  | Client/Employer | NZC Champion, Whole Life Consultant, All Parties |  | Client/Employer | NZC Champion, Whole Life Consultant, All Parties |  | Client/Employer | NZC Champion, Whole Life Consultant, All Parties |  | Client/Employer | NZC Champion, Whole Life Consultant, All Parties
Environmental Screening & obtaining ELC Screening Opinion | TBC |  | TBC | [11 empty] | Planning and Environmental | All Designers | Opinion/ Report | Planning & Environmental | All Designers | this may also involve the client and contractor
Environmental Scoping | TBC |  | TBC | [11 empty] | Planning and Environmental | All Designers | Scoping Report | Planning & environmental | All Designers | this may also involve the client and contractor
Environmental Impact Assessment/ HRA (if required) | TBC |  | TBC | PM_30_30_27 : Environmental impact report | [10 empty] | Planning and Environmental | All Designers | Assessment Report | Planning & environmental | All Designers | this may also involve the client and contractor
Commissioning Testing & Handover
Develop Project Commissioning Strategy | TBC |  | TBC | PM_40_20_15 : Commissioning strategy | [7 empty] | Whole Life Consultant | Operations/FM | feed into client requirements | MEP Consultant | Whole Life Consultant, Client Ops/FM | Strategy- Feed into client requirements | MEP Consultant | Whole Life Consultant, Client Ops/FM | Strategy- Feed into client requirements | MEP Consultant | Whole Life Consultant, Client Ops/FM |  | Principal Contractor | Whole Life Consultant, Client Ops/FM, MEP Consultant |  | Principal Contractor | Whole Life Consultant, Client Ops/FM, MEP Consultant |  | Principal Contractor | Whole Life Consultant, Client Ops/FM
Monitor Commissioning Programme | TBC |  | TBC | PM_60_30_13 : Commissioning programme | [22 empty] | MEP Consultant | Whole Life Consultant, Client Ops/FM, MEP Consultant |  | MEP Consultant | Whole Life Consultant, Client Ops/FM, MEP Consultant
Witness Testing & Commissioning of Building systems | TBC |  | TBC | [23 empty] | MEP Consultant | Whole Life Consultant, Client Ops/FM, MEP Consultant |  | MEP Consultant | Whole Life Consultant, Client Ops/FM, MEP Consultant
Attend statutory inspections of completed systems (e.g. life safety systems) | TBC | Ac_05_50_43 : Inspecting | TBC | PM_60_30_77 : Site inspection programme | [22 empty] | MEP Consultant | Whole Life Consultant, Client Ops/FM, MEP Consultant |  | MEP Consultant | Whole Life Consultant, Client Ops/FM, MEP Consultant
Attend site & witness Contractor acoustic tests | TBC |  | TBC | PM_70_75_01 : Acoustic test report | [25 empty] | MEP Consultant
Attend site & witness air tightness tests | TBC |  | TBC | PM_70_15_02 : Airtightness test certificate | [25 empty] | Architect | MEP Consultant
Passivhaus Certification | TBC |  | TBC | [26 empty] | Architect
Review Building O&M Manual prepared by the Contractor | TBC |  | TBC | PM_70_85_56 : Operation and maintenance manual | [25 empty] | All Designers | Client Ops/FM
Participate in Client training | TBC |  | TBC | PM_70_85_91 : Training programme | [25 empty] | Client Ops/FM | All Designers
Confirm Contractor snagging complete and the works are ready for handover. | TBC |  | TBC | PM_70_15_12 : Certificate of making good defects | [25 empty] | Client Ops/FM | All Designers
Attend site and witness Contractor thermal envelope tests | TBC |  | TBC | [26 empty] | MEP Consultant | Client Ops/FM
Note on AK6: The Design Responsibility Matrix cannot deal with the complexity of the many design interfaces encountered on a project. To bring further clarity notes can be added to bring clarity on certain subjects.
Note on A9: Project Tasks: List the specific Tasks which require to be undertaken in development of the design and delivery of the Project. Hint: avoid 'business as usual' tasks, which are inherent in the role or covered by the conditions of contract
Note on J9: Design responsibility: This is the party that is responsible for undertaking the Task at this stage.
Note on K9: Support & Contribution: This the parties who provide input and support to the party with primary responsibility
Note on A105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should this form part of stage 3???
Note on A222: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should this be reworded?

## NDAV
New Dimensions & Adding Value
Initiative | Document Link
Managing Outcomes and Requirements and setting up for success | Briefing & Evaluation Framework
Setting up for success | Baseline Skillset Tool
Improving Construction Quality | https://cqic.org.uk/
Delivering resilient and sustainable places | SFT Place Guide
Place Standard Tool
Asset Performance & Information Management | Standard Information Management Plan V2
Scottish Futures Trust BIM Portal Guidance
Scottish Futures Trust BIM Grading Tool
Minimum parameters and guidance for POE
Carbon & Energy Target (NZC) | Net Zero Public Sector Buildings Standard
Social Benefits | Social value portal
Soft Landings | Delivering Soft Landings
Capturing project data | Community Infrastructure Benchmark Database
Modern Methods of Construction / Design for Manufacture | To follow
Minimum Parameters and Requirements | To follow
Whole Life Performance | Whole Life Appraisal Tool
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hub-North comments: suggest guidance from other UK and Scottish Government bodies on best practice is considered.

## Meeting Schedule
Project Meeting Schedule Template
Meeting | Purpose | RIBA Stage | Frequency | Chaired By | Attendees | Comments
Project Brief Meeting | To review and develop Project Brief | Stage 2 | Fortnightly | Lead Designer/Consultant | Architect, C&S Engineer, MEP Engineer, Landscape Architect, Cost Manager, Project Manager | Other designers and team members as required
User Workshops | To review end user requirements and test design assumptions | Stage 2 | Fortnightly | Lead Designer/Consultant | Architect, C&S Engineer, MEP Engineer, Landscape Architect, Cost Manager, Project Manager | Other designers and team members as required
Stakeholder Meetings | To review external stakeholders interests and requirements | Stage 2, 3, 4 | As required | As appropriate/ Lead Designer | Architect, C&S Engineer, MEP Engineer, Landscape Architect, Cost Manager, Project Manager | Other designers and team members as required
End of Stage Design Reviews | To review design proposals with Project Board and SRO at end of each design stage | Stage 1,2 ,3 | N/A | Client Project Manager | Architect, C&S Engineer, MEP Engineer, Landscape Architect, Cost Manager, Project Manager | Other designers and team members as required
Project Board Meetings | Monthly governance meeting and decision making forum | All stages | Monthly | Client | Project Manager, Cost Manager | Other designers and team members as required
Gateway Reviews | Review meetings to check that project is within tolerance and on course to meet the objectives | All stages | At key stages | Gateway Reviewers | Client, key stakeholders, Project Manager, Cost Manager, designers (as appropriate) | Other designers and team members as required
Planning Meetings | Meetings and liaison with local authority Planners | Stage 2-4 | As required | Architect | As required | Other designers and team members as required
Consultation Events | Public consultation events to support Planning application | Stage 2-3 | As required | Architect | As required | Other designers and team members as required
BIM/Digital Information Review | Meeting to review Digital Information Exchanges and BIM model deliverables | All Stages | Monthly | Information Manager | Architect, C&S Engineer, MEP Engineer, Landscape Architect | Other designers and team members as required
Compliance Review Meetings | Meeting to review compliance of design with Building Standards | Al Stages | Each design stage/as required | Compliance Manager | Architect, C&S Engineer, MEP Engineer, Landscape Architect | Other designers and team members as required
Procurement Workshop | Workshops to review procurement options | Stage 1 & 2 | 2 Workshops | Project Manager | Architect, C&S Engineer, MEP Engineer, Landscape Architect, Client, Cost Manager | Other designers and team members as required
Design Team Technical Meetings | Design team technical review meetings | Stage 2-4 | Fortnightly | Architect | Architect, C&S Engineer, MEP Engineer, Landscape Architect, Cost Manager, Project Manager | Other designers and team members as required
Monthly Project Meeting | Monthly Project progress review meeting | All Stages | Monthly | Project Manager | Architect, C&S Engineer, MEP Engineer, Landscape Architect, Cost Manager, Client | Other designers and team members as required
Cost Meeting | Monthly cost review meeting | All Stages | Monthly | Cost Manager | Client, Project Manager, Architect | Other designers and team members as required
Environmental/Sustainability Meeting | Meeting to review achievement of NZC and environmental targets and objectives | All Stages | as required | MEP Consultant | Architect, C&S Engineer, MEP Engineer, Landscape Architect, Cost Manager, Client | Other designers and team members as required
Passivhaus review meeting | Meeting to review of Passivhaus standard | All Stages | as required | Architect | Architect, C&S Engineer, MEP Engineer, Landscape Architect, Cost Manager, Client | Other designers and team members as required
Risk Workshop | Detailed review of risk register in workshop environment | All Stages | 3-monthly | Project Manager | Architect, C&S Engineer, MEP Engineer, Landscape Architect, Cost Manager, Client | Other designers and team members as required
Value Engineering Workshop | Review of opportunities to achieve best value for money | Stages 2-4 | Monthly | Cost Manager | Architect, C&S Engineer, MEP Engineer, Landscape Architect, Cost Manager, Client | Other designers and team members as required
Contractor Progress Meeting | Contractor progress review meeting | Stage 5 & 6 | Monthly | Project Manager | Architect, C&S Engineer, MEP Engineer, Landscape Architect, Cost Manager, Client | Other designers and team members as required
Other meetings |  | All stages | as required | as appropriate | All team members

## 0 - SD
Multidisciplinary Schedule of Services
0 -Strategic Definition
Stage Outcome
The best means of achieving the Strategic Objectives is confirmed.
Stage Overview
The primary goal of Stage 0 is strategic – it is not about design, but is defining the Client Requirements and outcomes being sought, and to ratify that a construction project, or otherwise, is the best means of achieving them. It focuses on making the right strategic decisions and capturing them in a Strategic Business Case. The SFT Briefing & Evaluation Framework should be adopted and implemented, to establish and define the Project Strategic Objectives. The Project strategies which will be implemented should also be considered at Stage 0, including: - Digital Information exchange (BIM)+B13 - Sustainability and Net Zero Carbon - Modern Methods of Construction - Placemaking - Quality initiatives The Client must complete the SFT BIM Grading Tool to determine if BIM is to be adopted on the Project. Stage 0 is not about design or the practical details - it is prior to the appointment of the design team. An 'intelligent client' function is critical to achieving the successful definition and initiation of a project, as well as Vision Champion/Agent for Change. The Client may possess the required expertise and capacity to undertake tasks involved, or may appoint appropriately skilled and experienced Advisers to support them in this, covering a number of disciplines, including: Project Management, Cost Management, Architectural, Landscape . Competencies can be tested using the Baseline Skillset Tool. The stage involves considering the pros and cons, Project Risks and Project Budget for a range of options and, where necessary, carrying out Site Surveys and corresponding planning appraisals, before undertaking a comparative analysis and recommending and ratifying the best option to meet the Strategic Objectives. This will establish is a building project is the best means of achieving the Strategic Objectives, rather than the detail of any building itself. Consideration should be given to re-using existing assets, rather than replacing or creating new. Similarly, Place considerations and how the project will support the National Performance Framework outcomes must also be considered. The Project Risks consider any circumstances which would affect the delivery of the Strategic Objectives for each option, taking into account that, beyond this stage, substantive costs could be incurred. Examples might include onerous stakeholder constraints that could delay the delivery date, or a costly services diversion that could make an option unviable. The Project Budget – the funds the client has available for all aspects necessary to achieve the Strategic Objectives – will need to be considered for each option. This will include professional fees and, where relevant, land acquisition costs The high-level Spatial Requirements relevant to any option may need to be determined as these can significantly influence the capital or operational investment decision. Stage 0 is also about gleaning Feedback from previous similar projects and gathering insight from Project Stakeholders, making sure that lessons are learned. Knowledge gained in this way can help the briefing process, improve design quality and make the building perform better. The Project Strategies to achieve the Strategic Objectives will be identified, defined, but not fully developed during Stage 0.
Key Stage Outputs& Deliverables
Project Strategic Objectives Project Strategies defined Strategic Risks identified Strategic Business Case Approval Project Budget confirmed Approval to proceed to Stage 1

## 1 - PB
Multidisciplinary Schedule of Services
1 - Preparation and Brief
Stage Outcome
Project Brief approved by the client, and confirmed that it can be accommodated on the site.
Stage Overview
The Statement of Need and outcomes developed during Stage 0 will be developed into a Project Brief during Stage 1. The SFT Briefing & Evaluation Framework should continue to be adopted to support this exercise. In addition to functional and operational requirements, the Project Brief will contain guidance on the Project Outcomes, Sustainability and Environmental Outcomes and Quality Aspirations. These may influence how the client, design and construction teams are assembled to form the project team, as part of the Procurement Strategy, and may dictate the core milestones in the Project Programme. The final design team is generally not in place for Stage 1, although design support should be provided to support the development of the Client Requirements. This can be provided by in-house resource if suitably experienced personnel are available or can be separately procured externally as sperate appointments. In order to achieve best advice and support, it is recommended that the Project Manager and Cost Manager are appointed early in Stage 1. The client will appoint an Information Manager and develop the Employer's Information Requirements (EIR's). and the Standard Information Management Plan (SIMP) Feasibility Studies might be required in order to tease out the full range of briefing considerations and to demonstrate that the Spatial Requirements can be accommodated on the site. In some instances, several options might be prepared, but these options should not be vetted and appraised at this stage. The Client should appoint an Information Manager and prepare the Employer's Information Requirements (EIR's) and Standard Information Management Plan (SIMP)setting out the information to be delivered, standards and process to be adopted during the project design and delivery. The Design Responsibility Matrix and the SFT Toolbox should be prepared so that it is clear what tasks will underpin the production of information and who will undertake them. At this stage of the project development, the detail of the systems which are to be designed will not be known. For this reason, it is recommended that initial DMRIE is based upon Uniclass Elements/Functions, which generally can be established. These can be expanded upon as the design develops during subsequent stages, adopting Uniclass System Codes A key task during Stage 1 is to develop the Procurement Strategy and undertake the procurement of the design services. Whilst the form of the construction contract imam well not have been fully developed, it is essential that this considered, to ensure that the design appointments are appropriate and consistent with this. For example, if a 2-stage design and build for of construction is being considered, then provision for this option, including novation agreements must be made in the design consultant appointments. Consideration must also be given and expected extent of contractor design portions/packages (CDPs) defined, such these add value to the design process and offer value for money. Similarly, the design consultant's responsibilities for monitoring construction quality and site attendance during the construction stage must be clearly defined, to ensure that the 'Golden Thread' is maintained throughout the Project duration. This is to ensure that the requirements are clear and that all design consultants bid on the same basis, avoiding potential for abnormally low tenders (ALTs) and ultimately the required quality standards are achieved throughout all stages of the Project. The Project budget defined at Stage 0 will be developed into an Order of Cost report. A Project Execution Plan should be prepared, and a Digital Execution Plan will allow the design team to set out how they will produce the information. The design team, with appropriate knowledge, skills and experience to deliver the Project Outcomes, needs to be procured, ready for Stage 2 to commence. On some projects, this team may already have been appointed to develop the Project Brief. A comprehensive set of Site Information needs to be sourced, including Site Surveys, ready for Stage 2 to commence. The Project Strategies identified at Stage 0 will be further defined and developed during Stage 1.
Key Stage Outputs & Deliverables
Project Strategic Outcomes & SMART Objectives Project Brief Project Strategies Strategic Risk Register PID Employer's Information Requirements EIR's Site Information Feasibility Studies & Reports Project Scopes of Service and Responsibility Matrix Initial Procurement Startegy Order of Cost Report Project Execution Plan Design Team appointments Approval to proceed to Stage 2

## 2 - CD
Multidisciplinary Schedule of Services
2 - Concept Design
Stage Outcome
Architectural Concept approved by the client and aligned to the Project Brief.
Stage Overview
Stage 2 sets the design concepts for a project. Proposals that align with the Site Information and the Project Brief, including the Spatial requirements, are prepared. it is essential to revisit the brief during this stage and it should be updated and issued as the Final Project Brief as part of the Information Exchange at the end of Stage 2. Regular Design Reviews are used to seek comments from the client and other Project Stakeholders and the design is iterated in response. Any Project Brief Derogations are agreed, or the Project Brief is adjusted to align with the Architectural Concept. Ongoing validation should be undertaken at each stage to ensure achievement of project outcomes and objectives: the client should regularly check and gain assurance that emerging design is addressing all Project Outcomes & Objectives. In response to this, the design team should regularly check and demonstrate to client, alignment of emerging design with Project Outcomes & Objectives. The SFT Briefing & Evaluation Framework should continue to be adopted to support this exercise. The Architectural Concept proposals must also be iterated to accommodate inputs from the design team and from specialist consultants, including the Strategic Engineering requirements (building services, civil and structural engineering) and outline specifications. The proposals must also be coordinated with the Project Strategies, and everything captured in a Stage Report. Depending on the Soft Landings or other strategy adopted, it is essential that the end-users or their representatives are actively involved in the design process. The building services design will be developed as defined in BSRIA BG6 proforma 2. The concept design(s) are produced in line with the initial project brief. The level of detail is limited, but does allow for some key decisions regarding choice of site, building orientation and overall form to be made. A model showing basic building services proposals, connections to incoming services and utilities, locations of plant areas using rectangular blocks, and routes of main pipes, ducts and electrical distribution in such detail as to show the incorporation of the engineering services in the project as a whole and with respect to any treatment zoning across the floor-plate. The design team should also identify any specialist contractor contribution which will be required to support and inform the development of the design proposals. The designers should also consider the elements which contractor design will be required and will be specified as contractor design portions (CDP's), which should be kept to the appropriate level. The design team will identify, scope and develop the requirement for any surveys (e.g. site investigation, asbestos, building condition, environmental & ecological , archaeological etc) In parallel with design activity, a number of other related tasks need to be progressed in response to the emerging design, including a review of the Cost Information, the development of a Construction Strategy, a Maintenance and Operational Strategy and a Health and Safety Strategy and updating of the Project Execution Plan. The Building Energy Model will be developed to test that the proposals will achieve the Client's carbon and energy requirements. The Cost Plan should provide as much information as possible, broken down into elemental and system level. This is to demonstrate that the proposals and Outline Specification are aligned to the Project Budget. The proposals should demonstrate that the Spatial Requirements are being achieved, along with any adjacency requirements. Any non-briefed areas, such as cores, plant space etc must be developed sufficiently to coordinate with the Architectural Concept. Externally, the building must meet the vision of the client, as well as the demands of the local context and environment. Initial Planning Advice and dialogue with Planers should be sought on the suitability of the initial proposal from a planning adviser or the relevant planning department. The Architectural Concept must also be reviewed against the Quality Aspirations, and the route to Building Warrant compliance needs to be clarified and agreed. If a Planning Permission in Principle has been identified, this will generally be progressed during Stage 2. A Stage 2 Design Programme must be prepared, in line with the Project Programme and Responsibility Matrix, to guide the design process and to ensure that the Information Requirements are included in the Stage Report signed off by the client. The Construction Procurement Strategy initiated during Stage 1 should be reviewed and developed. If a 2-Stage strategy is selected, the first stage tender will be undertaken, so that the contractor is appointed in preparation to support the design team in the development of the Stage 3 proposals.
Key Stage Outputs & Deliverables
Concept Design Federated BIM Model Stage 2 Concept Design Report Outline Specifications Project Execution Plan Cost Plan (elemental) Cash Flow Developed Risk Register Design Programme Project Programme BIM Execution Plan Project Strategies developed Procurement Strategy Health & Safety Strategy Building Energy Model PPiP application Approval to Proceed to Stage 3

## 3 - SC
Multidisciplinary Schedule of Services
3 - Spatial Coordination
Stage Outcome
Architectural and engineering information Spatially Coordinated.
Stage Overview
Stage 3 is fundamentally about testing and validating the Architectural Concept, to make sure that the architectural and engineering information prepared at Stage 2 is Spatially Coordinated before the detailed information required to manufacture and construct the building is produced at Stage 4. During Stage 3, the Concept Design is further developed and, crucially, the design work of the core designers is progressed until the spatial coordination exercises have been completed between the main design disciplines. This process may require a number of iterations of the design and different tools may be used, including design workshops Detailed Design Studies and Engineering Analysis are undertaken to ratify the assumptions made during Stage 2 and to layer more detail onto the design. Stage 3 is not about adjusting the Architectural Concept, which should remain substantially unaltered, although detailed design or engineering tasks may require adjustments to make sure that the building is Spatially Coordinated. Changes to the Architectural Concept, for whatever reason, should be agreed via a Change Control Procedure. Design Studies should be aligned to Cost Exercises and the development of the Outline Specification – iterations of the design may be required to ensure the Cost Plan aligns with the Project Budget. Product suppliers and specialist subcontractors might be consulted to test or conclude specific aspects of the design. A Spatially Coordinated design allows each designer, including specialist subcontractors, to finalise their information at Stage 4 (except for minor tweaks at interfaces) without further major iterations of the design. Depending on the Soft Landings or other strategy adopted, it is essential that the end-users or their representatives are actively involved in the design process. The Cost Plan will be further developed during Stage 3, broken down into products and systems. The Cost Consultant may also lead Value Engineering initiatives, supported by all consultants, to achieve alignment of the designs with the budget and offer value for money. The building services design will be developed in accordance with BSRIA BG 6 Proforma 3 – Developed design. By the end of this proforma, the design team has arrived at a design where each discipline has its allocated volumes within the building. From a building services perspective, there is sufficient evidence to show that the services volume is sufficient to contain the building services and it is consistent with all project strategies. Services treatments in rooms and spaces are scheduled in performance terms. By the end of Stage 3, the architectural, building services and structural engineering designs will all have been developed, and will have been checked by the lead designer, with the stage design coordinated between disciplines and the Cost Information aligned to the Project Budget. Depending on the Consenting Strategy, the Planning Application will be prepared based on Stage 3 information and submitted to the local authority. Project Strategies that were prepared during Stage 2 should be developed further and in sufficient detail to allow the client to sign them off once the lead designer has checked each strategy and verified that the Cost Information incorporates adequate allowances. Change Control Procedures should be implemented to ensure that any changes to the Concept Design are properly considered and signed off, regardless of how they are instigated. While specialist subcontractors will undertake their design work at Stage 4, they may provide information and guidance at Stage 3 in order to facilitate a more robust developed design. The Project Strategies need to be updated and additional detail added, and a Building Warrant review undertaken. A Stage 3 Design Programme is created to make sure that the right tasks are undertaken at the right time. At the end of Stage 3, once the client has signed off a Stage Report that captures all the design development work undertaken during the stage, a Planning Application can be submitted. Ongoing validation should be undertaken at each stage to ensure achievement of project outcomes and objectives: the client should regularly check and gain assurance that emerging design is addressing all Project Outcomes & Objectives. In response to this, the design team should regularly check and demonstrate to client, alignment of emerging design with Project Outcomes & Objectives. The SFT Briefing & Evaluation Framework should continue to be adopted to support this exercise.
Key Stage Outputs & Deliverables
Spatially coordinated architectural and engineering designs Stage 3 Design Report Federated BIM Model Developed Cost Plan & Cash Flow Change Control process implemented Developed Risk Register Design Risk Assessments Planning Application Prepared Approval to submit Planning Application to proceed to Stage 4

## 4 - TD
Multidisciplinary Schedule of Services
4 - Technical Design
Stage Outcome
All design information required to manufacture and construct the project
Stage Overview
Stage 4 involves the preparation of all information required to manufacture and construct a building. The architectural, building services and structural engineering designs are further refined to provide technical definition of the project and the design work of specialist subcontractors is developed and concluded. The level of detail produced by each designer will depend on whether the construction on site will be built in accordance with the information produced by the design team or based on information developed by a specialist subcontractor. The Design Responsibility Matrix will set out how these key design interfaces will be managed. Once the work of the design team has been progressed to the appropriate level of detail, as defined in the Design Responsibility Matrix and the Design Programme, specialist subcontractors and/or suppliers undertaking design work will be able to progress their design work. The lead designer and other designers, where required as part of their Schedule of Services, may have duties to review this design information and to ensure that specialist subcontractor design work is integrated with the coordinated design. With complexity of modern buildings, it is not possible to complete the building design without significant contribution from contractor and their specialist design sub-contractors. For this reason, in this Toolbox, Stage 4 is divided: - Stage 4a: Pre-contractor appointment - Stage 4b: Post contractor appointment Stage 4a involves the preparation by the design of the final production information, upon which the Contractor will tender/market test the proposals and prepare their second stage tender. The design team will be novated to the Contractor on acceptance of the Contractor's final tender. Thereafter, through Stage 4b, the design team will be novated to the contractor and will coordinate and incorporate the contractor & their supply chain's designs. Depending on the Soft Landings or other strategy adopted, it is essential that the end-users or their representatives are actively involved in the design process. The building services design will be developed in accordance with BSRIA BG 6 Proforma 4 – Technical design. Proforma 4 covers the building services technical design. Building services design is advanced through detailed calculations or modelling to arrive at an engineering design and layout for each service from which coordination and installation are feasible. Where there is no building services contractor selected, the design will use generic or typical components that may be substituted during equipment procurement, or specified components where no such “equal or equivalent” substitution is permitted. Building services design is coordinated to remove all clashes. Where a building services contractor has been appointed, it is likely that coordination will take place using plant and components that have been, or are going to be, procured by the contractor, and specialist design is incorporated at the same time. Where there is no trade contractor, coordination will be in terms of specified or generic items. Building services design is finalised, including details from specialists, and where changes occur the coordination of the design is checked. BSRIA’s view is that if these activities are allocated to the building services consultant then these almost certainly occur after the building services contractor has been appointed, even if earlier proforma activities do not. On design and build contracts, with design team novated to the contractor, the Client must appoint a team of Technical Advisers or retain some design team services, to check and verify that the contractor's designs are in compliance with the project requirements. Building Warrant Applications will be made by the design team (on behalf of the contractor on design and build) during Stage 4, before work commences on site for the appropriate elements. It will also be necessary to discharge any pre-commencement Planning Conditions. Cost control measures applied during this stage will vary from project to project. These will include the preparation of an updated Cost Plan, bills of quantities or pricing schedules, as defined by the Procurement Strategy. The Building Contract will be agreed and signed a during the stage, to allow Stage 5 to commence. The majority of Project Strategies developed by the design team will be embedded in the Manufacturing Information and/or Construction Information, but some will continue into this stage and beyond. It is not usually necessary to produce a Stage Report for Stage 4. Ongoing validation should be undertaken at each stage to ensure achievement of project outcomes and objectives: the client should regularly check and gain assurance that emerging design is addressing all Project Outcomes & Objectives. In response to this, the design team should regularly check and demonstrate to client, alignment of emerging design with Project Outcomes & Objectives. The SFT Briefing & Evaluation Framework should continue to be adopted to support this exercise.
Key Stage Outputs & Deliverables
Completion of consultant team Design (4.1) Finalised Specifications (NBS) Room Data Sheets and internal elevations prepared Tender Recommendation Report Contractor procured and appointed Design Team novated (if applicable) Specialist Contract design completed (4.2) Updated BIM Model Construction & Manufacturing Information issued Building Warrant submission progressed (Staged) Preconstruction Information pack Planning consent granted Planning Conditions tracker schedule Approval to commence Construction

## 5 - MC
Multidisciplinary Schedule of Services
5 - Manufacturing and Construction
Stage Outcome
Manufacturing, construction and Commissioning completed.
Stage Overview
Construction includes the erection of components that have been fabricated off site. Stage 5 includes the manufacturing and construction of the Building Systems in accordance with the Construction Programme agreed in the Building Contract. The Design Team members will be responsible for responding to Site Queries. They will also regularly visit the site, reporting on Construction Quality, for inspecting the works and monitoring progress. Whilst the Contractor is ultimately responsible for achieving the quality standards detailed in the construction contract, the design team, Clerk of Works (and Supervisor on NEC contracts) will work closely with the contractor to identify defects, agree remedial action and sign-off once rectified. In order to maintain the 'golden thread', it is essential that the parties responsible for the development of the design, retain involvement and responsibility for inspecting and verifying that the works achieve the specified quality standards. The Commissioning Manager will work in close collaboration with the Contractor to agree and coordinate the testing, commissioning and witnessing of the Building systems. Stage 5 concludes with the issue of a Completion certificate, which allows a building to be handed over. The Plan for Use Strategy may require several tasks and activities to be undertaken before and after Completion. A team may be formed to focus on the tasks that will deliver effective performance and operation of the building in use, rather than on completing the construction works. Preparations for handover will include compilation of the Building Manual and the completion of Verified Construction Information, and maybe the delivery of Asset Information. Even the simplest of projects requires a Building Manual. The Contractor will collate as-constructed information from their supply chain, which will be incorporated into the BIM model. NOTE: It is likely that Stages 4 and 5 will overlap. Ongoing validation should be undertaken at each stage to ensure achievement of project outcomes and objectives: the client should regularly check and gain assurance that emerging design is addressing all Project Outcomes & Objectives. In response to this, the Principal contractor with the support of the Design Team should regularly check and demonstrate to client, alignment of emerging solution with Project Outcomes & Objectives. The SFT Briefing & Evaluation Framework should continue to be adopted to support this exercise.
Key Stage Outputs & Deliverables
Health & Safety File Building Manual As constructed information Updated BIM Model Testing, commissioning data Statutory approvals Defects/snagging schedule Practical Completion/Completion Certificate issued

## 6 - H
Multidisciplinary Schedule of Services
6 - Handover
Stage Outcome
Building handed over, Aftercare initiated and Building Contract concluded.
Stage Overview
Stage 6 starts with the building being handed over to the client, with Aftercare initiated and the Building Contract concluded. After the building has been handed over, the construction team rectify any residual defects as promptly as possible. Twelve months after Practical Completion, the Final Certificate will be issued, which concludes the contractual involvement of the design and construction teams. Although Stage 6 commences after the building has been handed over, several tasks may need to commence during Stage 5 to ensure that the handover of the building is as efficient and effective as possible, such as training the users on how to use the Building Systems. In addition to the core contractual obligations to rectify defects, certify Completion and close out the Building Contract, other tasks need to be undertaken. The building services consultant role must include provision for monitoring throughout the initial 12 months period (or longer if required) after the building comes into operation to monitor the building energy use and systems' performance, providing advice and recommendations as appropriate. A Project Performance session needs be facilitated, so that the project team can share their experiences for the benefit of future projects. If required, the Move Manager will coordinate and manage the Client's occupation of the Building. Aftercare tasks need to be initiated and completed in accordance with the Soft Landings or Building In Use Strategy. The project team will monitor the building in use in terms of performance, actual energy use etc, so they can understand how the building is performing and whether the building and its systems are being used as planned. Client, design and construction teams undertaking repeat building types can gain enormously from this process, by identifying trends across several projects.
Key Stage Outputs & Deliverables
Building accepted by Client and handed-over Final BIM model incorporating as constructed information Post Project Lessons Learned/Evaluation End of Defects Certification issued Review of energy use and building performance Building in use evaluation Project Roles concluded

## 7 - U
Multidisciplinary Schedule of Services
7 - Use
Stage Outcome
Building used, operated and maintained efficiently.
Stage Overview
Stage 7 involves the management and operation of the facility throughout its operational life, through adaption, disposal and ultimately demolition. Stage 7 commences on completion of the construction contract and does not therefore involve any of the design or other consultants, unless specifically specified. Post Occupancy Evaluation services are commissioned to determine how the building is performing in use to help fine tune the building and inform future projects. Some client teams will continue to be closely involved during the life of a building, implementing Facilities Management or Asset Management strategies over the course of the building’s lifetime. Asset Information, the Building Manual and these strategies may be updated on a regular basis. During this stage Clients along with appropriate project team members should arrange and participate in Post Occupancy Evaluation, verifying achievement of project outcomes and sharing lessons learned. The SFT Briefing & Evaluation Framework should continue to be adopted to support this exercise. NOTE: Stage 7 starts concurrently with Stage 6
Key Stage Outputs & Deliverables
Post Project Evaluation Post Occupancy Evaluation Updated BIM model to reflect adaptions Client maintains Health & Safety File and Building Manual

## Level of information need
Guidance - Level of information need framework
In alignment with BS EN 17412-1:2020, the level of information need framework should be used to specify how information will be delivered on a project through established: - purposes (i.e. for the use of the information being delivered) - information delivery milestones (e.g. RIBA project stages) - objects organised into one or more breakdown structures (e.g. Uniclass classification assignment) The level of information need framework is further used to define the extent and granularity of the information to be exchanged for specific purposes, across three sub-divisions, namely: Geometrical information The specification of 3D model geometry (object, or sets of objects) using detail, dimensionality, location, appearance, parametric behaviour aspects. Below are a series of high-level geometrical complexity levels and descriptions which are listed with the Picklists tab of this toolbox for selection within the DMRIE table. (*)
Complexity | Description
Generic (Gen) | graphical representation of system or object, dimensionally inaccurate.
Developed (Dev) | graphical representation of specific system or object, location and dimensionally accurate for measurement and other model coordination.
Detailed (Det) | graphical representation of specific system or object, location and dimensionally accurate for measurement, detailed coordination with other models, and fabrication purposes.
Constructed (Con) | graphical representation of installed system or object, location, orientation and dimensionally accurate per agreed construction and project model handover tolerances.
Alphanumerical information The specification of how model geometry (object, or sets of objects) should be identified on a project and what embedded information/ data content is required, namely: - Identification (e.g. Uniclass codes and descriptions used to identify and classify model objects) - Information Content (e.g. asset or technical performance data requirements such as fire, acoustic etc) Below are high-level values which are listed with the Picklists tab of this toolbox for selection within the DMRIE table. (*)
Assignment Value | Description
Yes- Project | alphanumerical project information requirements in model objects
Yes- Asset | alphanumerical asset information requirements in model objects
Yes- Both | alphanumerical project and asset information requirements in model objects
Documentation The specification of required project documentation related to an object, or sets of objects to support processes, decisions, approvals etc. (e.g. space layouts, drawings, reports, photographs, warranties, user manuals etc) Within this toolbox high level information deliverables are initially mapped against scheduled and assigned tasks within the Task Responsibility Matrix tab, using Uniclass project management (PM) codes and descriptions. As the project design evolves the high level deliverables should be further expanded into detailed sets of information delivery plans for each responsibly party. (*) (*) The SFT Standard Information management plan resource supports the use and detailed implementation of the Level of Information need framework principle across all project stages. Refer to the Useful Links tab for further information.

## Useful links
Useful links
1 | NBS BIM Toolkit | https://toolkit.thenbs.com/
2 | Technical article on classification | https://toolkit.thenbs.com/articles/classification
3 | Technical article on levels of definition | https://toolkit.thenbs.com/articles/levels-of-definition
4 | RIBA Plan of Work 2020 Template | 2020RIBAPlanofWorktemplatepdf.pdf (architecture.com)
5 | RIBA Plan of Work 2020 Overview | 2020RIBAPlanofWorkoverviewpdf.pdf (architecture.com)
6 | Uniclass 2015 | Uniclass 2015 ¦ NBS (thenbs.com)
7 | RICS Whole Life Carbon Assessment | Whole Life Carbon Assessment for the Built Environment, 1st edition (rics.org)
8 | BCIS Elemental Standard Form of Cost Analysis (SFCA) | BCIS Construction Form and Documents (rics.org)
9 | The Scottish Futures Trust | Home - Scottish Futures Trust
10 |  | BIM Portal Guidance
11 |  | Standard Information Management Plan (SIMP)
12 |  | Net Zero Public Sector Buildings Standard - Scottish Futures Trust
13 |  | Improving Delivery - Scottish Futures Trust
14 |  | Briefing & Evaluation Framework
15 |  | Place Guide - Scottish Futures Trust
16 |  | Whole Life Appraisal Tool
17 |  | Community Infrastructure Benchmark Database
18 |  | Skills and Capability Toolkit
19 | NBS Uniclass Codes & Descriptions | https://uniclass.thenbs.com/download

## Revision Notes
Revision | Date | Author | Comments
1 | 2021-05-01 | R Smith Currie & Brown | Initial version issued for discussion
2 | 2022-05-01 | R Smith Currie & Brown | General update, incorporating SFT initiatives and roles, RIBA Stage notes developed
2.1 | 2022-06-01 | R Smith Currie & Brown | User notes added. Uniclass Roles and Systems added
2.2 | 2022-07-01 | R Smith Currie & Brown | T Tiernan SFT comments incorporated
2.3 | 2022-09-01 | R Smith Currie & Brown | General update to incorporate SFT comments NDAV sheet added. Digital inofrmation exchange criteria amended to be consistent with SFT SIMP Uniclass Roles data added to Pick Lists
2.4 | 2022-09-01 | R Smith Currie & Brown | Stage 5 & 6 added to DMRIE
2.5 | 2022-11-01 | R Smith Currie & Brown R Tennyson SFT | Ro, PM & Ac codes added RIBA Stages text amended
2.6 | 2022-12-01 | R Smith Currie & Brown | Uniclass Codes updated. PM codes added NDAV added into TRM
2.7 | 2023-01-01 | R Smith Currie & Brown R Tennyson SFT | Uniclass table references added to Picklists Guidance tab added for Level of information need