## Vital Signs
2020-06-17
Contents
Construction Completed
In Construction
In Development
Hub Pipeline
National hub Programme Board - 17 June 2020
Section 2.2 - Vital Signs
Construction Completed
Project Title | Bundle | Territory | TPD | Total Project Cost | Project Status | Primary Participant Organisation | Project Type/Sector | Agreed NPR Date | Financial Close - Planned Completion | Financial Close - Actual Completion | Construction - Actual Start | Construction - Planned Completion | Construction - Actual Completion | Services | Contract Type | Tier 1 Construction Contractor | Other Participant Organisations | Funding Partner | Tier 1 FM Contractor
Aberdeen Community Health Care Village |  | North | Jonathan Christie | 17148538 | Operational (Operational) | NHS Grampian | Health - Primary Care | 2011-03-18 | 2012-03-15 | 2012-03-15 | 2012-04-02 | 2013-11-15 | 2013-11-25 | Education;#4;#Health;#6;#Offices;#11;#Café;#1;#Police Services;#12;#Local Authority Offices;#9;#Community;#3 | DBFM | Morrison | Aberdeen City Council;#1;#Police Scotland;#43 | Aviva | GTFM
Aberdeen Criminal Justice Centre, Kittybrewster |  | North | Jonathan Christie | 10912006 | Operational (Operational) | Police Scotland | Community - Emergency Services | 2011-01-28 | 2013-03-17 | 2013-03-17 | 2013-03-17 | 2014-03-28 | 2014-05-23 | Health;#6;#Police Services;#12 | DBDA | Balfour Beatty | NHS Grampian;#33 | Capitally Funded
Alford Community Campus |  | North | Jonathan Christie | 33678807 | Operational (Operational) | Aberdeenshire Council | Schools SSF Rev - Primary School & Secondary School | 2013-09-01 | 2014-05-30 | 2014-05-30 | 2014-05-30 | 2015-10-02 | 2015-10-09 | Education;#4;#Library;#8;#Leisure;#7;#Community;#3;#Café;#1;#Sports Facilities;#14;#Child Care;#2;#Theatre;#15 | DBFM | Morrison |  | Aviva | GTFM
Allermuir Health Centre (Firrhill) | NHS Lothian Bundle | South East | Gordon Shirreff | 6824000 | Operational (Operational) | NHS Lothian | Health - Major Health | 2013-02-08 | 2016-03-14 | 2016-04-01 | 2016-04-01 | 2017-09-25 | 2017-09-29 | Education;#4;#Health;#6 | DBFM | Graham | West Lothian Council;#55;#City of Edinburgh Council;#8 | Nord LB | Graham
Alyth Primary School |  | East Central | Gordon Shirreff | 9470073.78 | Operational (Operational) | Perth & Kinross Council | Schools - Primary School | 2014-07-23 | 2016-02-02 | 2016-02-02 | 2016-02-02 | 2017-05-05 | 2017-06-16 | Education;#4;#Community;#3 | DBDA | Marshall |  | Capitally Funded
Anderson High School (Lerwick) |  | North | Jonathan Christie | 43040894 | Operational (Operational) | Shetland Islands Council | Schools SSF Rev - Secondary School | 2013-08-29 | 2015-07-29 | 2015-07-29 | 2015-07-29 | 2017-09-07 | 2017-10-06 | Education;#4;#Community;#3 | DBFM | Morrison | Shetland Recreational Trust;#49 | Aviva | Robertson FM
Anderson High School Halls of Residence |  | North | Jonathan Christie | 13787357 | Operational (Operational) | Shetland Islands Council | Schools - Secondary School | 2013-08-29 | 2015-07-29 | 2015-07-29 | 2015-07-29 | 2017-09-07 | 2017-10-06 | Residential;#13 | DBDA | Morrison | Shetland Recreational Trust;#49 | Capitally Funded
Angus Council HQ Refurbishment |  | East Central | Gordon Shirreff | 1483221 | Operational (Operational) | Angus Council | Community - Residential/Building |  | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2017-12-01 | 2017-10-06 | Offices;#11 | DBDA | Robertson |  | Capitally Funded
Ann Street Social Housing |  | East Central | Gordon Shirreff | 2061980 | Operational (Operational) | Clackmannanshire Council | Community - Residential/Building | 2015-03-25 | 2015-07-01 | 2015-07-01 | 2015-07-01 | 2016-03-15 | 2016-03-15 | Residential;#13 | DBDA | Marshall |  | Capitally Funded
Ardrossan Harbourside/Quayside |  | South West | Bill Martin | 2939831 | Operational (Operational) | Irvine Bay Regeneration Company | Community - Community Facility | 2014-01-21 | 2014-07-11 | 2014-07-11 | 2014-07-11 | 2015-06-22 | 2015-06-18 | Offices;#11 | DBDA | Morrison |  | Capitally Funded
Ardrossan Medical Centre |  | South West | Bill Martin | 2423006 | Operational (Operational) | Irvine Bay Regeneration Company | Health - Primary Care | 2013-02-21 | 2013-08-21 | 2013-08-21 | 2013-08-21 | 2014-05-23 | 2014-05-23 | Health;#6 | DBDA | Morrison | Police Scotland;#43 | Capitally Funded
Asset Resource Centre Refurbishment |  | East Central | Gordon Shirreff | 3145081 | Operational (Operational) | Scottish Fire and Rescue Service | Community - Community Facility |  | 2016-06-01 | 2016-01-18 | 2016-06-01 | 2016-08-30 | 2016-08-30 | Emergency Services;#5 | DBDA | Robertson |  | Capitally Funded
Auchinairn/Woodhill Primary School (Thomas Muir) |  | West | Bill Martin | 12644849 | Operational (Operational) | East Dunbartonshire Council | Schools - Primary School | 2015-02-04 | 2015-12-21 | 2015-12-21 | 2016-01-15 | 2017-04-07 | 2017-11-14 | Education;#4 | DBDA | Morgan Sindall |  | Capitally Funded
Ayr Academy |  | South West | Bill Martin | 24170004 | Operational (Operational) | South Ayrshire Council | Schools SSF Rev - Secondary School | 2014-07-25 | 2016-01-07 | 2016-01-07 | 2016-01-07 | 2017-08-04 | 2017-08-04 | Education;#4 | DBFM | Kier |  | Nord LB | FES FM
Baldragon Academy |  | East Central | Gordon Shirreff | 27637720 | Operational (Operational) | Dundee City Council | Schools SSF Rev - Secondary School | 2013-07-24 | 2015-02-17 | 2016-02-26 | 2016-02-26 | 2017-12-12 | 2017-12-12 | Education;#4 | DBFM | Robertson |  | Aviva | Robertson FM
Barrhead High School |  | West | Bill Martin | 22280759 | Operational (Operational) | East Renfrewshire Council | Schools SSF Rev - Secondary School | 2015-01-19 | 2016-03-18 | 2016-03-18 | 2016-03-21 | 2017-08-07 | 2017-08-07 | Education;#4 | DBFM | BAM |  | Aviva | BAM
Bearsden Community Hub |  | West | Bill Martin | 3096780 | Operational (Operational) | East Dunbartonshire Council | Community - Community Facility | 2015-05-06 | 2016-03-18 | 2016-03-18 | 2016-04-04 | 2017-03-03 | 2017-03-03 | Community;#3 | DBDA | CCG |  | Capitally Funded
Bellsmyre (St Peter's PS/Aitkenbar PS/Early Education & Childcare Centre) |  | West | Bill Martin | 9602340 | Operational (Operational) | West Dunbartonshire Council | Schools - Primary School | 2014-02-24 | 2015-06-10 | 2015-06-19 | 2015-06-19 | 2016-07-29 | 2016-08-22 | Education;#4 | DBDA | Morgan Sindall |  | Capitally Funded
Bertha Park High School |  | East Central | Gordon Shirreff | 33047000 | Operational (Operational) | Perth & Kinross Council | Schools SSF Rev - Secondary School | 2015-07-01 | 2017-09-29 | 2017-09-29 | 2017-09-29 | 2019-07-15 | 2019-07-15 | Education;#4 | DBFM | Robertson |  | Aviva | FES FM
Blackburn Partnership Centre | NHS Lothian Bundle | South East | Gordon Shirreff | 8055341 | Operational (Operational) | NHS Lothian | Health - Major Health | 2013-02-08 | 2016-03-14 | 2016-04-01 | 2016-04-01 | 2017-09-18 | 2017-10-04 | Education;#4;#Health;#6;#Leisure;#7;#Library;#8;#Offices;#11 | DBFM | Graham | West Lothian Council;#55;#City of Edinburgh Council;#8 | Nord LB | Graham
Blackhall Gym |  | South East | Gordon Shirreff | 1009376 | Operational (Operational) | City of Edinburgh Council | Schools - Secondary School | 2014-04-07 | 2015-06-01 | 2015-06-01 | 2015-06-01 | 2015-12-12 | 2015-12-12 | Leisure;#7 | DBDA | Morrison |  | Capitally Funded
Blairdardie Primary School | Blairdardie and Carntyne Bundle | West | Bill Martin | 12095852 | Operational (Operational) | Glasgow City Council | Schools SSF Rev - Primary School | 2016-05-02 | 2017-10-18 | 2017-10-23 | 2017-11-06 | 2019-02-08 | 2019-02-08 | TBC;#18;#Education;#4 | DBFM | BAM |  | Nord LB | Robertson FM
Brechin Community Campus (High School) |  | East Central | Gordon Shirreff | 25515858.11 | Operational (Operational) | Angus Council | Schools SSF Cap - Secondary School | 2012-08-08 | 2013-10-14 | 2014-08-28 | 2014-08-28 | 2016-11-01 | 2016-02-16 | Education;#4;#Leisure;#7;#Health;#6 | DBDA | Robertson |  | Capitally Funded
Brimmond Primary School (Formerly Bucksburn) |  | North | Jonathan Christie | 11947583 | Operational (Operational) | Aberdeen City Council | Schools SSF Cap - Primary School | 2013-03-11 | 2014-04-25 | 2014-04-25 | 2014-04-25 | 2015-07-31 | 2015-10-01 | Education;#4;#Child Care;#2;#Community;#3;#Sports Facilities;#14 | DBDA | Ogilvie |  | Capitally Funded
Burntisland Primary School |  | East Central | Gordon Shirreff | 10979196 | Operational (Operational) | Fife Council | Schools - Primary School | 2012-07-16 | 2013-09-18 | 2013-09-04 | 2013-09-04 | 2014-07-07 | 2014-07-03 | Education;#4;#Community;#3 | DBDA | BAM |  | Capitally Funded
Campbeltown High School | Campbeltown and Oban High School Bundle | North | Jonathan Christie | 24377753 | Operational (Operational) | Argyll & Bute Council | Schools SSF Rev - Secondary School | 2014-08-08 | 2016-03-24 | 2016-03-24 | 2016-04-25 | 2018-02-09 | 2018-02-21 | Education;#4;#Sports Facilities;#14;#Leisure;#7 | DBFM | Morrison |  | Aviva | FES FM
Canal Court Housing |  | South West | Bill Martin | 6104400 | Operational (Operational) | North Ayrshire Council | Community - Residential/Building | 2017-05-16 | 2017-07-31 | 2017-08-25 | 2017-07-31 | 2019-02-22 | 2019-03-11 | Residential;#13;#Community;#3 | DBDA | Ashleigh Scotland Ltd
Care Home Ostlers Way |  | East Central | Gordon Shirreff | 5179935 | Operational (Operational) | Fife Council | Community - Residential/Building | 2013-03-11 | 2014-05-19 | 2014-06-09 | 2014-06-09 | 2015-06-26 | 2015-06-26 | Health;#6 | DBDA | Robertson |  | Capitally Funded
Carnegie Primary School Extension |  | East Central | Gordon Shirreff | 1905476.67 | Operational (Operational) | Fife Council | Schools - Primary School | 2013-02-04 | 2015-11-16 | 2015-12-08 | 2015-12-08 | 2016-07-29 | 2016-07-29 | Education;#4 | DBDA | BAM |  | Capitally Funded
Carntyne Primary School | Blairdardie and Carntyne Bundle | West | Bill Martin | 7530120 | Operational (Operational) | Glasgow City Council | Schools SSF Rev - Primary School | 2016-05-02 | 2017-10-18 | 2017-10-23 | 2017-11-06 | 2018-10-25 | 2018-10-19 | Education;#4 | DBFM | BAM |  | Nord LB | Robertson FM
Carrick Leisure Centre |  | South West | Bill Martin | 5156851 | Operational (Operational) | South Ayrshire Council | Community - Leisure/Culture | 2014-12-04 | 2016-01-14 | 2016-01-14 | 2016-01-14 | 2017-03-24 | 2017-03-24 | Leisure;#7 | DBDA | Morrison |  | Capitally Funded
CEC Asset Management Works |  | South East | Gordon Shirreff | 731637 | Operational (Operational) | City of Edinburgh Council | Community - Residential/Building | 2014-03-20 | 2014-06-24 | 2014-06-24 | 2014-06-30 | 2014-08-22 | 2014-08-22 | Community;#3 | DBDA | Morrison |  | Capitally Funded
CEC Property Rationalisation |  | South East | Gordon Shirreff | 2566905 | Operational (Operational) | City of Edinburgh Council | Community - Residential/Building | 2014-06-06 | 2015-03-12 | 2015-03-12 | 2014-04-14 | 2015-03-13 | 2015-03-13 | Offices;#11;#Police Services;#12 | DBDA | Morrison | Police Scotland;#43 | Capitally Funded
CEC Toilets Upgrade |  | South East | Gordon Shirreff | 677521 | Operational (Operational) | City of Edinburgh Council | Community - Residential/Building | 2013-06-17 | 2013-07-22 | 2013-07-22 | 2013-07-22 | 2014-01-22 | 2014-01-22 | Community;#3 | DBDA | GTFM |  | Capitally Funded
Child & Adolescent Mental Health, Dundee |  | East Central | Gordon Shirreff | 5970970 | Operational (Operational) | NHS Tayside | Health - Primary Care | 2012-08-28 | 2014-05-26 | 2014-05-26 | 2014-05-26 | 2015-03-06 | 2015-03-06 | Health;#6;#Education;#4;#Residential;#13 | DBDA | BAM |  | Capitally Funded
Childrens School for Complex Needs |  | North | Jonathan Christie | 17370235 | Operational (Operational) | Aberdeen City Council | Schools - ASN | 2014-05-30 | 2015-11-05 | 2015-11-05 | 2015-11-05 | 2017-04-27 | 2017-07-21 | Education;#4;#Health;#6;#Child Care;#2;#Café;#1;#Residential;#13 | DBDA | Ogilvie | NHS Grampian;#33 | Capitally Funded
Clyde Valley Learning Campus |  | South West | Bill Martin | 26425000 | Operational (Operational) | North Lanarkshire Council | Schools SSF Cap - Secondary School | 2013-06-04 | 2014-06-24 | 2014-06-25 | 2014-06-25 | 2015-12-18 | 2016-01-25 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Clydebank Leisure Centre |  | West | Bill Martin | 23200684 | Operational (Operational) | West Dunbartonshire Council | Community - Leisure/Culture | 2014-07-18 | 2015-05-10 | 2015-05-22 | 2015-05-22 | 2017-02-27 | 2017-03-03 | Leisure;#7 | DBDA | BAM |  | Capitally Funded
Clydebank Workshops |  | West | Bill Martin | 1525716 | Operational (Operational) | Clydebank Rebuilt | Community - Leisure/Culture | 2012-10-25 | 2012-12-10 | 2012-12-10 | 2012-12-15 | 2013-09-29 | 2013-12-06 | Community;#3 | DBDA | Flemings |  | Capitally Funded
Creative Exchange |  | East Central | Gordon Shirreff | 3898067 | Operational (Operational) | Perth & Kinross Council | Community - Community Facility | 2017-11-30 | 2018-10-26 | 2018-11-23 | 2018-11-23 | 2019-07-12 | 2019-09-09 | Community;#3;#Vocational;#19;#Offices;#11 | DBDA | Robertson | Perth & Kinross Council;#42 | Capitally Funded
Crieff Primary School |  | East Central | Gordon Shirreff | 9586654 | Operational (Operational) | Perth & Kinross Council | Schools - Primary School | 2013-06-01 | 2014-05-09 | 2014-05-09 | 2014-05-09 | 2015-06-05 | 2015-06-05 | Education;#4 | DBDA | BAM |  | Capitally Funded
Cumbernauld Academy & Theatre |  | South West | Bill Martin | 36939526 | Operational (Operational) | North Lanarkshire Council | Schools SSF Rev - Secondary School | 2016-11-15 | 2017-06-28 | 2017-06-29 | 2017-07-10 | 2019-07-19 | 2019-07-19 | Education;#4;#Theatre;#15;#Community;#3 | DBFM | Morrison |  | Nord LB | FES FM
Cumbernauld Community Enterprise Development |  | South West | Bill Martin | 8536049 | Operational (Operational) | North Lanarkshire Council | Community - Leisure/Culture | 2014-06-26 | 2014-10-30 | 2014-12-05 | 2014-12-05 | 2016-07-04 | 2016-07-04 | Offices;#11 | DBDA | Kier |  | Capitally Funded
Curling Academy |  | East Central | Gordon Shirreff | 3193935 | Operational (Operational) | Stirling Council | Community - Leisure/Culture | 2015-09-28 | 2016-10-31 | 2016-09-19 | 2016-09-19 | 2017-08-10 | 2017-06-27 | Leisure;#7 | DBDA | Robertson |  | Capitally Funded
Dailly Primary School |  | South West | Bill Martin | 3789524 | Operational (Operational) | South Ayrshire Council | Schools - Primary School | 2014-08-15 | 2016-04-12 | 2016-04-12 | 2016-04-12 | 2017-02-24 | 2017-02-24 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Dalbeattie High School (Dalbeattie Learning Campus) |  | South West | Bill Martin | 24170004 | Operational (Operational) | Dumfries & Galloway Council | Schools SSF Rev - Secondary School | 2013-12-18 | 2016-01-26 | 2016-01-26 | 2016-01-26 | 2017-10-27 | 2017-10-27 | Education;#4;#Community;#3;#Sports Facilities;#14 | DBFM | Graham |  | Nord LB | FES FM
Dalbeattie Primary Care Centre |  | South West | Bill Martin | 1763188 | Operational (Operational) | NHS Dumfries & Galloway | Health - Primary Care | 2013-01-30 | 2013-09-05 | 2013-09-05 | 2013-09-05 | 2014-07-11 | 2014-07-11 | Health;#6 | DBDA | Ashleigh Scotland Ltd |  | Capitally Funded
Doune Health Centre |  | East Central | Gordon Shirreff | 2079568 | Operational (Operational) | NHS Forth Valley | Health - Primary Care | 2015-10-20 | 2018-10-01 | 2018-10-17 | 2018-10-22 | 2019-08-30 | 2019-08-29 | Health;#6 | DBDA | Hadden Construction |  | Capitally Funded
Drumbrae Library & Community hub |  | South East | Gordon Shirreff | 4500000 | Operational (Operational) | City of Edinburgh Council | Community - Leisure/Culture | 2010-08-01 | 2010-12-10 | 2010-12-10 | 2011-01-10 | 2011-11-30 | 2011-11-30 | Library;#8;#Offices;#11 | DBDA | Morrison |  | Capitally Funded
Duddingston Nursery |  | South East | Gordon Shirreff | 1085502 | Operational (Operational) | City of Edinburgh Council | Schools - Primary School | 2014-04-07 | 2015-06-30 | 2015-06-30 | 2015-03-16 | 2015-08-07 | 2015-07-14 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Dumbarton Care Home |  | West | Bill Martin | 12941106 | Operational (Operational) | West Dunbartonshire Council | Community - Residential/Building | 2013-10-10 | 2015-09-15 | 2015-09-15 | 2015-09-15 | 2017-02-28 | 2017-04-28 | Health;#6 | DBDA | Morgan Sindall | NHS Greater Glasgow & Clyde;#34 | Capitally Funded
Dumfries Learning Town Phase 1 - Learning hub (The Bridge) |  | South West | Bill Martin | 9999167 | Operational (Operational) | Dumfries & Galloway Council | Schools SSF Cap - Secondary School | 2014-11-14 | 2017-03-27 | 2017-03-31 | 2017-03-31 | 2018-11-05 | 2018-11-05 | Education;#4 | DBDA | Graham |  | Capitally Funded
Dumfries Learning Town Phase 1 - North West Campus |  | South West | Bill Martin | 28194847 | Operational (Operational) | Dumfries & Galloway Council | Schools SSF Cap - Primary School & Secondary School | 2014-11-14 | 2016-08-28 | 2016-08-25 | 2016-09-11 | 2019-03-01 | 2019-03-06 | Education;#4;#Community;#3 | DBDA | Graham |  | Capitally Funded
Dumfries Learning Town Phase 1 - St Josephs College |  | South West | Bill Martin | 23792075 | Operational (Operational) | Dumfries & Galloway Council | Schools SSF Cap - Secondary School | 2014-11-14 | 2016-07-15 | 2016-07-14 | 2016-08-08 | 2018-03-29 | 2018-03-29 | Education;#4 | DBDA | Graham |  | Capitally Funded
Dunfermline Museum & Art Gallery |  | East Central | Gordon Shirreff | 9187759 | Operational (Operational) | Fife Council | Community - Leisure/Culture | 2014-09-26 | 2014-11-17 | 2015-01-07 | 2015-01-07 | 2016-08-12 | 2016-10-17 | Library;#8;#Museum;#10 | DBDA | BAM |  | Capitally Funded
Dunoon Primary School |  | North | Jonathan Christie | 9226205 | Operational (Operational) | Argyll & Bute Council | Schools SSF Cap - Primary School | 2014-09-30 | 2017-04-26 | 2017-07-03 | 2017-07-10 | 2018-06-08 | 2018-11-07 | Education;#4;#Child Care;#2 | DBDA | Morrison |  | Capitally Funded
Duns Primary School |  | South East | Gordon Shirreff | 8997224.43 | Operational (Operational) | Scottish Borders Council | Schools SSF Cap - Primary School | 2014-03-14 | 2015-08-12 | 2015-08-12 | 2015-08-26 | 2017-02-06 | 2017-07-19 | Education;#4 | DBDA | Graham |  | Capitally Funded
Dunscore Primary Care Centre |  | South West | Bill Martin | 1273559 | Operational (Operational) | NHS Dumfries & Galloway | Health - Primary Care | 2012-12-19 | 2013-09-05 | 2013-09-05 | 2013-09-05 | 2014-06-16 | 2014-06-16 | Health;#6 | DBDA | Ashleigh Scotland Ltd |  | Capitally Funded
E N'Hood Library & Office, Craigmillar |  | South East | Gordon Shirreff | 8126734 | Operational (Operational) | City of Edinburgh Council | Community - Leisure/Culture | 2010-11-16 | 2011-07-08 | 2011-07-08 | 2011-08-08 | 2012-09-07 | 2012-10-08 | Library;#8 | DBDA | Graham |  | Capitally Funded
EAC Early Years New Build - Cumnock, Kilmaurs, Stewarton |  | South West | Bill Martin | 6554492 | Operational (Operational) | East Ayrshire Council | Early Years Child Care - Nursery | 2018-08-28 | 2019-06-10 | 2019-06-13 | 2019-06-15 | 2020-03-28 | 2020-03-30 | Child Care;#2;#Education;#4 | DBDA | Graham
East Kilbride Health Centre | NHS Lanarkshire Bundle | South West | Bill Martin | 14570701 | Operational (Operational) | NHS Lanarkshire | Health - Primary Care | 2012-12-05 | 2013-11-15 | 2013-12-19 | 2013-12-19 | 2015-05-15 | 2015-05-15 | Health;#6 | DBFM | Graham |  | Aviva | Graham
East Lothian Community Hospital (Haddington) |  | South East | Gordon Shirreff | 68880081 | Operational (Operational) | NHS Lothian | Health - Major Health | 2015-06-05 | 2015-10-21 | 2016-09-23 | 2016-10-10 | 2019-08-30 | 2019-10-28 | Health;#6 | DBFM | Morrison |  | Nord LB | GTFM
East Pollockshields GP Surgery |  | West | Bill Martin | 2070542 | Operational (Operational) | NHS Greater Glasgow & Clyde | Health - Primary Care | 2013-02-08 | 2014-03-24 | 2014-03-24 | 2014-03-24 | 2015-01-09 | 2015-01-09 | Health;#6 | DBDA | CBC |  | Capitally Funded
Eastwood Health Centre | Maryhill and Eastwood Health Centres Bundle | West | Bill Martin | 14946753 | Operational (Operational) | NHS Greater Glasgow & Clyde | Health - Primary Care | 2012-12-13 | 2014-10-10 | 2014-12-01 | 2014-12-01 | 2016-03-11 | 2016-06-03 | Health;#6 | DBFM | Morgan Sindall | East Renfrewshire Council;#18;#Glasgow City Council;#22 | Aviva | Robertson FM
Elgin High School |  | North | Jonathan Christie | 30535718 | Operational (Operational) | The Moray Council | Schools SSF Rev - Secondary School | 2014-05-24 | 2016-02-25 | 2016-02-25 | 2016-02-25 | 2017-10-06 | 2017-10-13 | Education;#4;#Leisure;#7;#Community;#3;#Sports Facilities;#14 | DBFM | Balfour Beatty |  | Aviva | Robertson FM
Fairfield Social Housing |  | East Central | Gordon Shirreff | 1722828 | Operational (Operational) | Clackmannanshire Council | Community - Residential/Building | 2014-09-24 | 2015-02-12 | 2015-07-30 | 2015-07-30 | 2016-04-29 | 2016-04-29 | Residential;#13 | DBDA | Marshall |  | Capitally Funded
Faithlie Dental Practice, Fraserburgh |  | North | Jonathan Christie | 1505848 | Operational (Operational) | NHS Grampian | Health - Primary Care | 2012-01-28 | 2013-02-27 | 2013-02-27 | 2013-02-27 | 2013-10-14 | 2013-10-14 | Health;#6 | DBDA | Morrison |  | Capitally Funded
Foresterhill Community Health Centre | Inverurie and Foresterhill Health Centres Bundle | North | Jonathan Christie | 8294479 | Operational (Operational) | NHS Grampian | Health - Primary Care | 2014-04-01 | 2016-11-29 | 2016-12-05 | 2016-12-05 | 2018-03-19 | 2018-05-08 | Health;#6 | DBFM | Morrison | Aberdeen City Council;#1 | Aviva | Robertson FM
Forfar Community Campus |  | East Central | Gordon Shirreff | 37398800 | Operational (Operational) | Angus Council | Schools SSF Rev - Secondary School | 2013-03-19 | 2014-12-02 | 2015-06-12 | 2015-06-12 | 2017-02-06 | 2017-02-06 | Education;#4;#Leisure;#7 | DBFM | Robertson |  | Aviva | Robertson FM
Forres Health Centre | Forres, Tain and Woodside Health Centre Bundle | North | Jonathan Christie | 5989123 | Operational (Operational) | NHS Grampian | Health - Primary Care | 2012-05-05 | 2013-03-25 | 2013-03-25 | 2013-04-29 | 2014-04-25 | 2014-08-08 | Health;#6;#Sports Facilities;#14 | DBFM | Morrison | NHS Highland;#35 | Aviva | GTFM
Forth Valley Royal Hospital Car Park |  | East Central | Gordon Shirreff | 958286 | Operational (Operational) | NHS Forth Valley | Health - Major Health | 2012-03-20 | 2014-03-20 | 2014-03-20 | 2014-03-20 | 2014-09-11 | 2014-09-11 | Community;#3 | DBDA | Laing O'Rourke |  | Capitally Funded
Foxcovert Primary School |  | South East | Gordon Shirreff | 1390512 | Operational (Operational) | City of Edinburgh Council | Schools - Primary School | 2014-06-30 | 2015-06-30 | 2015-06-30 | 2015-03-16 | 2015-10-09 | 2015-07-14 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Frederick Street Car Park, Aberdeen |  | North | Jonathan Christie | 2344662 | Operational (Operational) | Aberdeen City Council | Community - Residential/Building | 2011-02-01 | 2012-03-15 | 2012-03-15 | 2012-03-15 | 2012-12-01 | 2012-12-01 | Community;#3 | DBDA | Morrison | NHS Grampian;#33 | Capitally Funded
Free School Meals - Crammond |  | South East | Gordon Shirreff | 920475 | Operational (Operational) | City of Edinburgh Council | Schools - Free School Meals | 2015-11-26 | 2016-04-15 | 2016-04-14 | 2016-05-30 | 2016-10-14 | 2016-10-14 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Free School Meals - East Craigs |  | South East | Gordon Shirreff | 801843 | Operational (Operational) | City of Edinburgh Council | Schools - Free School Meals | 2015-11-26 | 2016-04-15 | 2016-04-14 | 2016-05-30 | 2016-10-14 | 2016-10-14 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Free School Meals - Sciennes |  | South East | Gordon Shirreff | 464460 | Operational (Operational) | City of Edinburgh Council | Schools - Free School Meals | 2015-11-26 | 2016-04-15 | 2016-04-14 | 2016-05-02 | 2016-08-19 | 2016-08-19 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Free School Meals - Towerbank |  | South East | Gordon Shirreff | 542768 | Operational (Operational) | City of Edinburgh Council | Schools - Free School Meals | 2015-11-26 | 2016-04-15 | 2016-04-14 | 2016-06-13 | 2016-10-14 | 2016-10-27 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Galashiels Transport Interchange |  | South East | Gordon Shirreff | 5182177 | Operational (Operational) | Scottish Borders Council | Community - Transport | 2014-01-22 | 2014-03-24 | 2014-08-28 | 2014-06-13 | 2015-06-22 | 2015-08-09 | Offices;#11;#Transport Services;#17 | DBDA | Morrison |  | Capitally Funded
Garnock Academy (Campus) |  | South West | Bill Martin | 32500000 | Operational (Operational) | North Ayrshire Council | Schools SSF Cap - Secondary School | 2014-06-27 | 2015-03-30 | 2015-02-16 | 2015-02-16 | 2016-12-19 | 2016-12-19 | Education;#4;#Leisure;#7;#Community;#3;#Child Care;#2;#Sports Facilities;#14 | DBDA | Kier |  | Nord LB
Garshake Pilot Office Refurbishment |  | West | Bill Martin | 446117 | Operational (Operational) | West Dunbartonshire Council | Community - Residential/Building | 2013-02-28 | 2013-06-24 | 2013-06-24 | 2013-06-24 | 2013-09-09 | 2013-09-20 | Offices;#11 | DBDA | CBC |  | Capitally Funded
Girvan Harbourside Facilities |  | South West | Bill Martin | 465395 | Operational (Operational) | South Ayrshire Council | Community - Residential/Building | 2014-08-01 | 2015-03-19 | 2015-03-16 | 2015-03-16 | 2015-06-23 | 2015-06-23 | Community;#3 | DBDA | 3b Construction Ltd. |  | Capitally Funded
Glasgow Women's Library Refurb |  | West | Bill Martin | 933415 | Operational (Operational) | Clyde Gateway | Community - Leisure/Culture | 2014-09-15 | 2014-11-24 | 2014-11-24 | 2014-11-24 | 2015-10-30 | 2015-10-30 | Community;#3 | DBDA | Maxi Construction |  | Capitally Funded
Glenwood Health Centre |  | East Central | Gordon Shirreff | 4290100 | Operational (Operational) | NHS Fife | Health - Primary Care | 2012-08-31 | 2013-04-04 | 2013-02-01 | 2013-02-01 | 2014-02-14 | 2014-02-14 | Health;#6;#Education;#4 | DBDA | BAM |  | Capitally Funded
Gorbals Health Centre | Gorbals and Woodside Health Centre Bundle | West | Bill Martin | 17197621 | Operational (Operational) | NHS Greater Glasgow & Clyde | Health - Primary Care | 2014-05-01 | 2017-04-05 | 2017-04-10 | 2017-02-06 | 2018-10-12 | 2018-11-06 | Health;#6 | DBFM | Morgan Sindall | Glasgow City Council;#22 | Nord LB | Robertson FM
Greenfaulds High School |  | South West | Bill Martin | 31989831 | Operational (Operational) | North Lanarkshire Council | Schools SSF Rev - Secondary School | 2013-09-16 | 2015-01-08 | 2015-01-08 | 2015-01-08 | 2016-09-21 | 2016-09-21 | Education;#4;#Leisure;#7 | DBFM | Morrison |  | Nord LB | FES FM
Greenock Early Years |  | West | Bill Martin | 2807104 | Operational (Operational) | Inverclyde Council | Early Years Child Care - Nursery | 2016-05-31 | 2017-07-27 | 2017-07-27 | 2017-08-07 | 2018-06-01 | 2018-06-15 | Education;#4 | DBDA | CCG |  | Capitally Funded
Gullane Medical Centre |  | South East | Gordon Shirreff | 2931491 | Operational (Operational) | East Lothian Council | Health - Primary Care | 2011-05-24 | 2013-01-21 | 2013-01-21 | 2013-01-21 | 2013-11-26 | 2013-12-24 | Health;#6 | DBDA | Graham |  | Capitally Funded
Haddington Primary School & St. Mary's Infants |  | South East | Gordon Shirreff | 10321227 | Operational (Operational) | East Lothian Council | Schools SSF Cap - Primary School | 2011-02-15 | 2011-08-15 | 2011-08-15 | 2011-07-04 | 2012-10-11 | 2012-10-11 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Hallpark Residential Development |  | East Central | Gordon Shirreff | 1940671 | Operational (Operational) | Clackmannanshire Council | Community - Residential/Building | 2013-02-21 | 2013-07-18 | 2013-07-18 | 2013-07-18 | 2014-05-28 | 2014-07-28 | Residential;#13 | DBDA | Marshall |  | Capitally Funded
Harris Academy, Dundee |  | East Central | Gordon Shirreff | 31200000 | Operational (Operational) | Dundee City Council | Schools SSF Cap - Secondary School | 2012-06-06 | 2013-10-26 | 2013-10-26 | 2013-10-26 | 2016-04-29 | 2016-05-01 | Education;#4;#Leisure;#7 | DBDA | Robertson |  | Capitally Funded
Hayshead Primary School | Muirfield, Ladyloan and Hayshead Bundle | East Central | Gordon Shirreff | 13607535 | Operational (Operational) | Angus Council | Schools SSF Rev - Primary School | 2017-01-23 | 2018-09-24 | 2018-09-19 | 2018-09-19 | 2020-01-24 | 2020-01-24 | Education;#4 | DBDA | Robertson |  | Capitally Funded
Hillhead Community Centre |  | West | Bill Martin | 2616413 | Operational (Operational) | East Dunbartonshire Council | Community - Community Facility | 2013-02-08 | 2013-11-13 | 2013-11-13 | 2013-11-25 | 2014-08-18 | 2014-08-18 | Child Care;#2;#Offices;#11 | DBDA | Flemings |  | Capitally Funded
Inverclyde Care Home |  | West | Bill Martin | 8482426 | Operational (Operational) | NHS Greater Glasgow & Clyde | Health - Residential/Building | 2013-04-02 | 2015-12-10 | 2016-02-26 | 2016-02-26 | 2017-06-30 | 2017-07-17 | Health;#6 | DBFM | Morgan Sindall |  | Aviva | Robertson FM
Inverness Royal Academy |  | North | Jonathan Christie | 36474718 | Operational (Operational) | The Highland Council | Schools SSF Cap - Secondary School | 2013-03-26 | 2014-07-16 | 2014-07-16 | 2014-07-16 | 2016-06-25 | 2016-08-18 | Education;#4;#Community;#3;#Sports Facilities;#14 | DBDA | Morrison | Highlife Highland;#74 | Capitally Funded
Inverurie Community Health Centre | Inverurie and Foresterhill Health Centres Bundle | North | Jonathan Christie | 14455752 | Operational (Operational) | NHS Grampian | Health - Primary Care | 2014-04-01 | 2016-11-29 | 2016-12-05 | 2016-12-05 | 2018-07-23 | 2018-07-23 | Health;#6 | DBFM | Morrison | Aberdeenshire Council;#2 | Aviva | Robertson FM
Irvine Annickbank |  | South West | Bill Martin | 1853896 | Operational (Operational) | Irvine Bay Regeneration Company | Community - Residential/Building | 2013-01-16 | 2013-10-09 | 2013-10-21 | 2013-10-21 | 2014-05-16 | 2014-05-23 | Offices;#11 | DBDA | Morrison |  | Capitally Funded
James Gillespies High School (D&B) Enabling Works |  | South East | Gordon Shirreff | 3936542 | Operational (Operational) | City of Edinburgh Council | Schools - Secondary School | 2012-06-12 | 2013-04-12 | 2013-04-12 | 2013-03-04 | 2013-10-25 | 2013-10-25 | Education;#4 | DBDA | Morrison |  | Capitally Funded
James Gillespies High School (DBFM) |  | South East | Gordon Shirreff | 34310036 | Operational (Operational) | City of Edinburgh Council | Schools SSF Rev - Secondary School | 2012-06-26 | 2012-12-31 | 2013-12-09 | 2013-10-28 | 2016-07-15 | 2016-07-15 | Education;#4 | DBFM | Morrison |  | Aviva | GTFM
Jedburgh Intergenerational Learning Campus |  | South East | Gordon Shirreff | 32814383 | Operational (Operational) | Scottish Borders Council | Schools SSF Rev - Primary School & Secondary School | 2017-09-27 | 2018-07-01 | 2018-10-25 |  | 2020-03-31 | 2020-03-06 |  | DBFM | BAM |  | Nord LB | BAM
Johnstone Town Hall |  | West | Bill Martin | 12487541 | Operational (Operational) | Renfrewshire Council | Community - Community Facility | 2012-12-17 | 2013-10-07 | 2013-10-07 | 2013-10-07 | 2015-10-18 | 2015-10-18 | Library;#8 | DBDA | BAM |  | Capitally Funded
Kelso High School |  | South East | Gordon Shirreff | 20203693 | Operational (Operational) | Scottish Borders Council | Schools SSF Rev - Secondary School | 2013-04-25 | 2016-02-15 | 2016-02-19 | 2016-03-14 | 2017-11-03 | 2017-11-03 | Education;#4;#Leisure;#7;#Library;#8 | DBFM | Morrison |  | Nord LB | GTFM
Kilmacolm Primary School |  | West | Bill Martin | 4404349 | Operational (Operational) | Inverclyde Council | Schools SSF Cap - Primary School | 2015-03-31 | 2015-10-06 | 2015-10-06 | 2015-10-19 | 2016-10-07 | 2016-09-29 | Education;#4 | DBDA | CBC |  | Capitally Funded
Kilmardinney House |  | West | Bill Martin | 2488191 | Operational (Operational) | East Dunbartonshire Council | Community - Residential/Building | 2015-07-17 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2017-03-24 | 2017-03-24 | Community;#3 | DBDA | Clarks |  | Capitally Funded
Kilpatrick ASN School |  | West | Bill Martin | 10226025 | Operational (Operational) | West Dunbartonshire Council | Schools - ASN | 2014-06-20 | 2015-07-23 | 2015-07-23 | 2015-08-01 | 2016-10-21 | 2017-08-09 | Education;#4 | DBDA | Heron Bros |  | Capitally Funded
Kilsyth Health Centre | NHS Lanarkshire Bundle | South West | Bill Martin | 14570701 | Operational (Operational) | NHS Lanarkshire | Health - Primary Care | 2012-12-05 | 2013-11-15 | 2013-12-19 | 2013-12-19 | 2015-05-15 | 2015-05-15 | Health;#6 | DBFM | Graham |  | Aviva | Graham
Kilwinning Synthetic Pitch |  | South West | Bill Martin | 700000 | Operational (Operational) | North Ayrshire Council | Community - Leisure/Culture | 2017-05-29 | 2017-07-12 | 2017-08-25 | 2017-07-05 | 2017-10-16 | 2017-09-29 | Leisure;#7 | DBDA | WH Malcolm |  |  | TBC
Kinross Primary School | Tulloch and Kinross Schools Bundle | East Central | Gordon Shirreff | 11781562.86 | Operational (Operational) | Perth & Kinross Council | Schools SSF Cap - Primary School | 2015-07-01 | 2016-12-12 | 2016-11-14 | 2016-11-14 | 2017-12-04 | 2017-12-04 | Education;#4 | DBDA | Robertson |  | Capitally Funded
Kirkintilloch Community hub - Strategic Partnering Services only |  | West | Bill Martin | 5328282 | Operational (Operational) | East Dunbartonshire Council | Community - Community Facility | 2012-04-01 | 2012-07-01 | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-09-01 | Library;#8 | SSS | Elmwood |  | Capitally Funded
Kirkintilloch Town Hall |  | West | Bill Martin | 4844173 | Operational (Operational) | East Dunbartonshire Council | Community - Community Facility | 2015-05-06 | 2016-03-01 | 2016-04-25 | 2016-04-25 | 2017-09-27 | 2018-09-27 | Offices;#11;#Community;#3 | DBDA | CBC |  | Capitally Funded
Kirn Primary School, Dunoon |  | North | Jonathan Christie | 9253198 | Operational (Operational) | Argyll & Bute Council | Schools SSF Cap - Primary School | 2014-08-14 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2017-09-26 | 2017-10-27 | Education;#4;#Child Care;#2;#Sports Facilities;#14;#Leisure;#7 | DBDA | Morrison |  | Capitally Funded
Ladyloan Primary School | Muirfield, Ladyloan and Hayshead Bundle | East Central | Gordon Shirreff | 7426547.96 | Operational (Operational) | Angus Council | Schools SSF Rev - Primary School | 2017-01-23 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2018-12-12 | 2019-06-21 | Education;#4 | DBFM | Robertson |  | Aviva | Robertson FM
Lairdsland Primary School |  | West | Bill Martin | 7602917 | Operational (Operational) | East Dunbartonshire Council | Schools SSF Cap - Primary School | 2012-10-26 | 2013-12-03 | 2014-02-06 | 2014-02-24 | 2015-04-10 | 2015-04-10 | Education;#4;#Library;#8 | DBDA | Morgan Sindall |  | Capitally Funded
Largs Academy |  | South West | Bill Martin | 43865088 | Operational (Operational) | North Ayrshire Council | Schools SSF Rev - Secondary School | 2015-01-15 | 2016-05-27 | 2016-05-27 | 2016-05-30 | 2018-03-05 | 2018-03-05 | Education;#4 | DBFM | Morrison |  | Nord LB
Lauder Health Centre |  | South East | Gordon Shirreff | 1238867 | Operational (Operational) | NHS Borders | Health - Primary Care | 2012-01-23 | 2012-11-30 | 2012-11-30 | 2012-11-05 | 2013-10-11 | 2013-10-11 | Health;#6 | DBDA | Morrison |  | Capitally Funded
Leith Meanwhile |  | South East | Gordon Shirreff | 800000 | Operational (Operational) | City of Edinburgh Council | Community - Community Facility | 2018-03-16 | 2018-05-17 | 2018-05-17 | 2018-05-21 | 2018-09-14 | 2018-09-14 | Health;#6;#Local Authority Offices;#9;#Vocational;#19 | DBDA | Morrison | NHS Lothian;#38
Lennoxtown Community hub |  | West | Bill Martin | 4454421 | Operational (Operational) | East Dunbartonshire Council | Community - Community Facility | 2014-04-22 | 2015-01-29 | 2015-01-29 | 2015-01-28 | 2016-01-29 | 2016-01-29 | Community;#3;#Health;#6;#Library;#8 | DBDA | Morgan Sindall | NHS Greater Glasgow & Clyde;#34 | Capitally Funded
Lenzie/Lenzie Moss Primary School |  | West | Bill Martin | 11138513 | Operational (Operational) | East Dunbartonshire Council | Schools SSF Cap - Primary School | 2014-09-08 | 2015-08-10 | 2015-08-10 | 2015-08-10 | 2016-12-23 | 2017-02-24 | Education;#4 | DBDA | Lend Lease |  | Capitally Funded
Levenmouth High School |  | East Central | Gordon Shirreff | 38480984 | Operational (Operational) | Fife Council | Schools SSF Rev - Secondary School | 2013-07-05 | 2014-08-15 | 2014-12-22 | 2014-12-22 | 2016-07-08 | 2016-07-08 | Education;#4 | DBFM | BAM |  | Aviva | FES FM
Levenmouth High School Enabling Works |  | East Central | Gordon Shirreff | 2697750 | Operational (Operational) | Fife Council | Schools - Secondary School | 2013-07-05 | 2014-09-01 | 2014-09-01 | 2014-09-01 | 2014-12-12 | 2014-12-12 | Education;#4 | DBDA | BAM |  | Capitally Funded
Marr College |  | South West | Bill Martin | 34280000 | Operational (Operational) | South Ayrshire Council | Schools SSF Cap - Secondary School | 2014-12-04 | 2015-10-08 | 2015-10-08 | 2015-10-08 | 2016-12-15 | 2016-12-15 | Education;#4;#Community;#3;#Sports Facilities;#14 | DBDA | Kier |  | Capitally Funded
Marr College Synthetic Pitches |  | South West | Bill Martin | 1572205 | Operational (Operational) | South Ayrshire Council | Schools - Secondary School | 2014-12-04 | 2015-02-13 | 2015-02-13 | 2015-02-13 | 2015-06-24 | 2015-07-29 | Education;#4;#Leisure;#7 | DBDA | Kier |  | Capitally Funded
Maryhill Health Centre | Maryhill and Eastwood Health Centres Bundle | West | Bill Martin | 12476288 | Operational (Operational) | NHS Greater Glasgow & Clyde | Health - Primary Care | 2012-12-13 | 2014-10-10 | 2014-10-10 | 2014-12-08 | 2016-08-08 | 2016-07-15 | Health;#6 | DBFM | Morgan Sindall | East Renfrewshire Council;#18;#Glasgow City Council;#22 | Aviva | Robertson FM
Montrose House (Care Home on Arran) |  | South West | Bill Martin | 4710536 | Operational (Operational) | North Ayrshire Council | Community - Residential/Building | 2012-12-21 | 2013-09-29 | 2013-09-27 | 2013-09-27 | 2014-10-03 | 2014-10-03 | Health;#6 | DBDA | Kier |  | Capitally Funded
Moorfoot Primary School |  | West | Bill Martin | 4803575 | Operational (Operational) | Inverclyde Council | Schools - Primary School | 2016-05-13 | 2017-04-28 | 2017-04-18 | 2017-04-18 | 2018-03-02 | 2018-05-18 | Education;#4 | DBDA | CCG |  | Capitally Funded
Motherwell High School Review Taylor and Braidhurst |  | South West | Bill Martin | 5020000 | Operational (Operational) | North Lanarkshire Council | Schools - Secondary School | 2017-02-14 | 2017-09-07 | 2017-10-06 | 2017-09-04 | 2018-05-14 | 2018-05-14 | Education;#4 | DBDA | Kier |  | Capitally Funded | TBC
Muirfield Primary School | Muirfield, Ladyloan and Hayshead Bundle | East Central | Gordon Shirreff | 7426547.96 | Operational (Operational) | Angus Council | Schools SSF Rev - Primary School | 2017-01-23 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2018-12-11 | 2019-06-21 | Education;#4 | DBFM | Robertson |  | Aviva | Robertson FM
New ASN School (previously Carrongrange) |  | East Central | Gordon Shirreff | 17917978 | Operational (Operational) | Falkirk Council | Schools SSF Cap - ASN | 2015-01-20 | 2016-04-12 | 2016-05-06 | 2016-05-06 | 2017-07-28 | 2017-07-28 | Education;#4 | DBDA | Ogilvie |  | Capitally Funded
Newbattle High School |  | South East | Gordon Shirreff | 33780894 | Operational (Operational) | Midlothian Council | Schools SSF Rev - Secondary School | 2013-10-01 | 2016-02-08 | 2016-02-12 | 2016-01-25 | 2018-03-30 | 2018-05-25 | Education;#4;#Leisure;#7 | DBFM | Morrison |  | Nord LB | GTFM
Newbridge Fire & Rescue Station |  | South East | Gordon Shirreff | 577972 | Operational (Operational) | Scottish Fire and Rescue Service | Community - Emergency Services | 2013-11-07 | 2014-02-14 | 2014-02-14 | 2014-01-27 | 2014-03-28 | 2014-03-27 | Emergency Services;#5 | DBDA | Morrison |  | Capitally Funded
NLC Smarter Working phase 1 |  | South West | Bill Martin | 1617500 | Operational (Operational) | North Lanarkshire Council | Offices - Workshops | 2016-12-02 | 2017-01-13 | 2017-02-16 | 2017-12-22 | 2018-06-01 | 2016-07-08 | Education;#4 | SBC | GHI Contracts |  | Capitally Funded
Oakbank Primary School |  | East Central | Gordon Shirreff | 9024141 | Operational (Operational) | Perth & Kinross Council | Schools - Primary School | 2013-05-03 | 2014-05-29 | 2014-05-29 | 2014-05-29 | 2015-06-05 | 2015-06-05 | Education;#4 | DBDA | BAM |  | Capitally Funded
Oban High School | Campbeltown and Oban High School Bundle | North | Jonathan Christie | 34756016 | Operational (Operational) | Argyll & Bute Council | Schools SSF Rev - Secondary School | 2014-08-08 | 2016-03-24 | 2016-03-24 | 2016-04-25 | 2018-03-23 | 2018-04-05 | Education;#4;#Leisure;#7;#Sports Facilities;#14;#Community;#3;#Vocational;#19 | DBFM | Morrison | Scottish Rugby;#73 | Aviva | FES FM
Orbiston Workshops |  | South West | Bill Martin | 500000 | Operational (Operational) | North Lanarkshire Council | Offices - Workshops | 2016-11-30 | 2018-05-31 | 2018-08-07 | 2018-10-01 | 2019-08-31 | 2019-08-31 | Community;#3 | SSS | CBC
Our Lady & St Patricks High School (OLSP) |  | West | Bill Martin | 26691472 | Operational (Operational) | West Dunbartonshire Council | Schools SSF Rev - Secondary School | 2014-09-22 | 2015-12-10 | 2016-03-31 | 2016-04-18 | 2017-10-06 | 2017-10-09 | Education;#4 | DBFM | BAM |  | Aviva | BAM
Overton Community Centre |  | East Central | Gordon Shirreff | 810491 | Operational (Operational) | Fife Council | Community - Community Facility |  |  | 2016-04-01 | 2016-04-01 | 2016-12-12 | 2016-12-14 | Community;#3 | DBDA | Robertson |  | Capitally Funded
Pennywell All Care Centre (North West Campus) | NHS Lothian Bundle | South East | Gordon Shirreff | 11547861 | Operational (Operational) | NHS Lothian | Health - Major Health | 2013-02-08 | 2016-03-14 | 2016-04-01 | 2016-04-01 | 2017-10-23 | 2017-12-11 | Education;#4;#Health;#6 | DBFM | Graham | West Lothian Council;#55;#City of Edinburgh Council;#8 | Nord LB | Graham
Perth Theatre |  | East Central | Gordon Shirreff | 15995991 | Operational (Operational) | Perth & Kinross Council | Community - Leisure/Culture |  | 2016-05-17 | 2016-06-17 | 2016-06-17 | 2017-10-19 | 2017-11-03 | Community;#3 | DBDA | Robertson |  | Capitally Funded
Pharmaceutical Specials Service (ex Unlicensed Medicines) |  | East Central | Gordon Shirreff | 25183514 | Operational (Operational) | NHS Tayside | Health - Major Health | 2013-08-02 | 2016-12-22 | 2016-12-22 | 2017-01-16 | 2018-12-21 | 2019-03-15 | Health;#6 | DBFM | Robertson |  | Aviva | Robertson FM
Pinewood Primary School |  | South East | Gordon Shirreff | 1324630 | Operational (Operational) | West Lothian Council | Schools - Primary School | 2015-12-18 | 2016-03-07 | 2016-03-24 | 2016-03-28 | 2016-08-19 | 2016-08-19 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Prestonpans Health Centre |  | South East | Gordon Shirreff | 1586710 | Operational (Operational) | NHS Lothian | Health - Primary Care | 2015-12-15 | 2016-06-09 | 2016-07-04 | 2016-07-04 | 2018-05-01 | 2017-04-29 | Health;#6 | DBDA | Graham |  | Capitally Funded
Quarry Road, Phase 2 |  | South West | Bill Martin | 5480700 | Operational (Operational) | North Ayrshire Council | Community - Leisure/Culture | 2017-10-31 | 2018-09-17 | 2018-12-14 | 2018-09-01 | 2019-07-12 | 2019-07-12 | Leisure;#7;#Community;#3;#Health;#6 | DBDA | Ashleigh Scotland Ltd
Queen Margaret Academy |  | South West | Bill Martin | 25834632 | Operational (Operational) | South Ayrshire Council | Schools SSF Rev - Secondary School | 2016-08-30 | 2017-11-07 | 2017-11-09 | 2017-11-20 | 2019-10-21 | 2019-10-21 | Education;#4;#Leisure;#7 | DBFM | Kier |  | Nord LB | FES FM
Redwell Primary School (St Johns/Claremont) |  | East Central | Gordon Shirreff | 8130017 | Operational (Operational) | Clackmannanshire Council | Schools SSF Cap - Primary School | 2012-06-15 | 2013-06-13 | 2013-06-18 | 2013-06-18 | 2014-08-08 | 2014-09-08 | Education;#4;#Leisure;#7 | DBDA | Robertson |  | Capitally Funded
Refurbishment of Wards 1, 18 & 19 at Falkirk Community Hospital |  | East Central | Gordon Shirreff | 2960479 | Operational (Operational) | NHS Forth Valley | Health - Major Health | 2013-03-04 |  | 2015-03-04 | 2015-03-04 | 2015-03-30 | 2015-06-30 | Health;#6 | DBDA | Robertson |  | Capitally Funded
Renfrew Community Safety Hub |  | West | Bill Martin | 972245 | Operational (Operational) | Renfrewshire Council | Community - Community Facility | 2015-01-26 | 2015-03-06 | 2015-03-06 | 2015-03-16 | 2015-07-17 | 2015-09-16 | Community;#3 | DBDA | Project Management & Construction |  | Capitally Funded
Rising Rolls - Simpsons Primary |  | South East | Gordon Shirreff | 1898263 | Operational (Operational) | West Lothian Council | Schools - Primary School | 2015-05-13 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2015-12-18 | 2015-12-18 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Rising Rolls (PS Extensions) |  | South East | Gordon Shirreff | 2536600 | Operational (Operational) | City of Edinburgh Council | Schools - Primary School | 2012-09-13 | 2013-05-31 | 2013-05-31 | 2013-03-29 | 2013-08-09 | 2013-08-09 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Rising Rolls (PS Extensions) Phase 2 |  | South East | Gordon Shirreff | 3234362 | Operational (Operational) | City of Edinburgh Council | Schools - Primary School | 2014-02-07 | 2014-04-02 | 2014-04-02 | 2014-03-27 | 2014-08-11 | 2014-08-11 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Rising Rolls 5 |  | South East | Gordon Shirreff | 2805985 | Operational (Operational) | City of Edinburgh Council | Schools - Primary School | 2016-10-03 | 2017-02-15 | 2017-02-15 | 2017-03-15 | 2017-08-11 | 2017-08-11 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Rising Rolls 6 |  | South East | Gordon Shirreff | 5491377 | Operational (Operational) | City of Edinburgh Council | Schools - Primary School | 2017-09-02 | 2018-02-16 | 2018-03-16 | 2018-03-23 | 2018-08-10 | 2018-08-10 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Rising Rolls Phase 3 |  | South East | Gordon Shirreff | 6032756 | Operational (Operational) | City of Edinburgh Council | Schools - Primary School | 2014-05-26 | 2015-04-21 | 2015-04-21 | 2014-03-20 | 2015-08-14 | 2015-08-14 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Rising Rolls Phase 4 - East Craigs |  | South East | Gordon Shirreff | 734563 | Operational (Operational) | City of Edinburgh Council | Schools - Primary School | 2015-11-26 | 2016-03-04 | 2016-03-04 | 2016-04-06 | 2016-08-12 | 2016-08-05 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Rising Rolls Phase 4- Fox Covert |  | South East | Gordon Shirreff | 1175004 | Operational (Operational) | City of Edinburgh Council | Schools - Primary School | 2015-11-26 | 2016-03-04 | 2016-03-04 | 2016-04-06 | 2016-08-12 | 2016-08-12 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Rising Rolls Phase 4- St Marys |  | South East | Gordon Shirreff | 942956 | Operational (Operational) | City of Edinburgh Council | Schools - Primary School | 2015-11-26 | 2016-03-04 | 2016-03-04 | 2016-04-06 | 2016-11-11 | 2016-11-23 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Rosemount Court Care Home |  | South East | Gordon Shirreff | 7152836 | Operational (Operational) | West Lothian Council | Community - Residential/Building | 2012-02-28 | 2014-03-04 | 2014-08-13 | 2014-08-13 | 2016-12-12 | 2017-03-31 | Health;#6 | DBDA | Graham |  | Capitally Funded
Rosewell Primary School Extension |  | South East | Gordon Shirreff | 1008000 | Operational (Operational) | Midlothian Council | Schools - Primary School | 2012-08-15 | 2013-07-29 | 2013-07-29 | 2013-07-29 | 2013-12-13 | 2014-01-30 | Education;#4 | DBDA | Graham |  | Capitally Funded
Roxburgh Health Centre |  | South East | Gordon Shirreff | 1902176 | Operational (Operational) | NHS Borders | Health - Primary Care | 2015-03-09 | 2016-05-06 | 2016-06-23 | 2016-06-23 | 2017-02-27 | 2017-04-14 | Health;#6 | DBDA | Morrison |  | Capitally Funded
Royal Edinburgh Mental Health - Phase 1 |  | South East | Gordon Shirreff | 42108545 | Operational (Operational) | NHS Lothian | Health - Major Health | 2013-04-02 | 2014-12-18 | 2014-12-18 | 2015-01-19 | 2016-12-05 | 2016-12-05 | Health;#6 | DBFM | Morrison |  | Nord LB | GTFM
Royston Care Home |  | South East | Gordon Shirreff | 8458117.04 | Operational (Operational) | City of Edinburgh Council | Community - Residential/Building | 2014-05-13 | 2015-04-21 | 2015-04-21 | 2015-05-04 | 2016-09-12 | 2016-09-12 | Health;#6 | DBDA | Graham |  | Capitally Funded
SAS Ambulance Station, Galashiels |  | South East | Gordon Shirreff | 1999861 | Operational (Operational) | Scottish Ambulance Service | Health - Emergency Services | 2012-01-19 | 2014-03-28 | 2014-03-28 | 2014-02-24 | 2014-12-05 | 2015-01-09 | Emergency Services;#5;#Health;#6 | DBDA | Morrison |  | Capitally Funded
South of the City Academy (Lochside Academy) |  | North | Jonathan Christie | 47607808 | Operational (Operational) | Aberdeen City Council | Schools SSF Rev - Secondary School | 2014-09-02 | 2016-05-30 | 2016-06-30 | 2016-06-30 | 2018-06-15 | 2018-06-15 | Community;#3;#Education;#4;#Leisure;#7;#Sports Facilities;#14;#Health;#6;#Vocational;#19 | DBFM | Balfour Beatty | NHS Grampian;#33;#Cove Rangers;#75 | Aviva | Robertson FM
Speirs Centre Museum |  | East Central | Gordon Shirreff | 3038867 | Operational (Operational) | Clackmannanshire Council | Community - Leisure/Culture | 2013-05-14 | 2013-05-28 | 2013-05-28 | 2013-05-28 | 2014-08-15 | 2014-08-22 | Library;#8;#Museum;#10;#Offices;#11 | DBDA | Marshall |  | Capitally Funded
Spiers Bridge Office Fit out |  | West | Bill Martin | 211112 | Operational (Operational) | East Renfrewshire Council | Community - Community Facility | 2017-12-12 | 2018-05-31 | 2018-06-12 | 2018-06-12 | 2018-08-10 | 2018-08-10 | Local Authority Offices;#9 | SBC | TBC
Sports Pitch Replacement Project Ph1 | Falkirk Sports Pitch Replacement | East Central | Gordon Shirreff | 620311 | Operational (Operational) | Falkirk Council | Community - Leisure/Culture | 2018-03-07 | 2018-08-03 | 2018-06-01 | 2018-06-25 | 2018-09-28 | 2017-08-11 | Sports Facilities;#14;#Leisure;#7 | Minor Works | WH Malcolm |  | Capitally Funded
St Agathas / St Flannans Primary School |  | West | Bill Martin | 8390929 | Operational (Operational) | East Dunbartonshire Council | Schools SSF Cap - Primary School | 2015-02-04 | 2016-04-01 | 2016-04-29 | 2016-04-29 | 2017-04-17 | 2017-12-13 | Library;#8;#Leisure;#7;#Health;#6 | DBDA | Morgan Sindall |  | Capitally Funded
St Andrews/St Josephs Primary School |  | West | Bill Martin | 10278388 | Operational (Operational) | East Dunbartonshire Council | Schools - Primary School | 2015-10-09 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2018-06-15 | 2018-06-15 | Education;#4 | DBDA | Morgan Sindall |  | Capitally Funded
St Margarets Primary School & Cowie nursery |  | East Central | Gordon Shirreff | 6592414.7 | Operational (Operational) | Stirling Council | Schools SSF Cap - Primary School | 2014-07-11 | 2015-05-06 | 2015-09-11 | 2015-09-11 | 2016-07-18 | 2016-08-09 | Education;#4 | DBDA | Robertson |  | Capitally Funded
St Ninian's Primary School (EC) |  | East Central | Gordon Shirreff | 7849384 | Operational (Operational) | Stirling Council | Schools SSF Cap - Primary School | 2015-04-03 | 2015-12-11 | 2015-12-02 | 2015-12-02 | 2017-05-01 | 2016-10-07 | Education;#4 | DBDA | Robertson |  | Capitally Funded
St Ninian's Primary School (W) |  | West | Bill Martin | 8445975 | Operational (Operational) | Inverclyde Council | Schools - Primary School | 2016-05-26 | 2017-05-30 | 2017-05-30 | 2017-06-12 | 2018-08-14 | 2018-08-14 | Education;#4 | DBDA | CCG |  | Capitally Funded
St Patricks Primary School |  | West | Bill Martin | 6900305 | Operational (Operational) | Inverclyde Council | Schools SSF Cap - Primary School | 2014-09-08 | 2015-08-03 | 2015-08-03 | 2015-08-03 | 2016-10-07 | 2016-10-28 | Education;#4 | DBDA | Lend Lease |  | Capitally Funded
Stirling Care Village |  | East Central | Gordon Shirreff | 34424764 | Operational (Operational) | NHS Forth Valley | Health - Primary Care | 2013-05-24 | 2016-12-05 | 2016-12-08 | 2016-12-11 | 2018-06-29 | 2018-06-29 | Health;#6 | DBFM | Robertson | Stirling Council;#51;#Scottish Ambulance Service;#45 | Aviva | FES FM
Tain Health Centre | Forres, Tain and Woodside Health Centre Bundle | North | Jonathan Christie | 4375844 | Operational (Operational) | NHS Highland | Health - Primary Care | 2012-05-05 | 2013-03-25 | 2013-03-25 | 2013-04-29 | 2014-04-25 | 2014-05-23 | Health;#6 | DBFM | Morrison | NHS Grampian;#33;#The Highland Council;#67 | Aviva | GTFM
Tarbolton Primary School & Community Campus |  | South West | Bill Martin | 8107074 | Operational (Operational) | South Ayrshire Council | Schools - Primary School | 2014-12-16 | 2016-02-21 | 2016-02-21 | 2016-02-21 | 2017-02-10 | 2017-02-09 | Education;#4;#Leisure;#7;#Library;#8 | DBDA | Morrison |  | Capitally Funded
Tarryholme Drive |  | South West | Bill Martin | 4643619 | Operational (Operational) | North Ayrshire Council | Community - Community Facility | 2017-10-28 | 2018-08-31 | 2019-04-30 | 2018-08-27 | 2019-11-18 | 2019-11-18 | Community;#3;#Health;#6;#Café;#1;#Residential;#13 | SBC | Ashleigh Scotland Ltd
Timmergreen Primary School |  | East Central | Gordon Shirreff | 4303314.85 | Operational (Operational) | Angus Council | Schools - Primary School | 2014-09-15 | 2015-05-20 | 2015-06-29 | 2015-06-29 | 2015-06-29 | 2016-05-27 | Education;#4;#Health;#6 | DBDA | Robertson |  | Capitally Funded
Tranent Health Centre |  | South East | Gordon Shirreff | 1079895 | Operational (Operational) | NHS Lothian | Health - Primary Care | 2012-02-03 | 2014-01-30 | 2014-01-30 | 2013-11-04 | 2014-07-25 | 2014-07-31 | Health;#6 | DBDA | Morrison |  | Capitally Funded
Tullibody South ( Abercromby PS) |  | East Central | Gordon Shirreff | 15179159 | Operational (Operational) | Clackmannanshire Council | Schools - Primary School | 2017-05-22 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2019-08-02 | 2019-08-22 | Education;#4;#Community;#3 | DBDA | Robertson |  | Capitally Funded
Tulloch Primary School | Tulloch and Kinross Schools Bundle | East Central | Gordon Shirreff | 10591094 | Operational (Operational) | Perth & Kinross Council | Schools SSF Cap - Primary School | 2015-07-01 | 2016-12-16 | 2016-12-15 | 2016-12-19 | 2018-01-21 | 2018-01-21 | Education;#4 | DBDA | Robertson |  | Capitally Funded
Vale of Leven Workshops |  | West | Bill Martin | 1777437 | Operational (Operational) | West Dunbartonshire Council | Community - Community Facility | 2014-04-18 | 2015-03-06 | 2015-03-06 | 2015-03-06 | 2015-08-14 | 2015-11-16 | Community;#3 | DBDA | Morgan Sindall |  | Capitally Funded
Waid Academy |  | East Central | Gordon Shirreff | 22400870 | Operational (Operational) | Fife Council | Schools SSF Cap - Secondary School | 2015-06-09 | 2015-10-20 | 2015-12-02 | 2015-12-02 | 2017-03-31 | 2017-04-28 | Education;#4;#Community;#3;#Leisure;#7 | DBDA | BAM |  | Capitally Funded
Wallyford Primary School |  | South East | Gordon Shirreff | 18986451 | Operational (Operational) | East Lothian Council | Schools SSF Cap - Primary School | 2016-09-01 | 2017-08-08 | 2017-08-31 | 2017-10-20 | 2019-01-23 | 2019-02-11 | Education;#4 | DBDA | Morrison |  |  | Morrison
Wardie Primary School |  | South East | Gordon Shirreff | 790641 | Operational (Operational) | City of Edinburgh Council | Schools - Primary School | 2014-06-30 | 2015-06-30 | 2015-06-30 | 2015-03-16 | 2015-09-28 | 2015-08-14 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Wardykes Primary School |  | East Central | Gordon Shirreff | 6032062 | Operational (Operational) | Angus Council | Schools - Primary School | 2014-08-29 | 2015-04-29 | 2015-06-29 | 2015-06-29 | 2016-11-09 | 2016-11-18 | Education;#4;#Leisure;#7 | DBDA | Robertson |  | Capitally Funded
WDC Office/Corporate HQ |  | West | Bill Martin | 15415948 | Operational (Operational) | West Dunbartonshire Council | Community - Residential/Building | 2015-05-06 | 2016-04-01 | 2016-09-02 | 2016-08-23 | 2017-12-22 | 2018-05-11 | Offices;#11 | DBDA | Lend Lease |  | Capitally Funded
West Calder High Bridge - DBDA |  | South East | Gordon Shirreff | 5085874 | Operational (Operational) | West Lothian Council | Community - Community Facility | 2015-09-21 | 2016-04-29 | 2016-04-19 | 2016-01-18 | 2016-12-01 | 2016-12-15 | Education;#4 | DBDA | Morrison |  | Capitally Funded
West Calder High School |  | South East | Gordon Shirreff | 30099082 | Operational (Operational) | West Lothian Council | Schools SSF Rev - Secondary School | 2016-04-27 | 2016-12-07 | 2016-12-14 | 2016-10-03 | 2018-06-29 | 2018-06-29 | Education;#4;#Leisure;#7;#Health;#6 | DBFM | Morrison |  | Nord LB | GTFM
Wester Hailes Healthy Living Centre |  | South East | Gordon Shirreff | 9747349 | Operational (Operational) | NHS Lothian | Community - Community Facility | 2010-10-29 | 2011-08-05 | 2011-08-05 | 2012-01-09 | 2013-09-13 | 2013-06-28 | Health;#6;#Local Authority Offices;#9;#Community;#3 | DBDA | Morrison | City of Edinburgh Council;#8;#NHS Lothian;#38 | Capitally Funded
Wester Hailes Underpass |  | South East | Gordon Shirreff | 709610 | Operational (Operational) | City of Edinburgh Council | Community - Community Facility | 2014-05-16 | 2014-05-22 | 2014-05-22 | 2014-07-28 | 2015-11-23 | 2015-11-23 | Community;#3 | DBDA | Morrison | NHS Lothian;#38 | Capitally Funded
Wick Community Campus incl South PS |  | North | Jonathan Christie | 50501822 | Operational (Operational) | The Highland Council | Schools SSF Rev - Secondary School | 2012-08-15 | 2014-12-19 | 2014-12-19 | 2015-01-01 | 2016-09-16 | 2017-01-10 | Education;#4;#Library;#8;#Leisure;#7;#Café;#1;#Child Care;#2;#Community;#3;#Sports Facilities;#14 | DBFM | Morrison | Highlife Highland;#74 | Aviva | Morrison
Wick North Primary (Noss) |  | North | Jonathan Christie | 15871079 | Operational (Operational) | The Highland Council | Schools - Primary School | 2013-09-06 | 2014-07-04 | 2014-07-04 | 2014-07-04 | 2015-09-14 | 2016-03-30 | Education;#4;#Sports Facilities;#14;#Community;#3;#Child Care;#2;#Leisure;#7 | DBDA | Morrison |  | Capitally Funded
William McIllvaney Campus (prev. East Ayrshire Learning Campus ) |  | South West | Bill Martin | 43108495 | Operational (Operational) | East Ayrshire Council | Schools SSF Rev - Secondary School | 2014-05-12 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2018-03-30 | 2018-03-30 | Education;#4 | DBFM | Kier |  | Nord LB | FES FM
Windygoul Primary School |  | South East | Gordon Shirreff | 3665798 | Operational (Operational) | East Lothian Council | Schools - Primary School | 2014-09-02 | 2015-03-02 | 2015-03-02 | 2014-12-01 | 2015-08-12 | 2015-08-19 | Education;#4 | DBDA | Morrison |  | Capitally Funded
Wishaw Health Centre | NHS Lanarkshire Bundle | South West | Bill Martin | 14570701 | Operational (Operational) | NHS Lanarkshire | Health - Primary Care | 2012-12-05 | 2013-11-15 | 2013-12-19 | 2013-12-19 | 2015-05-15 | 2015-05-15 | Health;#6;#Community;#3 | DBFM | Graham | NHS Lanarkshire;#36 | Aviva | Graham
Woodside Health Centre | Forres, Tain and Woodside Health Centre Bundle | North | Jonathan Christie | 4287311 | Operational (Operational) | NHS Grampian | Health - Primary Care | 2012-05-05 | 2013-03-25 | 2013-03-25 | 2013-04-29 | 2014-04-25 | 2014-06-27 | Health;#6 | DBFM | Morrison | Aberdeen City Council;#1;#NHS Highland;#35 | Aviva | GTFM
Woodside Health Centre (W) | Gorbals and Woodside Health Centre Bundle | West | Bill Martin | 20234360 | Operational (Operational) | NHS Greater Glasgow & Clyde | Health - Primary Care | 2014-05-01 | 2017-04-05 | 2017-04-10 | 2017-02-06 | 2019-05-03 | 2019-05-15 | Health;#6 | DBFM | Morgan Sindall | Glasgow City Council;#22 | Nord LB | Robertson FM
In Construction
Project Title | Bundle | Territory | TPD | Total Project Cost | Project Status | Primary Participant Organisation | Project Type/Sector | Agreed NPR Date | Financial Close - Planned Completion | Financial Close - Actual Completion | Construction - Actual Start | Construction - Planned Completion | Construction - Actual Completion | Services | Contract Type | Tier 1 Construction Contractor | Other Participant Organisations | Funding Partner | Tier 1 FM Contractor
Alness Community Campus | Inverurie, Lossiemouth and Allness Campuses | North | Jonathan Christie | 33766134 | In Construction (In Construction) | The Highland Council | Schools SSF Cap - Secondary School | 2017-06-22 | 2018-08-17 | 2018-10-29 | 2018-06-18 | 2020-04-10 |  | Education;#4;#Community;#3;#Sports Facilities;#14 | DBDA | Kier | The Moray Council;#52;#Aberdeenshire Council;#2 | Capitally Funded
Ayr Grammar Primary School and Nursery Project/Archive/Fine Art Store |  | South West | Bill Martin | 16374620 | In Construction (In Construction) | South Ayrshire Council | Schools - Primary School | 2017-08-17 | 2019-03-01 | 2019-03-18 | 2019-04-01 | 2020-07-17 |  | Library;#8;#Education;#4;#Community;#3;#Museum;#10 | DBDA | Morrison
Ayr Office Rationalisation |  | South West | Bill Martin | 2132637 | In Construction (In Construction) | South Ayrshire Council | Offices - Workshops | 2018-09-25 | 2019-04-08 | 2019-05-22 | 2019-05-22 | 2020-07-31 |  | Offices;#11 | DBDA | Linea
Badenoch & Strathspey | Isle of Skye and the Badenoch/Strathspey bundle | North | Jonathan Christie | 19728835 | In Construction (In Construction) | NHS Highland | Health - Primary Care | 2017-05-31 | 2019-09-06 | 2019-07-02 | 2019-07-29 | 2021-03-01 |  | Health;#6 | DBDA | Balfour Beatty | The Highland Council;#67;#Scottish Ambulance Service;#45 | Capitally Funded
Blackridge Nursery |  | South East | Gordon Shirreff | 1749184 | In Construction (In Construction) | West Lothian Council | Early Years Child Care - Nursery | 2019-05-31 |  |  | 2020-03-16 | 2020-06-19 |  |  | DBDA | Morrison
Brookwood Early Years |  | West | Bill Martin | 3097529 | In Construction (In Construction) | East Dunbartonshire Council | Early Years Child Care - Nursery | 2019-01-21 | 2019-11-13 | 2019-11-13 | 2019-11-15 | 2020-09-30 |  | Education;#4;#Child Care;#2 | DBDA | Robertson
Calderwood Primary School |  | South East | Gordon Shirreff | 14330719 | In Construction (In Construction) | West Lothian Council | Schools - Primary School | 2019-01-31 | 2020-02-21 | 2020-02-21 |  | 2021-07-16 |  |  | DBDA | Morrison
Carnoustie Early Years |  | East Central | Gordon Shirreff | 3463703 | In Construction (In Construction) | Angus Council | Early Years Child Care - Nursery | 2019-05-16 |  | 2019-09-30 | 2019-10-07 | 2020-06-26 |  |  | DBDA | Robertson
Castlebrae/ Craigmillar High School |  | South East | Gordon Shirreff | 28482999 | In Construction (In Construction) | City of Edinburgh Council | Schools - Secondary School | 2019-01-28 | 2019-11-01 | 2019-12-11 | 2020-01-14 | 2021-08-06 |  |  | DBDA | Morrison |  |  | GTFM
Clackmannanshire Primary Schools and Early Years Bundle |  | East Central | Gordon Shirreff | 4866000 | In Construction (In Construction) | Clackmannanshire Council | Early Years Child Care - Nursery | 2018-06-05 | 2018-07-09 |  |  | 2019-10-05 |  | Education;#4 | DBDA | Maxi Construction |  | Capitally Funded
Clydebank Health & Care Centre | Clydebank and Greenock Health Centres with Stobhill Hospital Bundle | West | Bill Martin | 21650200 | In Construction (In Construction) | NHS Greater Glasgow & Clyde | Health - Primary Care | 2015-05-19 | 2019-12-10 | 2019-12-10 | 2019-12-13 | 2021-06-24 |  | Health;#6 | DBFM | BAM |  | Nord LB | FES FM
Early Years - Newton, Kirkmuirhill, Crawfordyke (3 nurseries) |  | South West | Bill Martin | 8135395 | In Construction (In Construction) | South Lanarkshire Council | Early Years Child Care - Nursery | 2018-10-02 | 2019-09-26 | 2019-09-26 | 2019-10-09 | 2020-07-10 |  | Community;#3;#Child Care;#2 | DBDA | Morgan Sindall |  | Capitally Funded
East Whitlawburn Housing / regeneration project |  | South West | Bill Martin | 31345327 | In Construction (In Construction) | South Lanarkshire Council | Community - Residential/Building | 2018-06-08 | 2019-09-12 | 2019-09-26 | 2019-09-27 | 2021-07-26 |  | Community;#3;#Leisure;#7;#Residential;#13 | DBDA | CCG (Cambuslang) |  | Capitally Funded
Forfar Early Years |  | East Central | Gordon Shirreff | 3153247 | In Construction (In Construction) | Angus Council | Early Years Child Care - Nursery | 2019-05-16 |  | 2019-09-30 | 2019-10-07 | 2020-06-26 |  |  | DBDA | Robertson
Forth Valley GP Practice Refurbs |  | East Central | Gordon Shirreff | 805000 | In Construction (In Construction) | NHS Forth Valley | Health - Primary Care | 2015-12-11 | 2018-08-31 | 2017-12-11 |  | 2018-06-30 | 2018-08-25 | Health;#6 | Minor Works |  |  |  | FES FM
Greenock Health & Care Centre | Clydebank and Greenock Health Centres with Stobhill Hospital Bundle | West | Bill Martin | 20815298 | In Construction (In Construction) | NHS Greater Glasgow & Clyde | Health - Primary Care | 2015-05-19 | 2018-12-14 | 2018-12-21 |  | 2020-09-04 |  | Health;#6 | DBFM | BAM |  | Nord LB | FES FM
Hamilton new build housing - Highston Hall |  | South West | Bill Martin | 6303587 | In Construction (In Construction) | South Lanarkshire Council | Community - Residential/Building | 2019-01-31 | 2020-01-17 | 2020-01-20 | 2020-01-31 | 2021-05-30 |  | Residential;#13 | DBDA | Miller Homes |  | Capitally Funded
Housing St Michaels Wind, Kilwinning - Lot D |  | South West | Bill Martin | 12205673 | In Construction (In Construction) | North Ayrshire Council | Community - Residential/Building | 2018-04-05 | 2020-02-28 | 2020-02-06 |  | 2021-06-24 |  | Community;#3;#Residential;#13 | DBDA | Graham
Inverurie Community Campus | Inverurie, Lossiemouth and Allness Campuses | North | Jonathan Christie | 56865201 | In Construction (In Construction) | Aberdeenshire Council | Schools SSF Rev - Secondary School | 2017-05-26 | 2018-03-16 | 2018-04-19 | 2018-04-02 | 2020-02-28 |  | Education;#4;#Health;#6;#Café;#1;#Child Care;#2;#Community;#3;#Leisure;#7;#Library;#8;#Sports Facilities;#14 | DBFM | Robertson | NHS Grampian;#33;#NESCOL;#69;#The Highland Council;#67;#The Moray Council;#52 | Nord LB | FES FM
Isle of Skye Health Centre | Isle of Skye and the Badenoch/Strathspey bundle | North | Jonathan Christie | 20677884 | In Construction (In Construction) | NHS Highland | Health - Primary Care | 2017-05-31 | 2019-09-06 | 2019-07-02 | 2019-08-19 | 2021-04-19 |  | Health;#6 | DBDA | Balfour Beatty | The Highland Council;#67;#Scottish Ambulance Service;#45 | Capitally Funded
Jardine Building - REH Site |  | South East | Gordon Shirreff | 4610000 | In Construction (In Construction) | NHS Lothian | Health - Major Health | 2019-03-18 |  | 2019-05-17 | 2019-05-20 | 2020-09-11 |  |  | DBDA | Morrison
Killermont Early Years |  | West | Bill Martin | 2476148 | In Construction (In Construction) | East Dunbartonshire Council | Early Years Child Care - Nursery | 2019-01-21 | 2019-11-06 | 2019-11-05 | 2019-11-06 | 2020-05-20 |  | Child Care;#2;#Education;#4 | DBDA | Robertson
Largs Housing St Colms/Flatt Road - Lot A |  | South West | Bill Martin | 22847294 | In Construction (In Construction) | North Ayrshire Council | Community - Residential/Building | 2018-07-04 | 2019-06-07 | 2019-06-14 | 2019-06-11 | 2020-05-04 |  | Community;#3;#Residential;#13 | DBDA | Ashleigh Scotland Ltd
Linkwood Primary School |  | North | Jonathan Christie | 12600000 | In Construction (In Construction) | The Moray Council | Schools - Primary School | 2017-05-25 | 2019-01-18 | 2019-02-25 | 2019-03-18 | 2020-06-28 |  | Education;#4;#Child Care;#2;#Sports Facilities;#14 | DBDA | Balfour Beatty |  | Capitally Funded
Lossiemouth Learning Centre | Inverurie, Lossiemouth and Allness Campuses | North | Jonathan Christie | 41817703 | In Construction (In Construction) | The Moray Council | Schools SSF Cap - Secondary School | 2017-06-05 | 2018-09-21 | 2018-12-07 | 2018-10-01 | 2020-08-14 |  | Education;#4;#Community;#3;#Leisure;#7;#Sports Facilities;#14;#Vocational;#19 | DBDA | Balfour Beatty | Aberdeenshire Council;#2;#The Highland Council;#67 | Capitally Funded
Madras College, St. Andrews |  | East Central | Gordon Shirreff | 41900516 | In Construction (In Construction) | Fife Council | Schools - Secondary School | 2017-09-06 | 2019-03-29 | 2019-07-12 | 2019-07-12 | 2020-11-27 |  | Education;#4 | DBDA | BAM |  | Capitally Funded
Menstrie Early Years |  | East Central | Gordon Shirreff | 1975000 | In Construction (In Construction) | Clackmannanshire Council | Early Years Child Care - Nursery | 2019-02-01 |  | 2019-06-27 |  | 2019-12-09 |  |  | DBDA | Maxi Construction
NAC ASN |  | South West | Bill Martin | 28203953 | In Construction (In Construction) | North Ayrshire Council | Schools - ASN | 2018-05-22 | 2019-06-12 | 2019-06-26 | 2019-07-08 | 2020-11-20 |  | Education;#4;#Community;#3;#Residential;#13 | DBDA | Morrison
NAC Housing Various Locations - Lot B |  | South West | Bill Martin | 20366517 | In Construction (In Construction) | North Ayrshire Council | Community - Residential/Building | 2018-03-26 | 2020-02-01 | 2020-01-30 | 2020-02-17 | 2021-03-31 |  | Residential;#13;#Community;#3 | DBDA | Ashleigh Scotland Ltd
NLC Early Years New Build Nurseries(9 No locations) |  | South West | Bill Martin | 15685622 | In Construction (In Construction) | North Lanarkshire Council | Early Years Child Care - Nursery | 2018-09-04 | 2019-10-25 | 2019-10-25 | 2019-11-01 | 2020-07-31 |  | Child Care;#2;#Education;#4 | DBDA | Morgan Sindall
NLC Modular Buildings(kier hardie,our lady &st francis) |  | South West | Bill Martin | 784061 | In Construction (In Construction) | North Lanarkshire Council | Schools - Primary School | 2019-06-17 | 2020-01-21 | 2020-01-21 |  | 2020-06-12 |  | Education;#4 | DBDA | Portacabin |  | Capitally Funded
NLC Welfare Unit |  | South West | Bill Martin | 505137 | In Construction (In Construction) | North Lanarkshire Council | Community - Transport | 2019-06-17 | 2020-02-28 | 2020-02-28 |  | 2020-06-26 |  |  | DBDA | Wernick |  | Capitally Funded
Orbiston Workshops (Phase 2) |  | South West | Bill Martin | 2395653 | In Construction (In Construction) | North Lanarkshire Council | Offices - Workshops | 2019-06-03 | 2020-03-18 | 2020-03-18 |  | 2020-10-27 |  | Offices;#11 | DBDA | Robertson
Rising Rolls 7 |  | South East | Gordon Shirreff | 1978562 | In Construction (In Construction) | City of Edinburgh Council | Schools - Primary School | 2019-05-31 | 2020-02-07 | 2020-01-07 | 2020-01-07 | 2020-08-07 |  |  | DBDA | Morrison
South Queensferry High School |  | South East | Gordon Shirreff | 39978000 | In Construction (In Construction) | City of Edinburgh Council | Schools SSF Rev - Secondary School | 2017-03-31 | 2018-05-31 | 2018-06-14 | 2018-06-30 | 2020-03-31 |  | Education;#4 | DBFM | Morrison |  | TBC | GTFM
Southbank Road Early Years |  | West | Bill Martin | 3154206 | In Construction (In Construction) | East Dunbartonshire Council | Early Years Child Care - Nursery | 2019-01-21 | 2019-11-06 | 2019-11-05 | 2019-11-06 | 2020-09-13 |  | Education;#4;#Child Care;#2 | DBDA | Robertson
St Joseph's Early Years |  | West | Bill Martin | 3490909 | In Construction (In Construction) | East Dunbartonshire Council | Early Years Child Care - Nursery | 2019-01-21 | 2019-11-06 | 2019-11-05 | 2019-11-06 | 2020-07-13 |  | Child Care;#2;#Education;#4 | DBDA | Robertson
St. Mary's Nursery |  | South East | Gordon Shirreff | 1200000 | In Construction (In Construction) | West Lothian Council | Early Years Child Care - Nursery | 2018-12-20 | 2019-10-07 |  | 2020-02-10 | 2020-05-01 |  |  | DBDA | Morrison
Stobhill Mental Health | Clydebank and Greenock Health Centres with Stobhill Hospital Bundle | West | Bill Martin | 10599977 | In Construction (In Construction) | NHS Greater Glasgow & Clyde | Health - Primary Care | 2017-04-14 | 2018-12-14 | 2018-12-20 | 2019-01-21 | 2020-06-19 |  | Health;#6 | DBFM | BAM |  | Nord LB | FES FM
Tayside Cuisine |  | East Central | Gordon Shirreff | 1550240 | In Construction (In Construction) | Dundee City Council | Schools - Free School Meals | 2019-01-10 |  | 2019-11-15 | 2019-11-18 | 2020-04-06 |  |  | Minor Works | FES FM
In Development
Project Title | Bundle | Territory | TPD | Total Project Cost | Project Status | Primary Participant Organisation | Project Type/Sector | Agreed NPR Date | Financial Close - Planned Completion | Financial Close - Actual Completion | Construction - Actual Start | Construction - Planned Completion | Construction - Actual Completion | Services | Contract Type | Tier 1 Construction Contractor | Other Participant Organisations | Funding Partner | Tier 1 FM Contractor
All Saints and St Rochsolloch PS Classroom Extensions |  | South West | Bill Martin | 972000 | In Development (Stage 1) | North Lanarkshire Council | Schools - Primary School | 2019-08-20 |  |  |  | 2020-07-31 |  | Education;#4 | DBDA | Linea |  | Capitally Funded |  | TBC
Alloa Active Travel Hub |  | East Central | Gordon Shirreff | 200000 | In Development (Stage 1) | Clackmannanshire Council | Community - Transport | [7 empty] | Minor Works |  |  |  |  | TBC
Auldkirk Road, Cambuslang - New Build Housing |  | South West | Bill Martin | 7346826 | In Development (Stage 2) | South Lanarkshire Council | Community - Residential/Building | 2019-01-31 | 2020-03-17 |  |  | 2021-03-30 |  | Residential;#13 | DBDA | Cruden |  | Capitally Funded
Blairgowrie Recreation Centre |  | East Central | Gordon Shirreff | 14700000 | In Development (Stage 1) | Perth & Kinross Council | Community - Community Facility | 2019-01-10 | 2020-05-14 |  |  | 2022-01-20 |  | Community;#3;#Leisure;#7;#Education;#4;#Offices;#11;#Sports Facilities;#14 | DBDA | TBC
Burns House Demolition |  | South West | Bill Martin | 600000 | In Development (Stage 1) | South Ayrshire Council | Community - Community Facility | 2020-01-30 | 2020-07-01 |  |  |  |  | Community;#3;#Local Authority Offices;#9 | DBDA | TBC
Carbroe and Sikeside Primary Schools Campus |  | South West | Bill Martin | 19510925 | In Development (Stage 1) | North Lanarkshire Council | Schools - Primary School | 2020-05-12 | [6 empty] | DBDA | Morgan Sindall |  | Capitally Funded
Countesswells Primary School |  | North | Jonathan Christie | 16534100 | In Development (Stage 2) | Aberdeen City Council | Schools SSF Cap - Primary School | 2019-03-29 | 2020-03-27 |  |  | 2021-09-30 |  |  | DBDA | Morrison |  | Capitally Funded
Cowie Community Hub |  | East Central | Gordon Shirreff | 1425000 | In Development (Stage 2) | Stirling Council | Community - Community Facility | 2019-08-28 |  |  |  | 2020-11-30 |  | Library;#8 | DBDA
Fife Early Years |  | East Central | Gordon Shirreff | 8727966 | In Development (Stage 2) | Fife Council | Early Years Child Care - Nursery | 2018-11-15 | 2019-09-01 |  |  | 2020-07-25 |  | Education;#4 | DBDA
Gullane Primary School Extension |  | South East | Gordon Shirreff | 5123984 | In Development (Stage 1) | East Lothian Council |  |  | 2019-08-21 |  |  | 2020-08-07 |  |  | DBDA | Graham
Larkfield Children's Centre |  | West | Bill Martin | 2786865 | In Development (Stage 2) | Inverclyde Council | Early Years Child Care - Nursery | 2019-02-15 | 2020-03-22 |  |  | 2020-12-20 |  | Child Care;#2 | DBDA | CCG
Lochshore Leisure hub (leisure) |  | South West | Bill Martin | 4599262 | In Development (Stage 2) | North Ayrshire Council | Community - Leisure/Culture | 2018-09-21 | 2020-12-14 |  |  | 2021-12-01 |  | Leisure;#7;#Community;#3;#Sports Facilities;#14 | DBDA | CCG (Cambuslang)
Mainholm new build housing |  | South West | Bill Martin | 33217788 | In Development (Stage 1) | South Ayrshire Council | Community - Residential/Building | 2020-01-30 | 2021-01-29 | [5 empty] | DBDA | Ashleigh Scotland Ltd
Newmains and St Brigid's Primary Schools Shared Campus |  | South West | Bill Martin | 20013764 | In Development (Stage 1) | North Lanarkshire Council | Schools - Primary School | 2019-11-01 | 2021-02-05 |  |  | 2022-12-06 |  |  | DBDA | BAM |  | Capitally Funded
North East Hub |  | West | Bill Martin | 50839137 | In Development (Stage 2) | NHS Greater Glasgow & Clyde | Health - Primary Care | 2019-10-11 | 2021-07-28 |  |  | 2023-10-01 |  | Health;#6;#Community;#3 | DBDA | BAM | Glasgow City Council;#22 | Capitally Funded
Paisley Learning and Cultural Hub |  | West | Bill Martin | 4527654 | In Development (Stage 2) | Renfrewshire Council | Community - Community Facility | 2018-06-01 | 2020-05-31 |  |  | 2021-02-11 |  | Community;#3;#Library;#8 | DBDA | CCG
Park Farm/Rainbow Family Centre |  | West | Bill Martin | 2090391 | In Development (Stage 2) | Inverclyde Council | Early Years Child Care - Nursery | 2019-03-29 | 2020-06-12 |  |  | 2020-12-22 |  | Child Care;#2 | DBDA | CCG
Perth City Hall |  | East Central | Gordon Shirreff | 21004787 | In Development (Stage 2) | Perth & Kinross Council | Community - Community Facility | 2017-12-18 | 2019-08-29 |  |  | 2021-04-07 |  | Community;#3;#Museum;#10;#Leisure;#7 | DBDA | BAM |  | Capitally Funded | TBC
Perth Collections Store |  | East Central | Gordon Shirreff | 4500000 | In Development (Stage 1) | Perth & Kinross Council | Community - Community Facility | 2019-05-31 | [5 empty] | Community;#3 | DBDA | Pre-NPR |  | Capitally Funded | TBC
Perth High School |  | East Central | Gordon Shirreff | 45000000 | In Development (Stage 1) | Perth & Kinross Council | Schools - Secondary School | 2018-04-19 | 2020-07-25 |  |  | 2022-08-15 |  | Education;#4;#Sports Facilities;#14 | DBDA | Robertson
Prestwick Educational Campus |  | South West | Bill Martin | 17346026 | In Development (Stage 2) | South Ayrshire Council | Schools SSF Cap - Primary School | 2019-05-31 | 2020-10-02 |  |  | 2022-03-11 |  | Child Care;#2;#Community;#3;#Education;#4 | DBDA | Morgan Sindall
Prestwick Housing - Main Street |  | South West | Bill Martin | 1600000 | In Development (Stage 1) | South Ayrshire Council | Community - Residential/Building | 2019-08-08 | 2020-05-31 |  |  | 2021-06-26 |  | Residential;#13 | DBDA | Ashleigh Scotland Ltd |  | Capitally Funded
Riverside Development |  | South West | Bill Martin | 2000000 | In Development (Stage 1) | South Ayrshire Council | Community - Leisure/Culture | 2019-09-11 | 2020-08-30 |  |  | 2021-09-01 |  |  | DBDA | Linea |  | Capitally Funded
Riverside Housing |  | South West | Bill Martin | 10594690 | In Development (Stage 1) | South Ayrshire Council | Community - Residential/Building | 2020-01-30 | 2021-01-29 | [5 empty] | DBDA | Ashleigh Scotland Ltd
Ross High School Extension |  | South East | Gordon Shirreff | 5427660 | In Development (Stage 1) | East Lothian Council | Schools - Secondary School | 2018-12-20 |  |  |  | 2020-07-17 |  |  | DBDA | Graham
Sacred Heart Primary School, Girvan |  | South West | Bill Martin | 3600000 | In Development (Stage 1) | South Ayrshire Council | Schools - Primary School | 2019-09-20 | 2021-01-08 |  |  | 2022-01-21 |  | Community;#3 | DBDA | Morrison |  | Capitally Funded
South Ayrshire Combined Campus (Carrick) |  | South West | Bill Martin | 42625000 | In Development (Stage 1) | South Ayrshire Council | Schools SSF Cap - Primary School & Secondary School | 2019-05-31 | 2020-08-30 |  |  | 2022-07-31 |  | Community;#3;#Education;#4;#Child Care;#2;#Sports Facilities;#14;#Vocational;#19 | DBDA | Morgan Sindall
Sports Pitch Replacement Ph2 | Falkirk Sports Pitch Replacement | East Central | Gordon Shirreff | 657503 | In Development (Stage 2) | Falkirk Council | Community - Community Facility | 2019-01-21 | 2019-08-29 | 2019-03-22 | 2019-03-25 | 2019-05-31 | 2019-09-13 | Leisure;#7;#Community;#3 | Minor Works | WH Malcolm
Tom Johnston House Redevelopment |  | West | Bill Martin | 11837851 | In Development (Stage 2) | East Dunbartonshire Council | Community - Residential/Building | 2018-10-31 | 2020-05-30 |  |  | 2021-07-20 |  | Residential;#13 | DBDA | CCG |  | Capitally Funded
Torry Community Campus |  | North | Jonathan Christie | 20754200 | In Development (Stage 2) | Aberdeen City Council | Schools SSF Cap - Primary School | 2019-03-29 | 2020-03-27 |  |  | 2021-12-17 |  | Café;#1;#Community;#3;#Leisure;#7 | DBDA | Morrison |  | Capitally Funded
Wallyford High School |  | South East | Gordon Shirreff | 41653855 | In Development (Stage 2) | East Lothian Council | Schools - Secondary School | 2019-06-14 | 2020-08-03 |  |  | 2020-12-31 |  |  | DBDA | Morrison |  | Capitally Funded
Winchburgh Core Schools Development |  | South East | Gordon Shirreff | 60167764 | In Development (Stage 2) | West Lothian Council | Schools SSF Cap - Primary School & Secondary School | 2019-06-26 | 2020-04-27 |  |  | 2022-07-01 |  |  | DBDA | Morrison
Craigbank & Glengonner New Build Housing |  | South West | Bill Martin | 9722626 | In Development (On Hold) | South Lanarkshire Council | Community - Residential/Building | 2019-01-07 | 2020-01-17 | [5 empty] | DBDA | Cruden
HQ Office Accommodation & Civic Centre |  | East Central | Gordon Shirreff | 17500000 | In Development (On Hold) | Falkirk Council | Community - Residential/Building | 2015-05-21 | [6 empty] | DBDA | Robertson
North Berwick H.S. Sports Block |  | South East | Gordon Shirreff | 3626000 | In Development (On Hold) | East Lothian Council | Schools - Secondary School | 2018-12-20 | 2019-09-02 |  |  | 2020-07-17 |  |  | DBDA | Graham
Polmaise Depot |  | East Central | Gordon Shirreff | 6227285 | In Development (On Hold) | Stirling Council | Community - Community Facility | 2018-04-18 | 2019-01-15 |  |  | 2019-06-07 |  |  | Minor Works | Ogilvie
Royal Edinburgh Mental Health - Phase 2 DBDA |  | South East | Gordon Shirreff | 62200000 | In Development (On Hold) | NHS Lothian | Health - Major Health | 2015-06-22 | 2018-09-28 |  |  | 2020-07-31 |  |  | DBDA | Morrison